# United Nations Development Group Iraq Trust Fund

# Project #: E4-08

# Date and Quarter Updated: 1 July 2008 - Q2 2008

| Participating UN Organisation: UNDP | Sector: Infrastructure Rehabilitation |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Electricity |

| Title | Rehabilitation of Taji Gas Power Station |
| --- | --- |
| Location | Taji, Baghdad Governorate |
| Project Cost | US$ 25,891,860 |
| Duration | 22 months (as in project document) |
| Approval Date (SC) | 22.07.2004 | Starting Date | November 2004 | Completion Date | March 2006 (ext 30 Nov 2008) |
| Project Description | The technical rehabilitation of existing 3 x 20 MW units No. 4, 6 and 7 will complete the comprehensive refurbishment of the entire Plant as the replacement of the other 4 existing units No.1, 2, 3 and 5 will be carried out under a separate bilaterally funded Project. Implementation of the Project will result in reinstatement of their design capacity, significant extension of the operational life span of existing units and will increase the overall output of the Plant by 50 MW. |

# Development Goal and Immediate Objectives

1 To respond to the immediate humanitarian needs of the war-affected Iraqi people by ensuring the supply of reliable and safe electricity to permit operation of essential humanitarian services such as water supply, hospitals, schools, sewage treatment plants and other community services. 2 The generating capacity, availability and reliability of Taji Gas Power Station (Units No.4, 6 and 7) increased. 3 The plant management and staff able to operate and maintain the units in accordance with international standards.

# Outputs, Key activities and Procurement

| Outputs | 1.1 Gas units 4; 6 and 7 at Taji GPS rehabilitated with increased operational reliability. 2.1 Set of selected, essential spare parts supplied to Taji GPS, which will be available in stock for emergency repairs and routine maintenance - in order to improve the reliability of generation. 3.1 Trained a substantial number of Plant engineers, who will be able to operate and maintain the power plant for higher levels of performance and also in turn would be able to train other junior technical personnel (engineers and technicians).. |
| --- | --- |
| Activities | 1.1.1 Implementation of scheduled rehabilitation works to all 3 units (No. 4, 6 and 7). 2.1.1 Provision of the set of specified spare parts and relevant rectification of selected components coming from the all disassembled units. 3.1.1Implementation of the relevant training process carried out both at site and at the Manufacturer’s workshop. Trained a substantial number of Plant engineers, who will be able to operate and maintain the power plant for higher levels of performance and also in turn would be able to train other junior technical personnel (engineers and technicians). |
| Procurement (major items) | Generator rotor Generator rotor bearings |

| Funds Committed | US$ 25,586,911 | % of approved | 99% |
| --- | --- | --- | --- |
| Funds Disbursed | US$ 24,426,986 | % of approved | 94.34% |
| Forecast final date | June 2008 | Delay (months) | 21 |

# Quantitative achievements against objectives and results

| Spare parts and equipment | All the shipments of material have been delivered at site within schedule and are stored | % of planned | 100% |
| --- | --- | --- | --- |
| Drawings, manuals and test certificates | Drawings and manuals delivered, Certificate of Substantial Completion signed. | % of planned | 100% |
| Training of Trainers | 12 Taji site engineers have received extensive training at the manufacturer’s facility in Japan. | % of planned | 100% |
| Pre-shipment inspection. | Coordination and supervision of factory-witness tests in Japan of selected equipment successfully completed during March – April 06. | % of planned | 100% |

# Qualitative achievements against objectives and results

Rehabilitation of Unit 1, 4 & 6 has been completed, including performance tests and final certified completion. In 2006, the gas pipeline supplying fuel to Taji Power Station was sabotaged. With modifications, alternative fuel was used and rehabilitation progressed steadily. However, operation cannot be optimal unless the pipeline is repaired. On 14 January 2007, approx 15 km from the power plant, 4 subcontractor employees at Taji were kidnapped and murdered. Work was suspended for several weeks and brought about delay to substantial completion, which has now been reached. However, latest delivery at the request of the beneficiaries is expected by June 2008. Additional works to convert fuel firing from gas to oil are completed on unit 1 and will start on unit 6 Follow-up monitoring indicates Unit No. 1 has been running satisfactorily on oil during May 2008 at 18MW