SEVENTH Six-month progress report for project

# REPORT COVER PAGE

| ## Participating UN Organization: |  | ## Cluster: |
| --- | --- | --- |
| UN HABITAT |  | Infrastructure Rehabilitation |

| ## Project No. and Project Title: |  | ## Report Number: |
| --- | --- | --- |
| E4-14 Rehabilitation of Community Facilities and Infrastructure |  | 5 |

| ## Reporting Period: |  | ## Project Budget: |
| --- | --- | --- |
| 1 July to 31 December 2007 |  | UNDG ITF: $ 16,025,007 |

| ## List Implementing Partners: |  | ## Project Coverage/Scope: |
| --- | --- | --- |
| - Ministry of Construction and Housing, Ministry of Municipalities and Public Works, Ministry of Health, Ministry of Labour and Social Affairs, Local Municipal Councils, Iraqi Contractors and Consultants, |  | Baghdad, Basrah, Samawa, Najaf and Erbil |

| ## Abbreviations and acronyms: |  | ## Project Duration/Closed Project: |
| --- | --- | --- |
| MoCH: Ministry of Construction and Housing MoMPW: Ministry of Municipalities and Public Works DoH : Directorate of Health BoQ: Bill of Quantities MoH : Ministry of Health HQ : Headquarters |  | 34 months (September 2005 to 30 June 2008). Ongoing Budget was first revised and approved by ITF, for: - Extension of project duration; - Movement of funds between project budget components; and - Change of project scope |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

The main objective of the project is to improve the living conditions of the most vulnerable groups in Iraqi Society, primarily the urban poor, women- headed households and/or persons living in disadvantaged neighbourhoods of Iraq Cities and Towns.

Immediate Objectives:

- To improve housing conditions for 2,000 families (15,000 persons and 1,100 orphans)

- To improve the living environment in 8 urban areas (650,000 persons) by rehabilitating water supply & sewerage system and re-establishing solid waste disposal systems.

- To contribute to the promotion of community based approaches to the operation and maintenance of basic services.

- To assist in reducing the level of unemployment in Iraq by expanding employment opportunities in the construction sector.

Outputs:

The main outputs as per the approved project document are as follows:

- Housing conditions improved for 2,000 vulnerable families (15,000 persons) and adequate shelter and ancillary facilities provided for about 1,100 orphans.

- Improved water supply and sanitation infrastructure in 8 urban areas benefiting about 650,000 persons.

- Community based approaches to solid waste management in place.

- Job opportunities for about 3,000 construction workers on average during the implementation phase of the project (amounting to about 570,000 person days of direct employment).

Outcomes:

- Improved housing, water & sanitation infrastructure, and consequently living conditions for vulnerable groups (urban poor, women, orphans and other disadvantaged segments of the Iraqi society in the 5 targeted governorates).

- Reduced poverty levels through employment generation in the targeted governorates.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

The project is an integral component of the Programme being implemented by the Infrastructure Cluster within the framework of the UN Assistance Strategy for Iraq. The project will contribute to the achievement of at least three objectives which are outlined in the Cluster E strategic plan, to improve shelter conditions for vulnerable groups, increase access to potable water in urban areas and increase solid waste collection and disposal

- UN Millennium Development Goals,

The project is addressing Millennium Development Goal 7, Targets 10 and 11, which aim to ensure environmental sustainability through the following actions: (1) reduce by half the proportion of people without sustainable access to safe drinking water, and (2) achieve significant improvement in the lives of at least 100 million slum dwellers by 2020.

- Joint Needs Assessment ,

The project responds to the immediate needs (2004) & the medium–term priorities (2005- 2007) through the following approaches:

      - Provide quick, nationwide employment opportunities for the   unemployed

and vulnerable groups through labor-intensive reconstruction &

rehabilitation schemes and through community development projects.

      - Raise potable water access in urban areas by 15 percent and in rural areas

to 25 percent.

      - Raise sanitation coverage by 30 percent in urban areas and by 30 percent

in rural areas.

      - Reduce water loss by 20 percent.

      - Initiate a two-year programme for the rehabilitation and reconstruction of       war-damaged houses.

      - Initiate a fifteen-year urban upgrading programme that addresses the needs

of low –income social groups living in substandard neighborhoods.

- Iraqi National Development Strategy ,

The project is responding to the NDS goals of improving living conditions: Goal 5 - Reduce maternity deaths, Goal 6 - Full access to water and health services, Goal 7 - Descent housing for all.

  - Indicate the main implementing partners, their roles and responsibilities,          and their interaction with the Agency

UN-HABITAT is working closely with various partners in project implementation, as follows:

- The municipal councils for residential areas, representatives of the local water & sewerage authorities in each targeted governorate, and representatives of the Directorate of Health (DoH) in Samawa, in participating in  frequent field visits in collaboration with UN-HABITAT consultant engineers. These partners continue to be involved in all procedures relating to identification of neighbourhoods & public facilities, bid opening, supervision of the works, and final approval of the delivered work. Also, representatives from Baghdad Mayoralty are involved in the process of proposing & approving technical specifications of the cleaning & inspection equipment for Baghdad sewerage network.

- Local contractors in order to maximize the employment impact of the project.

- Local consultants and engineers, who are engaged to conduct technical assessments of scope of work, prepare bidding documents and undertake tender opening processes.  These consultants also supervise, follow up & control the rehabilitation works according to tender based requirements including:  quality of work & compliance with technical specifications and quantities according to the approved BoQ, and timely completion of works.

4. International suppliers for procurement of technical equipment, tools & instruments

# Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

Operations: 2, supported by 19 national field personnel.

Programme: 4

  - International Staff: Provide details on the number and type (operation/programme)

Operations: 2 (part time)

Programme: 1 (part time)

# Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- UN-HABITAT national consultants, with the active participation of representatives from the Municipal Councils, the Ministry of Health (MoH), and the Water & Sewerage Local Authorities, carry out a detailed assessment of the facility to be rehabilitated. An assessment report is prepared, which forms the basis for discussion among all stakeholders to agree on the needs and priorities. As soon as consensus is reached on the broad scope of the rehabilitation works, Bills of Quantities are prepared by the field personnel to give detailed scope of work and specifications.

- The Bills of Quantities and the technical specifications are sent to UN-HABITAT Office in Amman for review by the Rehabilitation Team. Once approved, the Rehabilitation Expert authorizes the preparation of tender documents. The rehabilitation works are packaged into small contracts - typically between $50,000 and $150,000 in size - that can be carried out by small Iraqi Contractors.

- UN-HABITAT maintains a register of close to 900 Iraqi Contractors with different specialties and grades. Bidders are selected from contractors’ database based on specially set criteria. Normally, between 10 and 20 Iraqi contractors are invited to tender for each rehabilitation contract depending on the estimated amount of each contract.

- Implementation supervision is carried out on a daily basis by UN HABITAT field Consultant Engineers.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

- The tender evaluation process incorporates a system of checks and balances with a clear segregation of functions. Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate Tender Evaluation Committee. A separate technical team based in Erbil/Iraq prepares the Agency estimated cost (“Agency Estimate”) for each contract, using a specifically designed database system, which generates priced Bill of Quantities using monthly updated market prices. Prices of materials and labour are regularly compared with that collected by other UN agencies.

- For contracts, which exceed $150,000 the tender evaluation report is subject to review and approval by the Local Contracts Committee of the United Nations Office in Nairobi (UNON). Contracts less than $150,000 are locally reviewed and approved by the Programme Manager under the terms of a special delegation of authority.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

- The rehabilitation works are supervised and monitored by Iraqi national consultants. The progress of works is monitored and approved through time-series photographs, daily briefings from the consultants, videos & telecommunication, and laboratory test reports for quality control of construction materials. In addition, initial handing over certificate is issued upon completion & receipt of the rehabilitated facility by the direct beneficiaries.

- Interim payments are only released to the contractor upon certification of the work progress and quality by the Senior Engineer & the Rehabilitation Expert in Amman Office, financial certification by the Programme Management Officer and finally approval by Programme Manager before being sent to HQ for processing.

- Liquidated damages are applied for any unjustified work delay and violation of other contract provisions.

- During the maintenance period, constant surveillance of the implemented work is carried out by the field personnel to guarantee implementation sustainability and defects repair. This is further substantiated through interviews with local authority staff and beneficiaries on their perceived quality of works. All contracts incorporate defects liability clause so that any defects, which emerge after completion have to be repaired by the contractor.

- Before the rehabilitated facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the Local Authority, the beneficiaries, the relevant department of the government and UN-HABITAT staff and consultants. The final payment is not released until the Acceptance Committee certifies that all work has been satisfactorily completed.

  - Report on any assessments, evaluations or studies undertaken

A third party evaluation of procurement practices was carried out during the reporting period.  The recommendations of the evaluation have since been implemented.

# Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

- During the reporting period, the total housing rehabilitation progress in all governorates has reached 97% representing 2,385 out of 2,460 houses contributing in achieving the immediate objective No. 1 and also benefiting 385 families more than that planned. (2,695 persons).

- The rehabilitation of water facilities (treatment plants, water compact units, and storage tanks,) has been completed in full, thus achieving the immediate objectives 2 & 3.

- Construction of storm water networks and disposal pumping stations in Samawa, Basrah & Baghdad has reached to 85% by the end of December contributing in achieving immediate objectives 2 & 3.

- Supply of equipment for solid waste management in Basrah has been completed achieving the immediate objectives 2 & 3.

- By the end of the reporting period the total casual employment generated through rehabilitation works under the project has reached 224,681 person-days

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

- Enhanced quality of life through improved housing conditions for 2,385 vulnerable families (around 16,700 persons) in 5 governorates.

- Improved access to drinking water in Basrah & Samawa cities, outskirts, and villages by rehabilitation of 15 water facility during the reporting period resulting in upgrading the water supply capacity of 1000 M3/hr in Basra and 4,500 M3/hr in Samawa also through the replacement of old pumps with new pumps of a larger capacity.

- Improved quality of water production in existing water treatment plants in Samawa by replacement of sand & gravel in the filters in addition to replacement of old scrapers in the settling tanks.

- Improved sanitation services in Samawa & Basrah cities by constructing new storm water networks in 6 neighbourhoods in addition to construction of 2 new disposal pumping stations.

- Improved garbage collection system for Basrah city through the increase in fleet capacity by 52 ton of municipal waste per day.

- Enhanced public facilities and services in Samawa city through the rehabilitation & construction of 2 hospitals, 1 primary health centre, and 1 youth centre.

- Employment generation of 9,681 person-days during the reporting period contributing so far to total employment generation of 224,681 persons-days.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

- Housing: In Baghdad, renovation works for 107 houses was completed during the reporting period benefiting about 750 people. The total number of completed works to 374 (out of 449) houses achieving 83% of the targeted number.

- Water & Sanitation: Rehabilitation of 2 water treatment plants in Samawa and 13 potable water compact units in Basrah villages.  With this, 100 % of the total planned rehabilitation works is now complete, benefiting over 610,000 of the population. Further, progress in the rehabilitation of the remaining sewerage storm water networks in Samawa has reached 75%.

- Public Facilities: Rehabilitation of hospitals, health centres, orphanage centre, and youth centre has reached 87 % completion benefiting approximately 203,000 persons of all levels of the local community.

- Supply of equipment, tools, and instruments for municipal services: Supply of garbage collectors & tippers was completed benefiting a total population of 104,000, while procurement process was initiated for the inspection system of sewerage, comprising cleaning tools & safety equipment for Baghdad Sewerage Directorate.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

The implementation of the various rehabilitation works has been delayed, largely due to security-linked constraints.  Further the supply of equipment has been affected by difficulties in border crossing and in obtaining customs clearances from the Iraqi authorities. Moreover, there were difficulties in importing some of the major items particularly for the construction of storm water networks and the paving of asphalt due to shortage of raw materials in the local market.

The implementation experience of this project has provided the following significant lessons:

Implementation planning of rehabilitation works:  Most rehabilitation works have taken much longer than planned due to security-related problems.  This experience has helped to plan the implementation schedules more realistically, factoring in such unanticipated delays. Offshore procurements were also delayed due to long procedure in obtaining the customs clearances, and transportation of goods cross border or through Umqasir port.

Fluctuations of market price:  Market prices of both labour and materials have been extremely volatile, affecting the final cost of the projects and scope of the project. UN-HABITAT is now considering carrying out sensitivity analyse of different design and technology options, so as to mitigate the problems resulting of unexpected price variations.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The project is being implemented in collaboration with the Municipal Councils in each governorate, the Water & Sewerage Authorities and the Directorate of Health in Samawa. These partners are involved in all stages of the project cycle, such as selection and prioritisation of educational facilities for rehabilitation, procurement and contracting, implementation supervision, in addition to final approval of works and supplies.  This has helped to ensure transparency, and foster a greater sense of responsibility and commitment amongst our counterparts.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The specific achievements regarding various cross cutting themes are as follows:

Security: Nothing substantive.  At the same time, despite security constraints and unforeseen delays, the project achieved 80% completion at the end of the reporting period.

Gender and Human Rights: The project addressed issues of human rights & gender equality taking into consideration the different needs, interests and conditions of women and men, in the design, implementation, monitoring and evaluation of the project activities.  The project has so far secured shelter, water & sanitation services for a vulnerable segment of the society in addition to its contribution to reducing mortality and improving maternity & infant’s health facilities.

Employment: The project has, until the end of the reporting period, generated local employment of 224,681 persons-days, of which 9,681 person-days were generated over the last six months.  At the same time it has contributed to significant capacity development of 11 new local contractors during the reporting period.

Environment: Through expanded access to potable water, the project has indirectly and potentially contributed towards environmental & health improvement, with more cleaning activities being undertaken.  Through improved sanitation facilities, the project has contributed directly to urban environmental & health improvement resulting in reduction of water-borne diseases. The supply of garbage collectors has increased systematic garbage collection and directly contributed to improvements in environmental health conditions.

# Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

    - The rehabilitation of 75 remaining houses in Baghdad will be completed and handed over to the beneficiaries.

    - The rehabilitation of storm water networks and re-asphalting of access roads will be completed in 3 neighbourhoods in Samawa.

    - The expansion & rehabilitation of two Hospitals (Maternity and Children Hospital & Rumaitha Public Hospital) in Samawa will be completed.

    - The procurement of CCTV inspection system, cleaning tools and safety equipment for the municipal sewerage services will achieve significant progress.