- United Nations Development Group Iraq Trust Fund

- Project #:F8-08

- Date and Quarter Updated: 2nd quarter, April-June 2009

| Participating UN Organisation: UNOPS | Sector: Human Rights Portfolio |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Ministry of Human Rights |  |

| Title | Support to MoHR in Techniques for Mass Grave Excavation and Identification of Missing Persons |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Geographic Location | Baghdad and mass grave sites particularly in Anbar area |  |  |  |  |
| Project Cost | US $ 974,182 |  |  |  |  |
| Duration | 12 months |  |  |  |  |
| Approval Date (SC) | 01 March 2009 | Starting Date | February 2009 | Completion Date | February 2010 |
| Project Description | Between 300,000 and 2 million persons in Iraq are still missing from the Iran-Iraq War of 1980-88, 1990-91 Gulf War, pre-2003 regime crimes, and post-2003 conflict. In addition, since 2003 the Baghdad Medico-Legal Institute (MLI) reports that it receives on average 800 bodies per month, of which a significant proportion remain unidentified due to inadequate technical and forensic equipment. Currently, only one team of 25 persons from MoHR has been trained on techniques related to the excavation of mass graves and forensic and DNA analysis. This project will support the development of Iraq’s capacity to address the large numbers of missing persons through building further capacity within MoHR, including the exhumation of Kuwaiti missing POWs. |  |  |  |  |

- Development Goal and Immediate Objectives

The project contributes to achieving the following development goals and objectives relevant to Iraq: Iraqi National Development Strategy (NDS): 8.1.1. National dialogue and reconciliation 8.3 Human Rights Goal: Uphold and protect human rights, establish the rule of law, and overcome the legacy of the recent and distant past 8.3.1 Establish a comprehensive human rights regime country wide International Compact with Iraq (ICI): Although there is not specific benchmark, the project addresses: 3.1.1 National dialogue and reconciliation 3.3 Uphold and protect human rights, establish the rule of law, and overcome the legacy of the recent and distant past Protection Sector Team Outcome(s): 1. Improved protection of civilians throughout Iraq and creation of an environment which contributes to the observance of human rights for all Iraqis and mitigates the effects of forced displacement Integrated Programme/Project Outcome(s): 1. The government of Iraq is better able to protect Human Rights in relation to identification of missing persons.

| - Outputs, Key activities and Procurement |  |
| --- | --- |
| Outputs | Output 1: Improved capacity of MoHR to undertake the excavation of mass graves Output 2: Improved capacity of MoHR to perform identification of human remains |
| Activities | For Output 1: - Identification of the trainees - Organizing and conducting the training - Purchase required equipment to undertake excavation - Site assessment, including electronic survey mapping - Site recording including crime scene photography and the role of exhibit officer Site excavation For Output 2: - Examination of remains including storage, anthropological examination, data recording and management - Electronic survey data collection Ante mortem data collection |
| Procurement (major items) | Procurement of ICMP contract to build Iraqi MoHR’s capacity to undertake the excavation of mass graves and to perform identification of human remains |

| Funds Committed | 729,823.46 USD $ | % of approved | 74.92% |
| --- | --- | --- | --- |
| Funds Disbursed | 409,708.82 USD $ | % of approved | 42.06% |
| Forecast final date | February 2010 | Delay (months) |  |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men |  |  |
| Women |  |  |
| Children |  |  |
| IDPs |  |  |
| Others | 25 additional MoHR staff trained on excavation and identification of missing persons. |  |
| Indirect beneficiaries | Families who have missing family members |  |
| Employment generation (men/women) |  |  |

| - Quantitative achievements against objectives and results |  |  |  |
| --- | --- | --- | --- |
| For Output 1: - Identification of the trainees - Organizing and conducting the training - Purchase required equipment to undertake excavation | 16 CVs received from the MoHR and expecting to receive 10 more from the MoD. This number is sufficient but ICMP would like to receive in total at least 30 to have a good roster of candidates and to choose the most suitable ones. ICMP is considering to support other Iraqi authorities, a letter was sent to indicate a need for a meeting with all concerned parties in order to address the enhancements needed from their side to overcome the difficulties faced. ICMP HQ procured the following items: - Anatomy warehouse, full disarticulated skeleton … 12 pcs (arrived in Baghdad); - Garmond, DNA envelopes ….. 5000 pcs (arrived in Baghdad); - Besser, paper bag ……. 5000 pcs (arrived in Baghdad); - GeoWild, Sokkia total station SET 630R …. 1 pcs - GeoWild, tripod, leveler and leveling meter (arrived in Baghdad); - DHL, DNA envelopes sent to Iraq … 1 pcs (arrived in Baghdad); - Amazon.com, different books (full delivery) .... 20 pcs (status on delivery not known); - DHL, paper bags sent to Iraq ……. 1 pcs (arrived in Baghdad); - France Casting, determination sets (full delivery) (not shipped yet); - Paleo Tech, osteometric board and calipers …. 9pcs (2 out of 3 shipments shipped to Iraq, delivery status not known); - WA products (scene of crime consumables) | % of planned %50 %0 %20 |  |
| Output 2 | No activities initiated yet within this output | % of planned |  |
| - Qualitative achievements against objectives and results |  |  |  |
| Given that the project is still in the preparatory stage focusing on procurement, qualitative results against the objectives have yet to be achieved. |  |  |  |

- Main implementation constrains & challenges (2-3 sentences)

The site of excavation has yet to be determined by the MoHR, effectively preventing initiation of excavations. To address this and other concerns raised about insufficient security on excavations sites, the ICMP sent a letter to all concerned parties on the 30th of June asking for a meeting to discuss the barriers and obstacles to implementation. The meeting aims to create a forum for resolving difficulties experienced.