# United Nations Development Group Iraq Trust Fund

# Project #: A7-03

# March 2007/ 1st Quarter 2007

# Summary

| Participating UN Organisation: UNOPS | Cluster: A |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Kurdistan Regional Government |

| Title | Support to Iraqi Kurdistan Mine Action Agency (IKMAA) |
| --- | --- |
| Location | Erbil, Northern Iraq |
| Project Cost | USD 2,921,852 |
| Duration | 17 months |
| Approval Date (SC) | 22 January -06 | Starting Date | 1 January -07 | Completion Date | 31 May -08 |
| Project Description | Support to Iraqi Kurdistan Mine Action Agency as per described here below. |

# Development Goal and Immediate Objectives

The overall objective of the Project is to increase the capacity building of the IKMAA as follows. To increase demining performance and production rates by providing up to date mechanical demining equipment and accessories to the IKMAA (formerly known as IKMAA). To provide courses in EOD Training and Information and Operations Management Training and to conduct a study visit to another Mine Action Programme. Procurement of Mine Detection Equipment including Mine Detectors, Personal Protection Equipment. Procurement of IT Equipment. Procurement of spare parts for the existing fleet of Mine Detectors and Mechanical Mine Clearance Equipment.

# Outputs, Key activities and Procurement

| Outputs: Increased production rates and enhanced deminer's performance through providing up to date demining equipment, office equipment, mine clearance accessories and training for IKMAA senior staff. |  |
| --- | --- |
| Activities: Training of IKMAA staff, construction of mine clearance machines and procurement of Mine Action related equipment and office equipment. |  |
| Procurement Minelab detector spare parts – Worth of US$ 51,945 for repair of the current fleet of Minelab detectors. Bozena spare parts - Worth of US$ 261,690.28 for repair of the current fleet of Bozena Mini Flails. Much of the spare parts were used during the month of July when two technicians from Way Industry (under a contract with UNOPS) repaired the fleet of Bozena Mini Flails on location in the Kurdistan Region. Battery Rechargeable for Minelab detector – 3,500pcs Charger Battery for detector – 240pcs Helmet lightweight c/w visor 30cm – 434pcs Appliqué for visor – 1,900pcs Battery Rechargeable for VHF hand held Radios – 168pcs Minelab F3 Mine Detectors – 12pcs Vest protective RBR c/w carry bag (OS) – 154pcs Laptop computer Sony Vaio VGN-FS875P/H – 10pcs UPS Power ware 9155 15KVA – 1pcs Digital Cameras – 18pcs Global Positioning Systems (GPS) – 25 Two Front End Loaders/sifters Two Excavators Three Mobile Workshops Two Water Tankers with sufficient spare parts for one year Quantity of spare parts for one year maintenance and repair for all the above listed Mine Clearance Machines |  |

# Part Two: Situation as of 31 March 2007

| Funds Committed | $862,718 | 29.52 % of approved |  |
| --- | --- | --- | --- |
| Funds Disbursed | $122,268 | 4.18 % of approved |  |
| Forecast final date | 31 May 2008 | Delay (months): 5 months |  |

# Quantitative achievements against objectives and results

- Increased production rates and enhanced demining performance through providing up to date demining equipment and accessories: 85% completed.

- Explosive Ordnance Disposal (EOD) training, Information Management training, and planning and operations planning: 100% completed.

- Repair the current fleet of Bozena mini flails and to purchase Bozena spare parts: 100% completed.

- Purchase of mine clearance and office equipment. All equipment has been purchased and delivered except for equipment purchased directly by IKMAA.

- Monitoring of construction of all items of mechanical equipment by IKMAA logistics staff: 80% completed.