# United Nations Development Group Iraq Trust Fund

# Project #: G11-18

# Date and Quarter Updated: January- March, 1st Quarter 2009

| Participating UN Organisations: UNAMI - UNOPS | Sector: Governance |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Independent High Electoral Commission of Iraq (IHEC) |

| Title | Support to National Electoral Observer Groups for Provincial Council Elections in Iraq Phase IV |
| --- | --- |
| Geographic Location | Iraq, 14 Governorates (all except KRG and Kirkuk) |
| Project Cost | USD 6,913,900 |
| Duration | 6 months |
| Approval Date (SC) | 26 October 2008 | Starting Date | 1 November 2008 | Completion Date | 30 April 2009 |
| Project Description | Based on assessments conducted by the Independent High Electoral Commission of Iraq (IHEC), the International Electoral Assistance Team (IEAT), and various NGOs, the UN has been requested by the IHEC to support national electoral observer networks to increase the number of trained electoral observers from 20,000 to 40,000 and to mobilize them during the upcoming provincial elections in Iraq. In order to prevent the perception of a conflict of interest between the UN’s assistance to the IHEC and the independent observer groups, all support for the electoral observers is implemented through international partner organisations (FES, ACHRS) who will coordinate, jointly with their local NGO network partners, the training sessions (800 workshops in 14 governorates) and the observation process. UNAMI/Electoral Support will be responsible for technical supervision and monitoring (trainings and observer reports). UNOPS will be in charge of financial management (incl. procurement, legal, monitoring). |

Development Goal and Immediate Objectives

To contribute to an enhanced implementation of electoral processes in Iraq in line with UNCT Goal 4 (Promote good governance and democratic processes, assist to uphold the rule of law and establish a human right regime) through the provision of electoral observation training and support to Electoral Observers during the upcoming Provincial Council Elections in Iraq. The project identified as immediate objectives: 1. Strengthening the capacity of electoral observer networks in Iraq 2. Facilitating the successful observation of provincial elections in Iraq in 2009

| Outputs, Key activities and Procurement |
| --- |
| Outputs | Output 1.1 Sufficient number of qualified national electoral observers to cover the Provincial Elections in 14 governorates of Iraq Output 2.1 Sufficient numbers of national electoral observers mobilized on Election Day for Provincial Elections in 14 governorates of Iraq in 2009 |
| Activities | 1.1.1 Identify Iraqis for training in electoral observation (through Iraqi NGO networks) 1.1.2 Organize and conduct training sessions 1.1.3 Monitor training sessions 1.1.4 Evaluate and report (narrative and financial) 2.1.1 Accredit national electoral observers through partner networks with IHEC 2.1.2 Mobilize electoral observers on Election Day 2.1.3 Evaluate and report (narrative and financial) |
| Procurement (major items) | None |

| Funds Committed | USD 6,737,532.70 | % of approved | 97 % |
| --- | --- | --- | --- |
| Funds Disbursed | USD 6,354,826.37 | % of approved | 92% |
| Forecast final date | 30 April 2009 | Delay (months) | 0 |

| Direct Beneficiaries | Number of Beneficiaries | % of planned (current status) |
| --- | --- | --- |
| Men | 15,298 | 100 % |
| Women | 4,702 | 100 % |
| Children |  |  |
| IDPs |  |  |
| Others |  |  |
| Indirect beneficiaries | By contributing to a transparent democratic election process, the mobilisation of electoral observers benefits the population of Iraq and in extension also the populations of the neighbouring countries |  |
| Employment generation (men/women) |  |  |

| Quantitative achievements against objectives and results |
| --- |
| Output 1.1 Sufficient number of qualified national electoral observers to cover the Provincial Elections in 14 governorates of Iraq |  |  |  |
| 1.1.1 Identify Iraqis for training in electoral observation (through Iraqi NGO networks) | 100 | % of planned |  |
| 1.1.2 Organize and conduct training sessions | 100 | % of planned |  |
| 1.1.3 Monitor training sessions | 100 | % of planned |  |
| Output 2.1 Sufficient numbers of national electoral observers mobilized on Election Day for Provincial Elections in 14 governorates of Iraq in 2009 |  |  |  |
| 2.1.1 Accredit national electoral observers through partner networks with IHEC | 100 | % of planned |  |
| 2.1.2 Mobilize electoral observers on Election Day | 100 | % of planned |  |
| 2.1.3 Evaluate and report (narrative and financial) | 100 | % of planned |  |

Qualitative achievements against objectives and results during this reporting period

Output 2.1.2 40,000 independent national observers were mobilised on election day the 31st January 2009. Output 2.1.3 FES an ACHRS submitted their final reports. Final consolidated reports have been circulated.

Main implementation constrains & challenges (2-3 sentences)

Although monitoring of the elections ran smoothly, recommendations for future mobilisations of independent observers suggest that a greater clarification of the appropriate relationship between IHEC and independent observers, as well as the role that IHEC plays in elections, would be of value. In order to enhance results, there should also be a call centre available to advise election observers on how appropriately to implement their observation tasks during elections.