- United Nations Development Group Iraq Trust Fund

- Project #: G11-04

- December 2007/4th Quarter 2007

- Project Summary Sheet

| Participating UN Organisation: UNDP/ EAD | Cluster: G Support to the Electoral Process in Iraq |
| --- | --- |
| Govt of Iraq Line Ministry Responsible: Independent High Electoral Commission (IHEC) |  |

| Title | Technical Assistance to IHEC |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Location | Iraq – Jordan |  |  |  |  |
| Project Cost | US$ 7,801,996 |  |  |  |  |
| Duration | Approval for extending the project was granted until December 2008. |  |  |  |  |
| Approval Date (SC) | 25 Oct 2004 | Starting Date | October 2004 | Completion Date | * December 2008 |
| Project Description | Recruitment of short term electoral experts to assist IHEC develop the capacity of organising for electoral events in Iraq |  |  |  |  |

- Development Goal and Immediate Objectives

The main goal of the IEAT assistance is to increase the institutional capacity of IHEC to the international standards and best practices. This project provides a key intervention areas to assist IHEC develop their internal regulations and procedures to include recruitment policies as well as financial regulations based on the Iraqi laws.

- Outputs, Key activities and Procurement

| Outputs | - Assist IECI to complete preparations for holding three sets of elections in 2005. - UN DPA EAD to identify international experts in order for them to be recruited by UNDP to immediately join the UN team in Baghdad and Amman to increase the level of technical assistance provided to IECI/IHEC by the UN. |
| --- | --- |
| Activities | Annex one presents the areas of planned intervention through this project. UNAMI component of the staffing of IEAT include all the other essential areas. |
| Procurement (major items) | N/A |

- Situation as of 31/12/2007

| Funds Committed | USD 6,081,755.00 | % of approved | 78 |
| --- | --- | --- | --- |
| Funds Disbursed | USD 6,081,755 | % of approved | 78 |
| Forecast final date | This project remains the main tool for Electoral Assistance Team to response to the immediate needs of IHEC by providing international electoral experts in specific areas of interventions. The project end date was extended for an additional year as the need continued to develop with the appointment of a new board of commissioners of IHEC. IHEC is expected to organise and manage three main electoral events in Iraq. A referendum on the emended constitution, governorate elections and a referendum on the status of Kirkuk. | Delay (months) | Extension for one year requested |

- Quantitative achievements against objectives and results

| Assist IECI to complete preparations for holding three sets of elections in 2005 | The International Electoral Assistance Team (IEAT) headed by UNAMI successfully completed their role of assisting IECI to prepare and hold three electoral events in Iraq in 2005. | % of planned | 100 |
| --- | --- | --- | --- |
| UN DPA EAD to identify international experts in order for them to be recruited by UNDP to immediately join the UN team in Baghdad and Amman to increase the level of technical assistance provided to IECI/IHEC by the UN. | International Electoral Experts are selected by UNEAD and recruited on short term consultancy or contract of limited duration to respond to the needs of IHEC. Those experts who are requested for longer durations are then transferred to UNAMI longer-term contracts. The areas of assistance are logistics, operations, procedures, public outreach, security, IT and legal advice. This is all done in coordination with IHEC and, members of the IEAT composed of IFES, the EU and DIFID. | % of planned | 100% completed for the 2005 elections and remains ongoing for the upcoming electoral events in Iraq with IHEC (50%). |

- Qualitative achievements against objectives and results

The United Nations Electoral Assistance Division at NYHQ maintains an active roster of electoral experts for deployment. The challenge remains in Iraq of providing an acceptable package of compensation for those who are willing to travel to Iraq due to the security risks. The quality of experts selected is at high standards with high level of experience in elections in countries facing conflict situation or in transition. The Electoral Division recently moved to a developed electronic database with online possibility for candidates to apply for consideration of being added to the roster. With EAD being involved in more than 50 countries worldwide the division is able to maintain good record of experts working in elections.