# United Nations Development Group Iraq Trust Fund

# Project #:G11-17

# Date and Quarter Updated: 15th January 2009 -4th Quarter, October-December 2008

| Participating UN Organisation: UNAMI/ IEAT, UNOPS | Sector: Governance, [Formerly “Electoral Support”] |
| --- | --- |
| Government of Iraq – Responsible Line Ministry: Independent High Electoral Commission IHEC |

| Title | Provision of Communication Support and Technical Assistance to the IHEC at the HQ and Governorate Electoral Office (GEO) levels |
| --- | --- |
| Geographic Location | Iraq |
| Project Cost | US$ 4,521,300 |
| Duration | 18 Months |
| Approval Date (SC) | 14th Jan 2008 | Starting Date | 01 Feb 2008 | Completion Date | 31 Jul 2009 |
| Project Description |  |

UNAMI/ IEAT and UNOPS have developed a project to provide necessary communications assistance to the IHEC at the HQ and GEO levels, which is required in advance of the next electoral event. This project will upgrade the level of IHEC communications with VOIP internet capabilities as well as the provision of maintenance support, a training package for IHEC personnel in the areas of installation, maintenance and repairs, and provide technical advice to the IHEC on its communications strategy. This project will avail of identified communications equipment at both the HQ and GEO levels. A contractor will be engaged to provide the required support both in terms of upgrading the HQ and GEO communication capacities and the provision of the required capacity building training to IHEC personnel, while technical advice will be given by a specialist consultant.

# Development Goal and Immediate Objectives

﻿﻿To contribute to an enhanced implementation of electoral processes in Iraq in line with UNCT Goal 4 (Promote good governance and democratic processes, assist to uphold the rule of law and establish a human right regime) through the provision of sustainable communications improvement and technological capacity development within the IHEC.

# Outputs, Key activities and Procurement

| Outputs | Contractor(s) engaged to install internet and VOIP communications, provide maintenance support and capacity building to IHEC personnel at HQ and at all 19 GEOs. Improved connectivity through installation and subscription to Internet and VOIP communications equipment at IHEC HQ all 19 GEOs, and provision of generators as required. VOIP and Internet communication equipment developed and successfully introduced. Ownership and transfer of maintenance programme to IHEC, all relevant personnel trained in installation, maintenance and repair of internet and VOIP communications equipment. The IHEC has benefited from specialist guidance on their communications strategy and this is confirmed by a project evaluation. |
| --- | --- |
| Main Activities in reporting period | Contractor subscribes to internet and installs VOIP communications equipment at IHEC HQ and GEOs. Contractor drafts maintenance programme and activities for communications equipment at the HQ and GEOs and implement the programme endorsed by IHEC. Identify IHEC personnel at HQ and Governorate level to receive maintenance, installation and repair training of IHEC communication equipment. Develop and deliver training programme endorsed by IHEC. Hand over management of maintenance programme to IHEC personnel. Monitor & evaluate services provided by contractor. Contract an expert consultant in communications and technology implementation and strategy to conduct an assessment of the project results, the IHEC’s communication capacity, and any further support they might require. |
| Procurement (major items) | Implementation of the contract was outsourced to an Iraq organization, “Nashita for Information Technology & Communications” at an initial cost of US$ 1,571,899.00. This amount was further increased to US$ 964,071, to bring the total amount to US$2,563,955 which will cover costs for the contract extension. |
| Part Two: Situation as of 31 December 2008 Funds Committed $3,678,460 83% of approved Funds Disbursed $2,724,460 62% of approved Forecast final date 31 July 2009 Delay (months) 6 months Quantitative achievements against objectives and results Improved connectivity through installation and subscription to Internet and VOIP communications equipment at IHEC HQ all 19 GEOs, and provision of generators as required. 100% of Planned 1.2.1 Contractor subscribes to internet and installs VOIP communications equipment at IHEC HQ and GEOs. 100% of Planned 1.2.2 Monitor & evaluate services provided by contractor(s). 100% of Planned 1.2.3 Contractor submits report on installation and subscription package. 100% of Planned 1.3 VOIP and Internet communication equipment developed and successfully introduced. 100% of Planned 1.3.1Contractor drafts maintenance programme and activities for communications equipment at the HQ and GEOs 100% of Planned 1.3.2 IHEC endorses maintenance programme 100% of Planned 1.3.3 Contractor implements maintenance programme at IHEC’s HQ and GEOs 75% - Ongoing Activity 1.3.4 Monitor and evaluate contractor maintenance services 75% - Ongoing Activity 1.3.5 Contractor reports on implementation of maintenance programme 75% - Ongoing Activity 1.4 Ownership and transfer of maintenance programme to IHEC, all relevant personnel trained in installation, maintenance and repair of internet and VOIP communications equipment. 80% 1.4.1 Identify IHEC personnel at HQ and Governorate level to receive maintenance, installation and repair training of IHEC communication equipment. 75% Of Planned 1.4.2 Develop training programme for IHEC personnel by contractor. 100% 1.4.3 IHEC endorses training programme. 100% 1.4.4 Contractor delivers agreed training programme. 100% 1.4.5 Contractor hands over management of maintenance programme to IHEC personnel. 50% - Ongoing Activity 1.4.6 Monitor and evaluate contractor training programme and maintenance programme handover. 1.4.7 Contractor submits final report on training programme and maintenance programme handover. 1.5 The IHEC has benefited from specialist guidance on their communications strategy and this is confirmed by a project evaluation. 50% 1.5.1 Draw up TORs and VA for specific expert consultant in communications and technology implementation and strategy. 100% 1.5.2 Shortlist, interview and recruit communications expert. 100% 1.5.3 Consultant provides technical guidance and assistance to IHEC in the development of the communications strategy. 50% 1.5.4 Project evaluator conducts an assessment of the project results, the IHEC’s communication capacity, any further support they might require and, if so, how it might best be delivered. |  |

# Qualitative achievements against objectives and results

All the 20 IHEC GEO Office sites and the HQ had VSAT’s installed, were connected to the internet and had fully functional VOIP systems. On IHEC's request, UNOPS extended the contract for the provision of communications support for another 6 months until July 2009. Some additional items were added to address specific support requirements in the various GEO offices based on assessments carried out jointly by IHEC, UNOPS and UNAMI in December 2008. IHEC was unable to take over the system at this stage (With governorate elections planned for early 2009 and operational activities being given priority). This meant that the transfer of the system and the maintenance programme to IHEC, which was to be realized at the end of the project, was rescheduled to July 2009. The effects of the VSAT/VOIP installations are noticeable in the build-up to the upcoming electoral event with the improved communications and more efficient exchange of information between the HQ and the GEO’s and vis-à-vis all the stakeholders in the elections. Follow up training based on a needs assessment done previously in the 3rd quarter was given to the IT personnel on the ground at all the 21 sites. The Communications expert spent most of the time in Baghdad and was based at the IHEC HQ where he oversaw the systems streamlining, maintenance and support and also coordinated between and amongst the various stakeholders in the IEAT, IHEC and the contractor.

﻿