Sixth Six-month progress report for project

# REPORT COVER PAGE

| ## Participating UN Organization: |  | ## Cluster: |
| --- | --- | --- |
| UN-HABITAT |  | B - Education and Culture |

| ## Project No. and Project Title: |  | ## Report Number: |
| --- | --- | --- |
| B1-09 Educational Facilities Rehabilitation Project |  | No.6 |

| ## Reporting Period: |  | ## Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | UNDG ITF: $17,580,663 |

| ## List Implementing Partners: |  | ## Project Coverage/Scope: |
| --- | --- | --- |
| Ministry of Education; Ministry of Higher Education and Scientific Researches |  | Baghdad, Basrah, Samawa and Nassiriya |

| ## Abbreviations and acronyms: |  | ## Project Duration/Closed Project: |
| --- | --- | --- |
| MoE : Ministry of Education MoHE; Ministry of Higher Education DoE: Directorate of Education HQ: Head Quarter |  | 30 months (October 2004 – September 2007) |

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Objectives:

The main objective of the project is to enhance access to education in Iraq at all levels.

Outputs:

The main outputs as per the approved project document are as follows:

- Rehabilitation of 34 educational facilities in the selected locations to provide improved education environment for about 30,000 students;

- Improved skills for construction workers and young engineering professionals involved in the rehabilitation activities;   and

- Employment generated for approximately 5000 construction workers per day through local contractors selected in the areas of specific interventions.

Outcomes:

Improved access to educational facilities at all levels.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq:

The project is an integral component of the Programme being implemented by the Education & Culture Cluster within the framework of the UN Assistance Strategy for Iraq, which, as one of its principal developmental goals for the education sector, seeks to increase participation and completion rates at all levels of education, strengthen service delivery and support and inform policy development.

- UN Millennium Development Goals:

- The project is expected to strengthen primary, technical and higher education as envisaged in the Millennium Development Goal on Education; and

- The project is contributing to the Millennium Development Goal "eradication of extreme poverty and hunger" by providing significant employment opportunities.

- Joint Needs Assessment:

The project responds to the medium term priorities of the 2003 UN-World Bank Joint Needs Assessmentas follows:

- Ensure minimum quality standards of teaching and learning and system management through strengthening basic training and providing an adequate supply of materials and equipment.

- Begin physical rehabilitation and reconstruction of primary and secondary schools, prioritising replacement of schools that are no longer serviceable.

- For TVE rehabilitate key buildings and replace essential equipment as needed in the short-term, and assist the TVE system before carrying out more extensive investment.

- Iraqi National Development Strategy:

The project responds to the NDS Goal 2, i.e. Achieve Primary Education for All

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

UN HABITAT is partnering with the following in the execution of this project:

      - Representatives of the Directorates of Education (DoE) and representatives of Universities & Technical Institutes, who are conducting field visits in collaboration with UN-HABITAT consultant engineers in each governorate. The Ministry of Education via local Education Directorates and the Ministry of Higher Education & Scientific Research continue to be involved in all procedures relating to identification of educational facilities, providing the technical equipment needs and their specifications, bid opening and supervision of the works, and final approval of the delivered work & the supplied items.

      - Local contractors in order to maximize the employment impact of the project

      - Local consultants/engineers who are engaged to undertake the technical assessments of scope of work, prepare bidding documents, undertake the tenders opening process, and supervise, follow up & control the rehabilitation works according to tender based requirements including:  quality of work & compliance with technical specifications, quantities according to the approved BOQ, and the work time schedule.

      - International Suppliers of technical equipment, tools, and instruments.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

Total funds provided: $ 17,580,663 million,

Total committed amount: $ 17,580,663 for the period Jan 2004 – End December 2006.

Total disbursed amount: $ 17,580,663

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

None

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

The total accumulative expenditures up to the end of June are as follows:

- Personnel and field personnel : $ 969,903.38

- Sub-Contracts : $ 13,132,242 million

- Training, workshops and stakeholder meetings :$ 29,522

- Equipment : $ 2,093,601.72 million

- Supplies & Commodities : $ 7,400

- Transport : 0.0

- Travel : $15,031.62

- Miscellaneous: $140,782.11

- Security : $42,045.55

- Agency Support Costs (7%) : $ 1,150,137 million

  - Indicate other funding sources, if applicable.

None

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

None

  - Project expenditures for the 1st July to 31 December 2007 period.

Disbursed amount for the period 1st Jan 2007 – 30th June 2007 is $0.00

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

The number of national operations staff is 4 and 3 national programme staff, supported by 25 national field personnel.

  - International Staff: Provide details on the number and type (operation/programme)

The number of international operations staff is 2 and 2 international programme staff.

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

- UN-HABITAT national consultants, with the active participation of DoEs and representatives of Universities & Technical Institutes, carry out a detailed assessment of the facility to be rehabilitated. An assessment report is prepared and forms the basis for discussion among all stakeholders to agree on the priority needs. As soon as consensus is reached on the broad scope of the rehabilitation works, Bills of Quantities are prepared by the field personnel, who set out in precise detail, the scope of work and specifications.

- The Bills of Quantities and the technical specifications are sent to UN-HABITAT Office in Amman for review by the Rehabilitation Team. Once approved, the Rehabilitation Expert authorizes the preparation of the tender documents. The rehabilitation works are packaged into small contracts - typically between $50,000 and $150,000 in size - that can be carried out by small Iraqi Contractors.

- UN-HABITAT maintains a register of - now over 1000 - Iraqi Contractors with different specialties and grades in the four targeted governorates. Bidders are selected from a comprehensive contractors’ database based on a selection criteria. Normally, between 10 and 20 Iraqi contractors are invited to tender for each rehabilitation contract depending on the estimated amount of each contract.

- Implementation supervision is carried out on a daily basis by UN-HABITAT field Consultant Engineers.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

- The tender evaluation process incorporates a system of checks and balances with a clear segregation of functions. Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate Tender Evaluation Committee. A separate technical team based in Erbil/Iraq prepares the Agency Estimate (estimated cost) for each contract, using a specifically designed database system, which generates priced Bills of Quantities using monthly updated market prices. Prices of materials and labour are regularly compared with that collected by other UN agencies.

- For contracts, which exceed $150,000 the tender evaluation report is subject to review and approval by the Local Contracts Committee of the United Nations Office in Nairobi (UNON). Contracts of less than $150,000 are locally reviewed and approved by the Programme Manager under the terms of a special delegation of authority.

- Once the lowest acceptable tender is established, the contract is awarded.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

- The rehabilitation works are supervised and monitored by Iraqi national consultants. The progress of works monitored and approved through time-series photographs, daily briefings from the consultants, videos & telecommunication, laboratory test reports for quality control of construction materials. In addition, initial handing over certificate is issued upon completion & receipt of the rehabilitated facility by the direct beneficiaries.

- Interim payments are only released to the contractor upon accepting the work progress and quality by the Senior Engineer & the Rehabilitation Expert in Amman Office, certified by the PMO and then approved by PM as a final stage before being sent to HQ for processing.

- Liquidated damages are applied for any unjustified work delay and violation of other contract provisions.

- During the maintenance period, constant surveillance of the implemented work is carried out by the field personnel to guarantee implementation sustainability and defects repair. This is normally enhanced by interviews with local authority staff and beneficiaries for addressing their remarks on the work and responding to any justified request before the final handing over take place in order to ensure the public good reputation and impression on the agency achievements. All contracts incorporate defects liability clause so that any defects, which emerge after completion have to be repaired by the contractor.

- Before the rehabilitated facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the Local Authority, the beneficiaries, the relevant department of the government and UN-HABITAT staff and consultants. The final payment is not released until the Acceptance Committee certifies that all work has been satisfactorily completed.

  - Report on any assessments, evaluations or studies undertaken.

In 2007, the UN-HABITAT Iraq Programme commissioned an independent review of its procurement practices and implementation modalities. Following the review, a number of useful measures have been initiated to further strengthen practices.  This is also leading to a comprehensive training of field personnel to better perform their procurement, supervisory and quality control roles.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six-month reporting period.

- During the reporting period, the rehabilitation of the Mechanical & Water Resources Departments in Baghdad /Zafaraniya Technical Institute was completed.  The rehabilitation of the Electrical Department, Transformer Building and the sewage network for the Institute attained a progress of 93% completion.

- The construction of additional classrooms for the remaining Primary Schools in Samawa was completed and the rehabilitation of the Secondary School was more than 50% completed during this period.

- The supply of equipment, tools & instruments for the Samawa Technical Institutes was completed during the reporting period. Similarly the supply for the Basrah Institutes reached 83 % during the reporting period.

- The construction of the Deaf & Dumb Institute is also nearing completion (93%).

- Only a third of the planned supply of furniture to schools & kindergartens in Baghdad could be completed until end June due to the prevailing security situation.

- The project generated employment opportunities of 13,314 persons-days during the reporting period.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

- Increased the access to educational programmes at all levels (kindergartens, schools, vocational training, technical institutes & universities)

- Contributed widely to removing obstacles to access to vocational schools in southern governorates for both genders, and also in significant reduction in girls drop out especially at the secondary school level.

- Helping to overcome supply side capacity gaps in provision of technical education through the rehabilitation of specialized technical workshops, institutes & university departments and supply of equipment, tools & instruments.

- Contributing to improvement in standards of environmental health and hygiene through the rehabilitation/upgrading of sanitary facilities.

  - Report on the key outputs achieved in the six month period including and nature of the activities (inputs), % of completion and beneficiaries.

The overall progress, until end June 2007, based on the number of completed contracts is 90%, benefiting around 30,000 students at various levels of education.  Progress on specific sub projects during the reporting period are as follows:

- Rehabilitation of two technical departments & one primary school were completed;

- Rehabilitation of one technical department, one secondary school, and one Deaf & Dumb Institute have reached planned progress levels;

- The supply of equipment, tools and instruments to the Samawa Institute has been completed.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

The implementation of the various rehabilitation works has been delayed, largely due to security-linked constraints.  Further, the supply of equipment has been affected by difficulties in border crossing and in obtaining customs clearances from the Iraqi Authorities.

The implementation experience of this project has provided the following significant lessons:

Implementation Planning of Physical Works:  Most physical works have taken much longer than their planned duration due to security-related problems.  This experience has helped to plan more realistically the implementation schedules, factoring in such unanticipated delays.  Similarly, international procurements, which are subject to delays in border crossing and customs clearances are now being taken up with adequate lead on the one hand and on the other, the engagement with the relevant Iraqi authorities is also initiated well before the supplies are due.

Market Price Fluctuations:  Market prices of both labour and materials have been extremely volatile, in turn affecting the scope of the project.  In view of this, UN- HABITAT now started carrying out sensitivity analysis which is helping to look at various materials and construction technology alternatives that are less sensitive to price fluctuations.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

The project is being implemented in collaboration with the Directorate of Education in each governorate & the representatives of the technical institutes and university departments. These partners are involved in all stages of the project cycle, such as: selection and prioritisation of educational facilities for rehabilitation; procurement and contracting; implementation supervision; in addition to final approval of works and supplies.  This has helped to ensure transparency, and foster a greater sense of responsibility and commitment from amongst client departments.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including  of short and/or long-term jobs created), and environment.

Despite security constraints and resultant delays, the project achieved 90% completion at the end of the reporting period.  The specific planned achievements regarding the various cross cutting themes are as follows:

Gender and Human Rights:  All rehabilitated institutes offer equal learning opportunities for both women and men. By improving the quality of the built environment and teaching & learning facilities, the project has contributed towards the basic human right to quality education.

Employment: The project has, until the end of the reporting period, generated local employment of 34,324 persons-days.  At the same time it has contributed to significant capacity development of 57 Contractors.

Environment: Through improved access to quality education the project has indirectly and potentially contributed towards environmental improvement, with more citizens being educated and therefore more sensitive to environment related issues.  Through improved sanitation facilities, the project has contributed directly to environmental improvement.  Further, it has been ensured that technologies and materials used in this project are environmentally benign.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007.

- The project is expected to be 100% completed during the next reporting period.   The supply of the final consignment of equipment, tools & instruments to Baghdad/ Zafaraniya Technical Institute is expected to be completed by end November 2007.  The supply of the remaining equipment, tools & instruments for Basrah Technical Institute is also expected to be completed by end August 2007.  Activities will include facilitating supply and transportation including necessary Customs Clearances and formal handovers.

- The rehabilitation and final handover of Al-Muthanna Secondary School in Samawa, the Deaf & Dumb Centre in Nassiriya, and the Electrical Department & the Sewage Network of the Technical Institute in Baghdad are expected to be completed by end August 2007. Activities will include implementation supervision, contracts management, overseeing building performance during the maintenance period, and final formal handover to the client departments/local authorities.