LEBANON RECOVERY FUND

ANNUAL project NARRATIVE progress report

# REPORT COVER PAGE

| Participating UN Organization: |  | Report Number: |
| --- | --- | --- |
| Food and Agriculture Organization |  | Second Annual Report |

| LRF Project No: LRF 14 New Atlas Project No: 65554 |  | LRF Project Title: Integrated Forest Fire Management, Prevention and Control |
| --- | --- | --- |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 31 December 2008 |  | LRF-funding: $2,600,000 Other funding: $0 |

| List Implementing Partners: Ministry of Environment, Ministry of Agriculture, Lebanese Agriculture Research Institute, Association of Forests, Development and Conservation, local communities and municipalities |  | Project Coverage/Scope: National scope with specific activities in Akkar / north Lebanon region |
| --- | --- | --- |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| List the main abbreviations and acronyms that are used in the report. Food and Agriculture Organization – FAO Ministry of Environment - MoE Ministry of Agriculture – MoA Association of Forests, Development, and Conservation (AFDC) Lebanese Agriculture Research Institute (LARI) Lebanon Recovery Fund – LRF Project Steering Committee – PSC Chief Technical Advisor – CTA |  | Start Date: 1 March 2008 End date: 28 February 2010 Budget Revisions/Extensions: No major budget revisions undertaken Project Closure: Project was operationally active at reporting period |

LRF-14: Integrated forest fires management – forest fires prevention, forest fires fighting (control) and damaged forests assessment and rehabilitation

### I.  PURPOSE

The objective of the proposed programme is to create an enabling environment for the Government of Lebanon to address through its early recovery efforts: 1)the prevention of future forest fires; 2) the efficient fighting of fires when they occur; 3) updating the assessment of the ecological and socio-economic damage resulting from the July 2006 war as well as by the enormous fires that were erupted simultaneously and repeatedly during October 2007 in different parts of the country; and 4) the rehabilitation of forests that were damaged during the July 2006 war and recent environmental disasters to allow for re-access of rural communities to their land resources (woodlands, forests, etc.) through the alleviation of obstacles, such as demining.

The programme is part of the Ministry of Environment’s (MoE) National Campaign for the management of forests in Lebanon (prevention, control and rehabilitation) that has been recently launched in cooperation with the various partners and stakeholders. The main implementing partner for the project is the Association for Forests, Development and Conservation (AFDC).

FAO’s partners include MoE, AFDC, Ministry of Agriculture and the Lebanon Agriculture Research Institute.

### II. RESOURCES

Total Programme/Project Cost: US $ 2 600 000

LRF:  US $ 2 600 000

Government Input: US $ 0

Other: US $ 0

Total:  US $ 2 600 000

Budget: commitment and disbursement:

The below budget reflects all expenditures up to 30 September.

| OSRO/LEB/703/LEB |
| --- |
| Item | Approved Budget (in US$): | Estimated Disbursement/ Commitment (in US$) |
| Personnel and travel: | 272 276 | 10 992 |
| Contracts: | 1 000 000 | 1 000 000 |
| Supplies/Commodities/Equipment | 805 000 | 105 735 |
| Miscellaneous/Other: | 52 274 | 10 020 |
| Agency Support Costs: | 170 000 | 16 524 |
| TOTAL: | 2 600 000 | 1 154 255 |

Personnel and travel costs:

| Item: | Approved Budget cost (US$): | Estimated Disbursement/Commitment (US$) |
| --- | --- | --- |
| Personnel and travel: | 272 276 | 10 992 |

FAO expenditures for personnel and travel cover an inception mission by the Forestry Officer and operational backstopping missions from Headquarters; relevant travel costs and the recently assigned national consultant.

Contracts:

| Item: | Approved Budgeted cost (US$): | Estimated Disbursement /Commitment (US$) |
| --- | --- | --- |
| Letter of Agreement | 184 000 | 184 000 |
| Services Contract | 816 000 | 816 000 |

FAO and AFDC entered into a contractual agreement totalling USD 1 million for services under i) Letter of Agreement for the public awareness campaign and training and ii) Services Contract to undertake an assessment for land preparation and clearing, establish a tree nursery, reforest 100 hectares of damaged land, and manage rehabilitation of fire management infrastructure.

Equipment:

| Item: | Approved Budgeted cost (US$): | Estimated Disbursement /Commitment (US$) |
| --- | --- | --- |
| Equipment and supplies | 805 000 | 105 735 |

During the reporting period, FAO issued Purchase Orders for the following equipment: fire fighting safety clothing, fire fighting manual tools and fire hoses. During the tendering process for trucks, insufficient suppliers responded and the tender had to be launched several times. At the end of the reporting period, the trucks were still under tendering process. Arrival of the new trucks should be summer 2009. The trucks will be subsequently retrofitted with water tanks and these costs will be incurred after delivery.

Other costs (General Operating Expenses, and Miscellaneous):

Expenses under “Other”, which groups budget lines such as general operating expenses, miscellaneous and overhead costs are indicated below.

| Item: | Approved Budget cost (US$): | Estimated Disbursement/Commitment (US$) |
| --- | --- | --- |
| Other: | 52 274 | 10 020 |

### III. RESULTS

Outcome:

Supporting early recovery and alleviating poverty through improved forest fires management (prevention, control, assessment and rehabilitation) and their associated benefits to environment and rural communities.

Immediate Objectives:

- Adoption and implementation of preventive measures aiming at forests protection from fires and other risks. Adoption and implementation of control measures aiming at efficient forest fire fighting.

- Adoption and implementation of control measures aiming at efficient forest fire fighting.

- Assessment of the cost of environmental degradation from forest fires.

- Assessment and rehabilitation of forests in areas that suffered from the July 2006 war and October devastating fires.

- Restoration of livelihoods generated from the sound and sustainable use of forested trees (longterm).

Outputs:

Output 1: Prevention

Establishment of fire breaks, forest cleaning and clearing, promotion of research and development related to forest fire prevention.

Output 2: Control:

Software and hardware tools for fire fighting supplied and maintained

Output 3: Assessment & rehabilitation

Ecological and socio-economic losses from forest fires assessed and best restoration techniques for damaged forests identified, implemented and monitored

Output 4 awareness and capacity building:

Targeted public awareness and knowledge increased and strengthened for issues related to forests fire prevention, forest fires fighting, and damaged forests rehabilitation. Capacity building for local municipalities, communities and stakeholders on issues related to forests fire prevention, forest fires fighting, and damaged forests rehabilitation.

IV.	IMPLEMENTATION AND MONITORING ARRANGEMENTS

Establishment of the tree nursery in Andket village:

The cornerstone for the new tree nursery in Andket village was placed in November 2008 and the construction of the nursery was on-going at the end of the reporting period. The nursery will have the capacity to grow 100 000 tree seedlings which will be used for planting/reforesting damaged forest land.

Training and public awareness including publication and dissemination

- Training activities for volunteers and the public awareness campaign had been on-going during the reporting period. This public awareness campaign included Press Ads, Radio spots, and Mass Media (Billboards and Unipoles). The TV was aired in October 2008, which is the most dangerous month for forest fires in addition to billboards and unipoles that will be displayed in different sensitive locations in Lebanon.

Publications and Dissemination

Material for awareness on forest fire prevention, fighting and rehabilitation addressed to local communities living in and around sensitive forest areas were designed and produced including:

- A total of 500 forest fire awareness kits including an A0 display were developed. These kits are being disseminated to trained volunteers from various regions of the country. These kits will be used in local community awareness raising events in different regions of Lebanon.

The display is constituted of several sections with information on forests fires, impact of forest fires, economic value of Lebanese forests, and tips on forest fires prevention, fighting, control and burned areas rehabilitation. The displays are designed in such a way as to be practical for presentation and easy to follow by the targeted audience. The display and its annexes are all packed in a specially designed handbag.

- A total of 5000 magnetic “Forests’ calendar”, that include forest related indicators in the different seasons of the year. Such indicators are planting, irrigation, pruning, cleaning and fires. These calendars will be distributed to farmers particularly those living in forest sensitive areas in an attempt to decrease forest fires.

- Press Ads of three different designs were published in five Lebanese Newspapers (An Nahar, Al Mustaqbal, Ad diyar, Al Balad, and The Daily Star) in different sizes and at different dates.

Establishment of a tree nursery

Purchase Orders had been issued during the reporting period for construction materials for establishing the tree nursery in North Lebanon. AFDC has received bids from various suppliers and a supplier has been selected to begin works in the coming weeks.

Field assessment

The field assessment has started. The assessment of Akkar, Batroun, Metn and Shouf were achieved. The assessment of remaining region is on going.

Equipment

FAO completed procurement activities in the third and fourth quarter of 2008 for nearly all specified items to be purchased under this project. Purchase orders were issued for the following types of equipment: fire hoses; manual tools, including: backpack firefighting pumps, shoulder harness, drip torches, fire swatters, fire rakes, firefighting shovels, axes; safety clothing – wildland firefighting pants, coats, and shirts, carbon shield fire bandana, and firefighting gloves. The equipment arrived in Lebanon in December 2008 and January 2009 and handed over to the Civil Defense. A tender for six vehicles to be retrofitted into fire trucks was issued in the third and fourth quarter of 2008 but the responses from suppliers did not meet FAO specifications. However, the trucks were retendered in 2009 and expected to be delivered during the next reporting period.

Implementation constraints, lessons learned from addressing these and knowledge gained from evaluations and studies that have taken place during the reporting period.

- Current general political and security situation.

Key partnerships and inter-agency collaboration: impact on results.

- Close collaboration with MOE as the main national counterpart is continuous.

- Close collaboration with MOA on the development of the restoration plans for the targeted areas.

- Close collaboration with AFDC as main implementing partner

Other highlights and cross cutting issues pertinent to the results being reported on.

The project activities and agreement modalities with AFDC are now underway and more details on implementation will be reported on in the next progress report.

### IV. FUTURE WORK PLAN

Action plan proceeding as per established workplan approved at the first Project Steering Committee Meeting. The main activities for next reporting period are the following:

- Training Module 2 (Coordination in fire fighting) will be done in 2009 to avoid repetition of the same trainings in other projects.

- Training Module 3(forest fire fighting for volunteers): two more trainings will be done between January and February 2009.

- Awareness campaign: The community awareness activities will resume on May 2009.

- Distribution of tools: It was planned to be on the10th of January but it was postponed

Currently no major adjustment in strategies, targets or outcomes is envisaged.

Estimated Budget required (including any major funding shortfalls).

Currently no funding shortfall is foreseen.

------------------------------------------------------------------------------