Annex 1

|  | Insert Fund specific logo, if applicable |
| --- | --- |

[Name of Fund]

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2009

| Submitted by: Name, Title, Organization (Lead Agency) Contact information |  | Country and Thematic Area |
| --- | --- | --- |

| Programme: Lebanon Recovery Fund MDTF Office Atlas No: 00070663 Programme Title:Socio-Economic Rehabilitation Programme in the Framework of ART GOLD Lebanon |  | Participating Organization(s): UNDP |
| --- | --- | --- |

| Implementing Partners: National counterparts: The Council for Development and Reconstruction International Organizations, including NGOs |  | Programme Budget (from the Fund): |
| --- | --- | --- |
| Programme Duration (in months): Start date:March 2007 End date: December 2011 Original end date Revised end date, if applicable Operational Closure Date, if applicable: Budget Revisions/Extensions: List budget revisions and extensions, with approval dates, if applicable |

# NARRATIVE REPORT FORMAT

# Purpose

- Provide the main outputs and outcomes/objectives of the programme.

The ARTGOLD Lebanon’s overall objective is to support the Lebanese national government and the local communities in elaborating and implementing Strategic Development Plans, within the programme’s target areas while focusing on the most disadvantaged people, towards the achievement of the Millennium Development Goals (MDGs).

Most specifically, the programme aims to:

- Increase access to primary public health care services

- Increase sustainable income generation and job opportunities

- Enhance the preservation of the environment

- Increase youth participation in local development and enhance their social integration

Outcomes:

- Number of patients with access to primary health care centers increased (Bekaa, North Lebanon, BSS)

- Incomes increased for about 600 beneficiaries (South Lebanon, Bekaa, North Lebanon, BSS)

- Separation of solid waste facilitated (South Lebanon, Bekaa)

- Access to information technology for youth increased and youth offices established within municipalities. (North Lebanon, BSS)

# Resources

Financial Resources:

- Provide information on other funding resources available to the project, if applicable.

Belgium, Italy, Principality of Monaco and Spain contributed a total of US.$.6.8 M to ART GOLD’s 2009 strategy to which other contributions, in cash and kind, from different Decentralized Cooperation partners were added.

- Provide information on good practices and constraints in the mechanics of the financial process, times to get transfers, identification of potential bottlenecks, need for better coordination, etc.

As a constraint, different timing between project implementation and receipt of funds from the different donors.

Human Resources:

- National Staff: Provide details on the number and type (operation/programme)

Area Managers (4)

Communication Officer: (1)

Administrative Assistant (4)

LEDA Experts (4)

Field Coordinator (1)

Reports Officer (1)

- International Staff: Provide details on the number and type (operation/programme)

Chief Technical Advisor (1)

International Programme Officer (1)

# Implementation and Monitoring Arrangements

- Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the operating context.

UNDP AGL adopts a multi-scale Development approach, which relies on three main components:

- Participatory Approach and Working Groups Component: which aims at improving skills and capacities of local authorities and administrations to plan, manage, execute, monitor and evaluate human development interventions in a wide raging partnership with the private and civil society sector through the establishment of Local, Regional and Thematic Working Groups which are participative and consultative structures, used to build or reinforce the relational and social capital in the target territories.

- Local Economic Development Component which aims at promoting balanced and inclusive local economic development through the establishment of Local Economic Development Agencies (LEDAs) promoting sustainable socio-economic development, reinforcing local competitive systems, and creating inclusive markets for the disadvantaged people.

- Decentralized Cooperation Component which aims to establish long-term partnerships between North and South partners, and will allow access to technical assistance and financial resources from a wide-range of international partners.

The programme adopts the strategic planning approach to build an agreement on shared goals among territorial stakeholders towards the achievement of a balanced and sustainable development

- Provide details on the procurement procedures utilized and explain variances in standard procedures.

Procurement procedures comply with UNDP rules and regulations.

- Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing project.

The programme’s monitoring comply and adhere to the UDNP rules and regulations. Monitoring includes the following formal actions as visits, reporting, attending events, as well as a lot of informal communications – in personal, by phone, e-mail.  This helps applying systematic analysis of project implementation and progress against the planned outcomes, outputs and activities in order to take remedial actions, when necessary.

- Report on any assessments, evaluations or studies undertaken.

# Results

- Provide a summary of Programme progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the reporting period.

The year 2009 marked AGL’s second phase that was centered on a sustainable development oriented approach. Accordingly, all implemented projects for 2009 were coherent with AGL strategic objectives, outcomes and outputs. Moreover, projects were implemented in partnership with the working groups, line ministries, relevant municipalities, local stakeholders and DC partners.

At national level, the programme, in collaboration with the Council for Development and Reconstruction (CDR), coordinated with relevant ministries such as the Ministry of Public Health and the Ministry of Interior and with 300 Municipalities, of which ART GOLD had established partnerships with more than 100. At international level, the programme objectives and activities were promoted to European donors and DC partners through the ART Coordination Office based in UNDP Geneva and in collaboration with ART Antennas in Rome and Seville. Also, technical visits were exchanged between Lebanese and European local institutions facilitating the transfer of knowledge, best practices and experiences on issues of common interests. More specifically, the programme in Lebanon mobilized and attracted a number of Decentralized Cooperation partners. To date 45 partnerships have been established with local European partners, of which 10 were newly established in 2009, representing a 20% increase from last year’s.

- Report on the key outputs achieved in the reporting period including # and nature of the activities (inputs), % of completion and beneficiaries.

The key results that AGL achieved in 2009 are identified across the programme’s three main components: Participatory Approach and Working Groups, Local Economic Development, and Decentralized Cooperation:

Participatory Approach and Working Groups:

- The strengthening of local, regional and thematic working groups facilitated.

- Capacity building to WGs provided.

- Increased levels of coordination and cooperation between municipalities realized.

- Leadership role of Municipalities facilitated. (Municipalities are the ones responsible for the projects sustainability and for the mobilization of the community to support AG interventions.)

- WGs meetings involved different stakeholders to work together, create synergy among them and avoid duplication of projects.

- International exposure and intercultural relations built through the various missions conducted to and from Lebanon

Local Economic Development

ART GOLD ensured that the 2009 LRF contribution is focused on Local Economic Development activities.

- The LEDA mandate developed and discussed with the working groups, municipalities and line ministries.

- Four Local Economic Development Offices established and equipped in the four areas. Two persons recruited in each of these offices (Local Economic development Expert, and Bussiness Development Officer). Staff empowerment on Local Economic development conducted.

- Technical assistance provided to 100 farmers for the creation of cooperatives and to 15 cooperatives on organization and management, outreaching 100 beneficiaries

- The Bank managing the Guarantee Fund has been selected. As an instrument to facilitate access to credit for micro, small and medium enterprise partners of AGL, the GF will be operational before the end of the year 2009.

Decentralized Cooperation

- A DC strategy paper for Spain developed to help identify DC partners and coordinate their actions in line with the territorial priorities for greater impact.

- A set of criteria developed to facilitate the DC management. These include: Knowledge on the ART GOLD Methodology, Coherence with the Strategic Objectives and Outcomes of the AGL Program, Following the standard form and templates, When possible, promote the DC coalitions, Promoting economies of scale and synergies, and Ensure communication and visibility)

- Network with DC partners promoted through the participation in workshops, meetings, networking for the establishment or strengthening of local partnerships (for example preparation of ENPI proposals) and through the DC missions conducted to and from Lebanon and to Spain.

Please refer to Annex (1) to update on projects implemented through the Spanish fund.

- Explain, if relevant, delays in programme implementation, the nature of the constraints, actions taken to mitigate future delays and lessons learned in the process.

Few constraints were identified. These include the following:

- Political instability and security conditions make long-term planning difficult.

- Significant gaps in data and statistics due to the lack of coordination among ministries.

- Delays in implementation incurred due to the upcoming municipal elections.

Lessons Learned were identified under each of the programme’s three main components: 1)participatory approach and working groups, :2) Decentralized Cooperation and 3) Local economic Development

1) Participatory Approach and Working groups:

- Moving from numerous local working group (WG) towards regional working group (RWG)

- Local ownership more obvious whenever a bottom-up approach is used

2) Decentralized partnerships:

- The DC Partnerships are sometimes more fruitful if the partners experience similar challenges and contexts

- Working groups’ efficient and effective cooperation with decentralised cooperation partners has contributed to sustainable local development

- DC is a learning opportunity for a country such as Lebanon with a strong centralized administration, moving towards administrative decentralization

3) Local Economic Development:

- Innovative solutions: LEDOs instead of LEDAs

- List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

In 2009-2010, UNDP AGL adopted a multi-donor strategic framework with the aim to help boost accountability and strengthen resource effectiveness through uniting and pooling donor contributions. Besides Italy, whose funding first helped establish ART GOLD Lebanon, other donors who to AGL are Spain, Belgium, and the Principality of Monaco. The 2009 Spanish contribution was €1.5 M, representing 35% of the total funding

In cooperation with the Council for Development and Reconstruction (CDR), AGL coordinates closely with line ministries and ensures all projects comply with the national policies on health, water, agriculture and youth. This close liaison between the programme and relevant ministries helps improve the exchange of information, and strengthen cooperation and coordination. Moreover, it is envisioned that the strong linkage with line ministries ensures the ownership of ART GOLD interventions and the coherence between the local development strategies and the national priorities following a multi-scale approach.

Moroever, the programme works in partnership with municipalities and/or unions of municipalities ensuring by that to build their capacities.

In line with the above mentioned, AGL also developed partnerships with the DC helping namely Lebanese, European, and International communities to share experiences, best practices and know-how.

International Partners:

  - Government of Italy

  - Government of Spain

  - Government of Belgium

  - Principality of Monaco

DC partners: ART GOLD Lebanon has established partnerships with around 50 local European partners, to name a few: FAMSI (Federacion Andaluza de Muinicipios para la Solidaridad Internacional, SPAIN), Diputacion de Barcelona , Catalan Cooperative Agency for Development, Tuscany region, COCOPA (Coordinamento de Municipi de la province de Turino, Italy), Sint-Truiden Municipality (Belgium), and Les Amis du Liban from Monaco.

National Partners:

Council for Development and Reconstruction, line ministries and municipalities

- Other highlights and cross-cutting issues pertinent to the results being reported on.

# Future Work Plan (if applicable)

- Summarize the projected activities and expenditures for the following reporting period (1 January-31 December 2010), using the lessons learned during the previous reporting period.

South Lebanon:

Strategic Objective 1: Enhance the preservation of the Environment: towards an integrated water and solid waste management and increase in the use of renewable energy.

Projects approved address the following:

- Strengthening the water management systems supported during 2009 by replicating the successful approach in new areas.

- Improving the solid waste management in Tyre by replicating a successful experience of a compost facility.

Strategic Objective 2: Increase income generation and job opportunities focusing on women and youth groups in agro industry and small scale enterprises (shoe making, pottery, and glass industry).

Projects identified:

Projects approved address the following:

- Promoting the artisanal business development among youth and facilitating their access to job opportunities through the provision of vocational trainings. Support also includes the procurement of equipment.

- Increasing the production (quality and quantity) in key sectors including milk, honey and pottery production. Support also includes the procurement of equipment.

- Supporting women cooperatives through the creation of a network for food production. This entails building capacities of women and procurement of needed equipment.

Bekaa:

Strategic Objective 1: Increase access to quality social services with focus on Primary Health Care

Projects approved address the following:

- Enhancing access to PHCCs through improving equipment and developing a network of centers in remote areas such as Hermel, Baalbeck and Rashaya.

Strategic Objective 2: Enhance the preservation and quality of the environment with focus on forestry and water management.

Projects approved address the following:

- Increasing reforestation and implementing specific interventions in water management to help preserve the environment and improve the quality of agricultural production.

Strategic objective 3: Increase income generation and job opportunities in tourism and agro-industry with focus on dairy production, beekeeping, fruit and vegetables, and vineyards.

Projects approved address the following:

- Creating and strengthening SMEs in Eco-Tourism, Agro-Industry, Bee keeping, dairy and Fruit and Vegetable.

North Lebanon

Strategic Objective 1: Increase access to quality social services with focus on primary health care and education in Akkar, Minnieh-Dinnieh and Tripoli.

Projects approved address the following:

- Enhancing access to Primary Health Care (PHC) services and improving their quality through capacity building/ personnel training, and the procurement of equipment in addition to the creation of a system/network among the centres in Akkar, Tripoli and Dannieh.

Strategic Objective 2: Increase youth participation in local development processes in Akkar and Minnieh-Dinnieh.

Projects approved address the following:

- Enhancing the social integration and empowerment of youth by setting youth cultural centres. These centres provide trainings to facilitate access to job opportunities and to educational resources, raising awareness in such areas as health, citizenship, institution building and personal networking. The projects entail the creation of a network among the centres.

Strategic Objective 3: Increase income generation and job opportunities focusing on agriculture and agro industry (Milk, beekeeping, fruit and vegetables and fishing) particularly in Akkar and Minnieh Dinnieh

Projects approved address the following:

- Increasing the quantity and quality of rain-fed crops, honey and, milk produced in the region, through capacity building/trainings to farmers, beekeepers, and cow breeders.

- Promoting access to job opportunities to the youth through specific trainings in sectors that demand labour force such as construction, or mechanics among others.

Beirut Southern Suburbs:

Strategic Objective 1: Increase access to public health care services.

Projects approved address the following components:

- Setting up an Epidemiological data base through the Health Informatic System (HIS) of the MoPH.

- Starting up of the basic referral system.

- Ensuring the sustainability of the 3 PHCCs through receiving the Ministry of Interior and Municipalities approval for hiring the PHCCs personnel and involving the PHCCs in the accreditation process of the MoPH.

Strategic Objective 2: Enhance the Social integration of vulnerable youth.

Projects approved address the following:

- Youth offices for planning, networking and implementation operational in the municipalities.

- Improving the skills of the personnel at the Youth Municipal Offices (YMO)

- Producing the action plan for social promotion for 2011 and 2012 (reducing school drop- out and facing social exclusion).

- Receiving approval from the Ministry of Interior and Municipalities for hiring the personnel on contract basis.

- Developing and implementing an action plan to reduce school dropouts

Strategic Objective 3: Increase income generation and job opportunities for small scale enterprises (women and youth).

Projects approved address the following:

- Provide technical support to vulnerable groups in the fishing and handcraft sectors.

National Component:

Strategic Objective 1: Enhance access to quality social services with focus on primary health care services

Strategic Objective 2: Enhance the preservation of the Environment.

Strategic Objective 3: Enhance the social integration and dialogue of youth.

Strategic Objective 4: Multiply LED opportunities according to the strategic objectives established at area level.

International Component:

Strategic Objective 1: Promote international partnerships (especially Spanish DC partnership) and disseminate the ART GOLD methodology.

Strategic Objective 2: Coordinate efforts of donors and promote partnerships between different actors of international cooperation within the multi-donor framework.

Strategic Objective 3: Multiply LED opportunities with other ART experiences according to the international networks

- Indicate any major adjustments in strategies, targets or key outcomes and outputs planned.

# Performance Indicators (optional)

- Fill the table in this section to report on the indicators set at the output level as per the approved results framework in the programme document.

# Abbreviations and Acronyms

- List the main abbreviations and acronyms that are used in the report.

Annex: 1

Projects Status

Last Updated Dec: 2009

|  | Mohafaza | Village | Project Description | Sector | Starting Date | Expected Ending Date | Budget Breakdown | Progress to Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Funding Source |  |
|  | ART GOLD – South Lebanon, Status of 2009 Projects |
|  | Tyre Caza |
| 1 | South Lebanon and Nabatiyeh | Tyre and Union of Jabal Amel Municipalities | Improvement in drinking water distribution infrastructures and the water resource management system in the districts of Tyre and Jabal Amel | Env't/Watr Mng't | Aug-09 | Dec-09 | Spain | Progress to date: 85% |
|  | All Cazas |
| 2 | South Lebanon and Nabatiyeh |  | Women cooperative network | LED | Aug-09 | Jun-10 | Spain | Progress to date: 45% Assesment, Selection, Shortlisting food safety experts & selection of products |
|  | ART GOLD – Bekaa, Status of 2009 Projects |
|  | Baalbeck Caza |
| 3 | Bekaa | Baalbeck | Construction of Kiosks – Municiplity of Baalbeck | Tourism | Aug-09 | Oct-09 | Belgium | Project completed |
|  |  |  |  |  |  |  | Spain |  |
|  |  |  |  |  |  |  | Baalbeck Mun. |  |
| 4 | Bekaa | Nahle | Nahle irrigation canal | Env't/water Mng't | Oct-09 | Jan-10 | Spain | Progress to date: 20% |
|  | Hermel Caza |
| 5 | Bekaa | Alqaser | Establishment of a PHC (equipment) | Health | Aug-09 | Sep-09 | Spain | Completed |
|  | Rachaya Caza |
| 6 | Bekaa | Khawkaba | Reforestation & Fire Prevention (nursery) | Env't/ Watr Mng't | Sep-09 | Oct-09 | Spain | progress to date 100% |
|  |  |  |  |  |  |  | Kawkaba Mun. |  |
| 7 | Bekaa |  | Provision of 10000 pollen trees -eucalyptus & Acacia- to beekeepers in W.Bekaa & Rashaya | LED | Mid Nov. 2009 | Spain | Completed. |
|  | ART GOLD – North Lebanon, Status of 2009 projects |
|  | Al-Minnieh Al Dinnieh Caza |
| 8 | North | Azqi | Rehabilitation of cultural centre | Social | Nov. 09 | Dec. 09 | Belgium | Progress to date: 80% |
|  |  |  |  |  |  |  | Spain |  |
| 9 | North | Bakhoun | Rehabilitation of primary health care centre | Health | Nov. 09 | Feb 10 | Belgium | Progress to date: 50% |
|  |  |  |  |  |  |  | Spain |  |
| 10 | North | Deir Nbouh | Establish youth IT center | Youth | Nov. 09 | Dec.09 | Belgium | Progress to date: 80% |
|  |  |  |  |  |  |  | Spain |  |
| 11 | North | Kfarchalan | Build a municipal playground | Youth | Dec-08 | Sep-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  | Akkar Caza |
| 12 | North | Abboudieh | Rehabilitation of Primary health Care center | Health | Nov. 09 | Feb.10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 13 | North | Akkar | Establishment of a laboratory for soil & water testing & analysis at the LARI- Aabdeh station located in Akkar | Agriculture /LED | Nov. 09 | Dec.10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 14 | North | Akkar Atika | Establish Youth IT Center | Youth | Nov. 09 | Dec. 10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 15 | North | Fneidek | Establish a public park for children | Social | Oct-09 | Dec-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 16 | North | Halba | Establish a public park for children | Social | Oct-09 | Dec-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 17 | North | Halba | Rehabilitation of cultural center | Social | Nov. 09 | Dec. 09 | Belgium | Progress to date: 80% |
|  |  |  |  |  |  |  | Spain |  |
| 18 | North | Qobayat | Establish Youth IT center | Youth | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  | Tripoli Caza |
| 19 | North | Tebbeneh | Rehabilitation of Primary health Care center | Health | Nov 09 | Feb 10 | Belgium | Progress to date: 50% |
|  |  |  |  |  |  |  | Spain |  |
| 20 | North | Tripoli | Support the Youth vocational Training project | Youth | Nov. 09 | Dec. 09 | Italy | Progress to date: 50% |
|  |  |  |  |  |  |  | Italian DC |  |
|  |  |  |  |  |  |  | Spain |  |
| 21 | North | Tripoli | Establish Youth IT center | Youth | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 22 | North | to be defined | Establish Youth IT center | Youth | To be defined | Belgium | Delays incurred due to the upcoming municipal elections. |
|  |  |  |  |  |  | Spain |  |
|  | ART GOLD- Beirut Southern Suburbs, Status of 2009 projects |
|  | Baabda Caza |
| 23 | Mount Leb | Al Chiah, | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Progress to Date (%): 70% |
| 24 | Mount Leb | Hadath | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Progress to Date (%):70% |
| 25 | Mount Leb | Furn El Chebbak | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Progress to Date (%): 70% |
| 25.1 |  |  | Provision of equipment for the social programme in Al-Chiah - Al-Hadath - Furn Al Chebbak |  | 2009 | Spain | Completed |
| 25.2 | Mount Leb | Al-Chiah - Al-Hadath - Furn Al Chebbak | Capacity Building within the 3 projects "Social development addressed to youth" |  | 2009 | Tuscany Region -ARCI network | Completed |
|  |  |  |  |  |  | Spain |  |
| 26 | Mount Leb | Al Mreyjeh | Scholastic maps of Risk and Ressources | Social | Feb-08 | Oct-08 | Spain | Completed |
| 26.1 | Mount Leb | Al Mreyjeh | Capacity Building within the project "Scholastic maps of Risk and Ressources" | Social | Feb-09 | Oct-09 | Spain | Completed |
| 27 | Mount Leb | Haret Hreik | Pilot Programme for strengthening the Public Health Care Centers (PHCC) in Beirut Southern Suburbs | Health | Jul-08 | Dec-09 | Spain | Completed |
| 28 | Mount Leb | Haret Hreik Ghobeiri Burj Al Barajneh | Capacity Building within the "Pilot Programme for strengthening the Public Health Care Centers (PHCC)" |  |  |  | Spain | Progress to date (%): 60% |
|  |  |  |  |  |  |  | Arezzo Municipality- Tuscany region |  |
| 29 | Mount Leb | Haret Hreik Ghobeiri Burj Al Barajneh | Provision of equipment within the "Pilot Programme for strengthening the Public Health Care Centers (PHCC)" | Health |  |  | Spain | Progress to date (%):30% |

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

The start date is the date of the first transfer of funds from the MDTF Office as Administrative Agent.

All activities for which a Participating Organization is responsible under an approved MDTF programme have been completed. Agencies to advise the MDTF Office.

E.g. for the UNDG Iraq Trust Fund and the MDG-F.