THREE-MONTH PROGRESS REPORT

LEBANON RECOVERY FUND

Reporting UN Participating Organisation: FAO

### Country: Lebanon

### Project No. and Project Title:

LRF-3 OSRO/LEB/701/UNJ - Early recovery assistance for the horticulture smallholder

### Reporting Period:     1 April to 30 June 2009

LRF-3 OSRO/LEB/701/UNJ - Early recovery assistance for the horticulture smallholder

### PURPOSE

- Main objectives and outcomes expected as per approved project document.

The development goal of the project is to improve horticulture practices in Lebanon by improving cultivars, planting densities, greenhouse structure, Good Agriculture Practices (GAP), efficiency-use of water, fertilizers and rational use of low toxicity pesticides for the production of organic vegetables. The key immediate objective of the project is to provide support to the lives and livelihoods of 1 600 resource-poor and vulnerable horticulture farmers – with critical crop harvest losses – in south Lebanon who were severely affected by the July/August 2006 hostilities.

All the activities for assisting resource-poor farmers were completed during the current reporting period and in accordance to the project workplan. FAO provided assistance to 1 846 beneficiaries in 77 villages (246 more beneficiaries than originally planned in the project document). The activities completed are as follows: installation of 50 crop production greenhouses, four plant nurseries, procurement of 1 000 low tunnels for open field farming, and upgrading of 40 single and double span greenhouses. High quality vegetable seeds (cucumber, melon, squash, snake melon, okra and bean) were distributed to open field farmers and 60 000 grafted plantlets from high quality, high yielding vegetable seed (tomato and cucumber) were distributed to plant nursery greenhouse farmers in September in time for the autumn cropping season. The project completed distribution of fertilizers, including organic fertilizer and peat to enrich the soil with nutrients for improved crop production, quality and increase yield. In addition, FAO has procured low toxicity plant protection products for pest control. Improvements in agriculture practices in south Lebanon will help provide the essential nutrients for the family diet of targeted vulnerable groups and also help generate much needed household income.

Reference to how the programme/project relates to the national priorities and how it aims to support national reconstruction goals of Lebanon.

Following the hostilities in Lebanon in the summer of 2006, and at the request of the Government of Lebanon, FAO conducted jointly with the Ministry of Agriculture a “Damage and Early Recovery Needs Assessment of Agriculture, Fisheries and Forestry” mission. To meet the recovery needs of the most vulnerable, war-affected horticulture farmers and respond to the national reconstruction goals of Lebanon, the project will support farmers through the replacement of lost assets.  The improved greenhouse design will contribute to an increased harvest of high quality produce.  In addition, the project will introduce nurseries in remote areas, thus introducing a supply of plantlets farmers. FAO is distributing high quality hybrid vegetable seed of certified origin, in compliance with FAO international standards and registered with the Ministry of Agriculture in Lebanon. All plant protection products are registered in Lebanon. All these measures are to provide a sustainable vegetable production system in south Lebanon and introduce innovative agricultural practices that will benefit the farming community and contribute to poverty alleviation in the long term.

- List of the main international and national implementing partners involved.

FAO, Ministry of Agriculture, local municipalities, farmers unions and farmer cooperatives.

### II. FINANCIAL RESOURCES

Total Programme/Project Cost: US $ 1 370 670

LRF:  US $ 1 370 670

Government Input: US $ 0

Other: US $ 0

Total:  US $ 1 370 670

MAIN BUDGET ACTIVITIES:

The below budget reflects all expenditures up to 30 April 2009 and indicates a delivery rate of 99.4 percent. FAO distributed all agriculture inputs procured under the project and provided training to open field farmers and greenhouse farmers during the current reporting period.  The project was operationally closed on 30 April 2009.

Budget: commitment and disbursement:

| OSRO/LEB/701/LEB |
| --- |
| Item | Approved Budget (in US$): | Disbursement/ Commitment (in US$) |
| Personnel and travel: | 435 934 | 426 984 |
| Agriculture supplies / commodities / equipment: | 767 349 | 734 349 |
| Miscellaneous / Other: | 105 717 | 107 429 |
| Indirect support costs: | 89 670 | 89 150 |
| TOTAL: | 1 370 670 | 1 362 912 |

Personnel and travel costs:

FAO expenditures for personnel and associated travel costs cover four missions from the Chief Technical Advisor (CTA) as well as various backstopping missions from Headquarters to the field for project monitoring and backstopping. In addition, costs for local staff working under the horticulture project are included under this budget line.

|  | Approved Budget cost (in US$): | Estimated Disbursement/ Commitment (in US$) |
| --- | --- | --- |
| Personnel and travel: | 435 934 | 426 984 |

Agriculture equipment and supplies costs:

FAO had conducted a thorough selection of beneficiaries based on specific criteria developed by the project (farmers had to be resource poor, war-affected and still living on their farms and able to carry out horticulture activities). FAO had selected 94 beneficiaries for greenhouses (four plant nursery greenhouses, 50 crop production greenhouses, 40 updgraded greenhouses). In the original project document, the number of open field beneficiaries was 1 406, however, the project was able to extend seed and fertilizer distribution to 1 752 farmer beneficiaries in 77 villages. Agriculture supplies such as vegetable seeds, fertilizers, low tunnels were distributed to farmers in time for summer and fall cropping seasons. The project reached a total of 1 846 beneficiaries.

| Item | Approved Budgeted cost (in US$): | Estimated Disbursement/ Commitment (in US$): |
| --- | --- | --- |
| Agriculture equipment and supplies | 767 349 | 734 349 |

Other costs (Training, General Operating Expenses, and Miscellaneous):

Expenditures under “Other”, groups together budget lines such as training, general operating expenses, miscellaneous and overhead costs. Please note that full charges to support costs appear only on delivery of all project activities.

|  | Approved Budget cost (in US$): | Estimated Disbursement/ Commitment (in US$) |
| --- | --- | --- |
| Other: | 108 151 | 107 429 |

### III. 	RESULTS

- Progress achievement assessment of project component in relation to the outcomes and outputs expected for the duration of the project.

Outcome:

Provide assistance to the lives and livelihoods of 1 846 resource-poor and vulnerable horticulture war-affected farmers – with critical crop harvest losses. The project aimed to sustain the early rehabilitation and recovery of smallholder horticulture farmers in South and Nabatiyeh governorates and to ensure early recovery of productive agricultural activities.

Outputs:

Output 1:	Small-scale farmers enabled to resume crop production activities, and technical improvement of the production systems.

Output 2: Soil, water- and fertilizer-use efficiency improved through effective use of water using localized/adapted drip irrigation systems.

Output 3: 	Training Capacity of farmers and stakeholders built on the needs and means to rehabilitate the horticulture sector.

Output 4: 	South Lebanon open field concept, greenhouse design improved for higher quality harvest and increased yields.

2. Procurement of inputs

All seeds, organic fertilizer and greenhouse equipment had been procured within previous reporting periods from suppliers within Lebanon, thus contributing to the local economy and supporting local knowledge and experience.

The project assisted 1 752 open field farmers through the distribution of seeds (varieties included cucumber, melon, squash, snake melon, okra and bean) as well as fertilizers to help in crop production for the 2008 summer cropping season. In addition, FAO assisted 94 greenhouse farmers through the distribution and installation of greenhouse nurseries (four), crop production greenhouses (50) and upgraded 40 damaged greenhouses and 1 100 low tunnels. Crop production in the greenhouses increased threefold as the new design in ventilation and humidity index helped in the increased harvest yields.

3. Training and Capacity Building of farmers and stakeholders:

FAO provided training and agriculture advisory services to farmers until project closure in April 2008. The technical support is highly appreciated by farmers and FAO’s officers continued to carry out farm visits and follow up on crop production techniques. Most farmers still use traditional methods and the consistent support by FAO in good agricultural practices will ensure that sustainability to improved harvests, better crop quality and greenhouse maintenance continues after project closure.

Implementation constraints, lessons learned from addressing these and knowledge gained from evaluations and studies that have taken place during the reporting period.

As mentioned in the last progress report, an Evaluation Mission was fielded from 16 to 30 November 2008 and revealed that the horticulture and livestock projects distributed high-value, well-appreciated inputs; however, further training was required. FAO continued to provide training to farmers up to project closure of 30 April 2009 in order to provide advisory services on good agriculture practices to increase quality and yields.

Key partnerships and inter-agency collaboration: impact on results.

- Close collaboration with the MOA as the main national counterpart is continuous.

- Close collaboration with United Nations Mine Action Coordination Centre of Southern Lebanon 	(MACCSL) and FAO is working in mine-cleared lands accordingly.

- Through the Livelihoods Sector Working Group at the field level, coordination is taking place with all 	related agencies and NGOs to ensure no duplication of assistance and properly identify gaps and needs 	to streamline all related activities.

- Coordination with ILO on training modules relating to horticulture for common beneficiaries.

Other highlights and cross cutting issues pertinent to the results being reported on.

### IV. FUTURE WORK PLAN

- Priority actions planned for the subsequent reporting period to overcome constraints, build on achievements and partnerships, and use the lessons learned during the previous period.

None.

Indication of major adjustments in the strategies, targets or key outcomes and outputs.

Project closure date 30 April 2009.

------------------------------------------------------------------------------