## Sheet1
Annual Work Plan
Project ID: 00058325
Project Title: Inter-Ministerial Committee
Year: 2009
EXPECTED OUTPUTS | PLANNED ACTIVITIES | TIMEFRAME |  |  |  | RESPONSIBLE PARTY | PLANNED BUDGET
And baseline, associated indicators and annual targets | List activity results and associated actions | Q1 | Q2 | Q3 | Q4 |  | Funding Source | Budget Description | Amount
Output 1: Support the elaboration of a national social development strategy and implementation plan (including a national anti poverty strategy) | Activity Result: National Social Strategy developed | [7 empty] | 123750
Baseline: National Social strategy not available | Recruit consultant / institution to undertake the mission of elaborating and social strategy |  |  |  |  | Poverty Project / Inter-Ministerial Committee | LRF
Indicators: | Compile available studies and sectoral strategies
Targets: Social development strategy endorsed | Prepare draft / detailed outline of social strategy
Related CP outcome(s): | Organize workshops to reach consensus on components of social strategy
Synthesize available studies, sectoral strategies and the outcomes of the workshops and prepare final draft of social strategy
Based on strategy develop detailed workplan for the implementation of the strategy with identified outputs, time plan, resources required, performance indicators
Endorse strategy by IMC
Output 2: Provision of Social Services and implementation of programs better coordinated between MoSA, MoPH and MEHE | Activity Result: Plan for reduction of duplication of social services and programs elaborated and duplication reduction activities initiated | [7 empty] | 30600
Baseline: Zero duplicated program are eliminated | Identify and compile duplicated programs between MoSA, MoPH and MEHE. Prepare detailed report and presentation on duplicated programs |  |  |  |  | Poverty Project / Inter-Ministerial Committee | LRF
Indicators: | Organize/coordinate working sessions/meetings between MoSA, MoPH and MEHE to discuss and reach consensus on actions to reduce duplication and improve
Targets: by end of 2010, 40% of duplicated programs are reformed | Coordinate and support the implementation of concrete actions for reducing duplication based on decisions taken between the concerned ministries (transfer of certain services, closing of centers, establishment of coordination setups)
Related CP outcome:
Output 3: Implementation of local development initiatives better coordinated and better synchronized with needs and priorities | Activity Result: Mapping and database of local development project produced and disseminated and framework of development needs and prioritized developed | [7 empty] | 73250
Baseline: No database of local development initiatives and no framework for needs | Review and finalize mapping based on workshop outcomes |  |  |  |  | Poverty Project / Inter-Ministerial Committee | LRF
Indicators: | Ensure regular update of the local development database
Targets: by Q1 of 2009, database developed and disseminated and by Q4 of 2009 framework of needs and priorities developed | Develop an interactive map on local development initiatives implemented by the government and update regularly
Related CP outcome: | Elaborate a framework of needs and priorities in the regions (with detailed mapping) based on compilation of existing studies and reports *
TOTAL | [8 empty] | 227600
* For details check activity number 2 of output 1. Budget for this action is estimated at 15,000.