### PROGRESS REPORT

| Reporting UN Organization | : | United Nations Development Programme |
| --- | --- | --- |
| Country | : | Lebanon |
| Project No. | : | LRF - 19 |
| Project Title | : | Socio – Economic Rehabilitation Programme in the Framework of ART GOLD Lebanon. |
| LRF Signature date | : | March 26, 2009 |
| Project Start date | : | April 2009 |
| Project Timeframe | : | 2009 - 2010 |
| Reporting Period | : | Oct - Dec 2009 |

I. PURPOSE

Project Summary:

The ART GOLD Programme is a part of the ART global initiative that was specially designed by a group of UN Agencies under UNDP leadership (UNESCO, UNIFEM, WHO, UNITAR and UNOPS).

The ART GOLD Lebanon (AGL) was launched in March 2007 in the four neediest areas of the country, characterized by high poverty rates and raging socio-economic problems: North Lebanon, South Lebanon, Bekaa and Beirut Southern Suburbs (BSS). The programme is managed at country level by UNDP in partnership with its national counterpart the Council for Development and Reconstruction (CDR).

The ART GOLD is based on a cooperation framework between local, national and international partners interested in combining and coordinating their efforts to achieve the Millennium Development Goals (MDGs) and to contribute to local governance, decentralization and balanced socio-economic development in the medium and long term.

ART GOLD Main Donors

Besides Italy, whose funding first helped the establishment of ART GOLD Lebanon, other donors who have also announced significant financial contributions to AGL are Belgium, the Principality of Monaco and Spain.

2009 Spanish Contribution for ART GOLD

The Spanish Government is providing its support (effective in 2009) in sectors identified by the Local Working Groups in the four programme areas. The 2009 Spanish contribution was €1.5 M, representing 35% of the total funding.

2009 Spanish Fund Allocation for ART GOLD Lebanon.

In 2009, 60% of the Spanish fund was allocated for “Increase Income generation and Job opportunities” activities, followed by “Youth development” (24%), “Enhance Water Management” (10%) and “Support to Primary Health care” (6%).

In addition to this, the Spanish Government has contributed a sum of $400,000 for the National and International components of ART GOLD. The Nnational component assures the technical support and monitoring to the areas and promotes coordination among them. At the national level it is ensured that the project’s initiatives are implemented in accordance with Government policies. The International component ensures liaison with donor countries, promotes decentralized cooperation partnerships and exchange of best practices and international events (ILS LEDA, UNIVERSITAS etc...).

Project Objectives:

The ARTGOLD Lebanon’s overall objective is to support the Lebanese national government and the local communities in elaborating and implementing Strategic Development Plans, within the programme’s target areas while focusing on the most disadvantaged people, towards the achievement of the Millennium Development Goals (MDGs).

Most specifically, the programme aims to:

- Increase access to primary public health care services

- Increase sustainable income generation and job opportunities

- Enhance the preservation of the environment

- Increase youth participation in local development and enhance their social integration

Project Outcomes:

- Number of patients with access to primary health care centers increased (Bekaa, North Lebanon, BSS)

- Incomes increased for about 600 beneficiaries (South Lebanon, Bekaa, North Lebanon, BSS)

- Separation of solid waste facilitated (South Lebanon, Bekaa)

- Access to information technology for youth increased and youth offices established within municipalities. (North Lebanon, BSS)

Project Linkages to National Priorities and Reconstruction Goals:

The projects are in line with the Government’s goals to support basic social services and primary health care, enhance social integration and support to the youth, enhance the preservation of the environment (waste, water, energy and forestry) and Increase income generation and job opportunities.

Project Implementation Partners:

International Partners:

- Government of Italy

- Government of Spain

- Government of Belgium

- Principality of Monaco

DC partners: ART GOLD Lebanon has established partnerships with around 50 local European partners, to name a few: FAMSI (Federacion Andaluza de Muinicipios para la Solidaridad Internacional, SPAIN), Diputacion de Barcelona , Catalan Cooperative Agency for Development, Tuscany region, COCOPA (Coordinamento de Municipi de la province de Turino, Italy), Sint-Truiden Municipality (Belgium), and Les Amis du Liban from Monaco.

National Partners:

Council for Development and Reconstruction, line ministries and municipalities

II. RESOURCES

Belgium, Italy, Principality of Monaco and Spain contributed a total of US.$.6.8 M to ART GOLD’s 2009 strategy to which other  contributions, in cash and kind, from different Decentralized Cooperation partners are added.

|  | Preliminary Financial Report as of December 31st, 2009 |  |
| --- | --- | --- |
|  | Account | Amount Disbursed by project |
|  |  | 00053003 - ARTGOLD Lebanon | 00056944 - ARTGOLD BSS | 00056945 - ARTGOLD South | 00056946 - ARTGOLD Bekaa | 00056947 - ARTGOLD North | 00073242 - Guarantee fund |
| 71300 | Local Consultants | - | - | - | 2,600.00 | - | - |
| 71400 | Contractual Services - Individual | - | - | 13,855.20 | 16,004.00 | - | - |
| 71600 | Travel | 5,676.80 | - | 240.00 | 1,225.09 | - | - |
| 72100 | Contractual Services-Companies | - | 151,078.00 | - | 18,850.00 | - | - |
| 72200 | Equipment and Furniture | - | 5,571.00 | - | 1,895.00 | 42,961.05 | - |
| 72300 | Materials & Goods | - | - | - | 39,007.00 | - | - |
| 72400 | Communication & Audio Visual Equip | - | - | 1,235.00 |  | - | - |
| 72500 | Supplies | - | 51.00 | - |  | - | - |
| 72600 | Grants | - | - | - | 41,050.00 | 67,145.46 | 520,000.00 |
| 72800 | Information Technology Equip | - | 22,058.30 | 1,385.00 |  | 9,669.77 | - |
| 73100 | Rental & Maintenance-Premises | - | - | - | 2,064.81 | - | - |
| 74200 | Audio Visual & Print Prod Costs | - | 6,650.00 | - | 530.20 | - | - |
| 74500 | Miscellaneous Expenses | - | 957.00 | - | 1,598.34 | - | - |
|  | Total Expenditure per project | 5,676.80 | 186,365.30 | 16,715.20 | 124,824.44 | 119,776.28 | 520,000.00 |
|  | Total Disbursement | 973,358.02 |  |  |  |  |  |
|  | UNDP Indirect Cost (7%) | 68,135.06 |  |  |  |  |  |
|  | Total Expenditure as of Dec 31, 2009 | 1,041,493.08 |  |  |  |  |  |
|  | Total Contribution | 2,391,450.00 |  |  |  |  |  |
|  | Remaining to be spent | 1,349,956.92 |  |  |  |  |  |

III. RESULTS

AGL coordinates closely with line ministries and ensures all projects comply with the national policies on health, water, agriculture and youth. This close liaison between the programme and relevant ministries shall be continued throughout 2010.

Project Outputs and Indicators:

Strategies framework documents developed:

- ART GOLD’s strategies framework document developed following an integrated and bottom up approach. The document outlines the strategic objectives, outcomes and outputs for each of ART GOLD areas of intervention.

- Operations Manual developed outlining the practical procedures for the implementation of the ART GOLD Lebanon project

Working Group (WG) Processes strengthened :

- The strengthening of local, regional and thematic working groups facilitated.

- Capacity building to WGs provided.

- Increased levels of coordination and cooperation between municipalities realized. (This level of cooperation has not been witnessed since 1998 during which municipal elections in Lebanon was reconvened for the first time in 22 years.)

- Leadership role of Municipalities facilitated. (Municipalities are the ones responsible for the projects sustainability and for the mobilization of the community to support AG interventions.)

- WGs meetings involved different stakeholders to work together, create synergy among them and avoid duplication of projects.

- International exposure and intercultural relations built through the various missions conducted to and from Lebanon

ART GOLD ensured that the 2009 LRF contribution is focused on Local Economic Development activities.

Local Economic Development Office (LEDO) Established:

- LEDO start up strategy re-defined

- The LEDO statute developed and discussed with 4 working groups and municipalities.

- Technical assistance provided to 100 farmers for the creation of cooperatives  and  to 15 the cooperatives on organization and management

- Training on LEDOs organized for 4 LED experts and 4 business development officers.

- The Bank managing the Guarantee Fund has been selected. The GF as an instrument to facilitate access to credit for micro, small and medium enterprise partners of AGL will be operational before the end of the year 2009.

Donors Mobilized:

Italy, Spain, Belgium and Principality of Monaco and almost different Decentralized Cooperation partners.

DC partnerships strengthened

- A DC strategy paper for Spain developed to help identify DC partners and coordinate their actions in line with the territorial priorities for greater impact.

- A set of criteria developed to facilitate the DC management. These include: Knowledge on the ART GOLD Methodology, Coherence with the Strategic Objectives and Outcomes of the AGL Program, Following the standard form and templates, When possible, promote the DC coalitions, Promoting economies of scale and synergies, and Ensure communication and visibility)

- Network with DC partners promoted through the participation in workshops, meetings, networking for the establishment or strengthening of local partnerships (for example preparation of ENPI proposals) and through the DC missions conducted to and from Lebanon and to Spain.

Communication and visibility materials produced

- First Newsletter issued covering the period from Dec. 2008 – June 2009 covering briefs on AGL events, intervention in the Health sector, and upcoming activities.  1000 Arabic copies and 500 English copies were published, and disseminated among donor country representatives, potential donor countries, line ministries, CDR, local and International NGOs working in Lebanon; Lebanese Local authorities in AGL targeted areas; UN Chiefs; AGL working groups, media institutions and media reporters at local and central level.

- Identity LOGO developed

- Web site under construction: home page developed and finalized; inside pages are being developed along with the final text. Expected to be online in late March.

- Other promotional materials which relates to the publicity of the programme developed: pens, CDs, blocknotes, notepads, stickers, leather folders, events banners, etc.

- 9 project inaugurations have taken place until the end of 2009:

  - “Health Awareness Project Graduation Ceremony in Tripoli, North Lebanon”,

  - “Inauguration of an audiovisual room in Tripoli, North Lebanon”,

  - “Inauguration of a youth Sports Club in Al Dinniyeh, North Lebanon”,

  - “Inauguration of the municipal playground in Kfarchalan, Al Dinniyeh, North Lebanon”,

  - “Inauguration of 15 Kiosks in Baalbeck city, Bekaa”,

  - “Inauguration of the Social and Cultural center and the public library in Rashaya, Bekaa”,

  - “Inauguration of the commercial and touristic kiosks in Baalbeck, Bekaa”, “Inauguration of Two Water Maintenance centers in Binet Jbeil and Nabatieh, South Lebanon”,

  - “Inauguration of the Primary Health care in Al Qaser, Bekaa”

  - Inauguration of six projects in Akkar Caza including the two IT centers in Qobayyat and Akkar Al Atika, Opening of the two public parks in Fneidek and HAlba, the youth and cultural center in Halba and  a laboratory for soil and water testing and analysis in Abdeh.

A short newsletter covering the above mentioned events was developed and distributed to donors.

End of year calendar/notepads were developed as a season’s greeting: 1000 copies were published, and disseminated among donors, potential donors, line ministries, CDR, local and International NGOs working in Lebanon; Lebanese Local authorities in AGL targeted areas; UN Chiefs; AGL working groups, media institutions and media reporters at local and central level.

Progress in Project Implementation:

The Primary Health Care sector

- Three Primary Health care centers (PHCCs) with international standards adapted to the Lebanese context in Haret Hreik, Ghobeiry and Borj al Barajneh in Beirut Southern

- Number of patients with access to primary health care centers increased to 150,000 in Bekaa, North Lebanon and Beirut Southern Suburbs.

- Quality and quantity of the services improved at the PHCCs in Bekaa, North Lebanon and Beirut Southern Suburbs.

The Local Economic Development Component

- 32,000 farmers have access to the soil and water testing facility in Abdeh, North Lebanon.

- A network of 15 women cooperatives developed in South Lebanon;

- Number of women members of cooperatives increased to 50;

- Marketing and managerial skills of women cooperatives strengthened in South Lebanon.

- 1000 SMEs and disadvantaged groups have access to credits for business development.

The youth sector:

- Youth development strategy and action plans developed and implemented in the three municipalities of Chiah, Hadath and Furn Chebbak in Beirut southern Suburbs;

Three offices for youth development established at these municipalities.

- Services provided at two Cultural Centres (in Halba and Azaki) and four IT centres in Akkar, Minnieh Dinnieh and Tripoli in North Lebanon;

IT, communication, managerial and marketing skills of 2,000 youth developed at those centres.

- Recreational facilities and services for children established over an area of 2,800 square meters in North Lebanon.

The Environment Sector

- Improve capacity building of farmers in pesticides management in Bekaa

- Initiatives conducted for improving water management in Bekaa

- 7,000 trees (for honey bees) are planted to increase honey production in West Bekaa and Rachaya

- Two water maintenance centres in Tyre and Marjeyoun established;

Timely repairs provided to pipes networks upon requests made by the population of 300,000 persons.

Local Development Offices

- Four Local Economic Development Offices established and equipped in the four areas.

- Recruitment process for Local Economic development Experts and Business Development Officers started.

- Training for staff on Local Economic development Conducted.

The Guarantee Fund

- Established at a total of 1. 5 Million USD for 2009.

- First National Bank was selected through a competitive bidding process to facilitate the process of issuing loans to beneficiaries. This project is carried out in collaboration with CDR/the Economic and Social Fund for Development (ESFD. The LED offices will be able to provide loans through the bank up to a total of 25 Million USD over the course of the UNDP AGL Programme; hence encompassing a wider scope of beneficiaries estimated at 1000 entrepreneurs.

- Technical assistance provided to 550 farmers

- Three cooperatives established (dairy, beekeeping and agriculture).

- Technical assistance provided to 15 SMEs and Cooperatives on organization and management, outreaching 100 beneficiaries.

2009 Honey value chain project

- AGL is facilitating the establishment of the National Consortium of Lebanese beekeepers. The National Consortium will help small farmers to better organize their efforts in working collectively with the Government. This falls within a series of activities the AGL is implementing in support of the honey value chain in Lebanon.

- Several trainings were conducted for Lebanese Beekeepers by an Italian Beekeeping expert on disease control among other topics.

- A delegation of Lebanese beekeepers attended the Mediterranean Forum of Beekeepers in October 2009. The Forum aimed at exchanging experiences among Mediterranean beekeepers.

- A screening was conducted on honey quality to prepare the beekeepers for the market.

Please refer to Annex (1) to update on projects implemented through the Spanish fund.

Implementation Constraints and Lessons Learned:

Constraints: Different timing between project implementation and receipt of funds from the different donors. Political instability and security conditions make long-term planning difficult. Significant gaps in data and statistics due to the lack of coordination among ministries. Delays in implementation incurred due to the upcoming municipal elections. Lessons Learned are identified under each of the programme’s three main components: 1)participatory approach and working groups, :2) Decentralized Cooperation and 3) Local economic Development 1)Participatory Approach and Working groups: Moving from numerous local working group (WG) towards regional working group (RWG) Local ownership more obvious whenever a bottom-up approach is used 2)Decentralized partnerships: The DC Partnerships are sometimes more fruitful if the partners experience similar challenges and contexts Working groups’ efficient and effective cooperation with decentralised cooperation partners has contributed to sustainable local development DC is a learning opportunity for a country such as Lebanon with a strong centralized administration, moving towards administrative decentralization 3) Local Economic Development: Innovative solutions: LEDOs instead of LEDAs

IV. FUTURE WORK PLAN

The Area managers organized meetings of the Regional Working Groups to discuss potential 2010 activities. The final selection and approval of the 2010 activities was made end of December 2009.

The 2010 activities maintain consistency and coherency with the strategic framework document. Therefore, only activities that comply with the strategic objectives of the respective regions were selected. However, there are other selection criteria for the activities. Some of these are the following:

- Project quality – justifiable problem, clear goals, relevant and realistic activities; timeframe; gender sensitive; innovative approach; monitoring mechanisms.

- Project effectiveness –quantitative and qualitative target results; long-term partnerships established; sustainable results and long-term impact; replicable model; cost-effective budget. Value added to on-going or already implemented projects.

- Territorial impact for the target groups.

ART GOLD budget proposal for 2010

ART GOLD is proposing donor countries and decentralized cooperation partners for additional funds in support of the 2010 activities. The 2010 contribution would help achieve the following objectives through the below mentioned activities:

South Lebanon:

Strategic Objective 1: Enhance the preservation of the Environment: towards an integrated water and solid waste management and increase in the use of renewable energy.

Projects approved address the following:

- Strengthening the water management systems supported during 2009 by replicating the successful approach in new areas.

- Improving the solid waste management in Tyre by replicating a successful experience of a compost facility.

Strategic Objective 2: Increase income generation and job opportunities focusing on women and youth groups in agro industry and small scale enterprises (shoe making, pottery, and glass industry).

Projects identified:

Projects approved address the following:

- Promoting the artisanal business development among youth and facilitating their access to job opportunities through the provision of vocational trainings. Support also includes the procurement of equipment.

- Increasing the production (quality and quantity) in key sectors including milk, honey and pottery production. Support also includes the procurement of equipment.

- Supporting women cooperatives through the creation of a network for food production. This entails building capacities of women and procurement of needed equipment.

Bekaa:

Strategic Objective 1: Increase access to quality social services with focus on Primary Health Care

Projects approved address the following:

- Enhancing access to PHCCs through improving equipment and developing a network of centers in remote areas such as Hermel, Baalbeck and Rashaya.

Strategic Objective 2: Enhance the preservation and quality of the environment with focus on forestry and water management.

Projects approved address the following:

- Increasing reforestation and implementing specific interventions in water management to help preserve the environment and improve the quality of agricultural production.

Strategic objective 3: Increase income generation and job opportunities in tourism and agro-industry with focus on dairy production, beekeeping, fruit and vegetables, and vineyards.

Projects approved address the following:

- Creating and strengthening SMEs in Eco-Tourism, Agro-Industry, Bee keeping, dairy and Fruit and Vegetable.

North Lebanon

Strategic Objective 1: Increase access to quality social services with focus on primary health care and education in Akkar, Minnieh-Dinnieh and Tripoli.

Projects approved address the following:

- Enhancing access to Primary Health Care (PHC) services and improving their quality through capacity building/ personnel training, and the procurement of equipment in addition to the creation of a system/network among the centres in Akkar, Tripoli and Dannieh.

Strategic Objective 2: Increase youth participation in local development processes in Akkar and Minnieh-Dinnieh.

Projects approved address the following:

- Enhancing the social integration and empowerment of youth by setting youth cultural centres. These centres provide trainings to facilitate access to job opportunities and to educational resources, raising awareness in such areas as health, citizenship, institution building and personal networking. The projects entail the creation of a network among the centres.

Strategic Objective 3: Increase income generation and job opportunities focusing on agriculture and agro industry (Milk, beekeeping, fruit and vegetables and fishing) particularly in Akkar and Minnieh Dinnieh

Projects approved address the following:

- Increasing the quantity and quality of rain-fed crops, honey and, milk produced in the region, through capacity building/trainings to farmers, beekeepers, and cow breeders.

- Promoting access to job opportunities to the youth through specific trainings in sectors that demand labour force such as construction, or mechanics among others.

Beirut Southern Suburbs:

Strategic Objective 1: Increase access to public health care services.

Projects approved address the following components:

- Setting up an Epidemiological data base through the Health Informatic System (HIS) of the MoPH.

- Starting up of the basic referral system.

- Ensuring the sustainability of the 3 PHCCs through receiving the Ministry of Interior and Municipalities approval for hiring the PHCCs personnel and involving the PHCCs in the accreditation process of the MoPH.

Strategic Objective 2: Enhance the Social integration of vulnerable youth.

Projects approved address the following:

- Youth offices for planning, networking and implementation operational in the municipalities.

- Improving the skills of the personnel at the Youth Municipal Offices (YMO)

- Producing the action plan for social promotion for 2011 and 2012 (reducing school drop- out and facing social exclusion).

- Receiving approval from the Ministry of Interior and Municipalities for hiring the personnel on contract basis.

- Developing and implementing an action plan to reduce school dropouts

Strategic Objective 3: Increase income generation and job opportunities for small scale enterprises (women and youth).

Projects approved address the following:

- Provide technical support to vulnerable groups in the fishing and handcraft sectors.

National Component:

Strategic Objective 1: Enhance access to quality social services with focus on primary health care services

Strategic Objective 2: Enhance the preservation of the Environment.

Strategic Objective 3: Enhance the social integration and dialogue of youth.

Strategic Objective 4: Multiply LED opportunities according to the strategic objectives established at area level.

International Component:

Strategic Objective 1: Promote international partnerships (especially Spanish DC partnership) and disseminate the ART GOLD methodology.

Strategic Objective 2: Coordinate efforts of donors and promote partnerships between different actors of international cooperation within the multi-donor framework.

Strategic Objective 3: Multiply LED opportunities with other ART experiences according to the international networks

Annex: 1

Projects Status

Last Updated Dec: 2009

|  | Mohafaza | Village | Project Description | Sector | Starting Date | Expected Ending Date | Budget Breakdown | Progress to Date |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Funding Source |  |
|  | ART GOLD – South Lebanon, Status of 2009 Projects |
|  | Tyre Caza |
| 1 | South Lebanon and Nabatiyeh | Tyre and Union of Jabal Amel Municipalities | Improvement in drinking water distribution infrastructures and the water resource management system in the districts of Tyre and Jabal Amel | Env't/Watr Mng't | Aug-09 | Dec-09 | Spain | Progress to date: 85% |
|  | All Cazas |
| 2 | South Lebanon and Nabatiyeh |  | Women cooperative network | LED | Aug-09 | Jun-10 | Spain | Progress to date: 45% Assesment, Selection, Shortlisting food safety experts & selection of products |
|  | ART GOLD – Bekaa, Status of 2009 Projects |
|  | Baalbeck Caza |
| 3 | Bekaa | Baalbeck | Construction of Kiosks – Municiplity of Baalbeck | Tourism | Aug-09 | Oct-09 | Belgium | Project completed |
|  |  |  |  |  |  |  | Spain |  |
|  |  |  |  |  |  |  | Baalbeck Mun. |  |
| 4 | Bekaa | Nahle | Nahle irrigation canal | Env't/water Mng't | Oct-09 | Jan-10 | Spain | Progress to date: 20% |
|  | Hermel Caza |
| 5 | Bekaa | Alqaser | Establishment of a PHC (equipment) | Health | Aug-09 | Sep-09 | Spain | Completed |
|  | Rachaya Caza |
| 6 | Bekaa | Khawkaba | Reforestation & Fire Prevention (nursery) | Env't/ Watr Mng't | Sep-09 | Oct-09 | Spain | progress to date 100% |
|  |  |  |  |  |  |  | Kawkaba Mun. |  |
| 7 | Bekaa |  | Provision of 10000 pollen trees -eucalyptus & Acacia- to beekeepers in W.Bekaa & Rashaya | LED | Mid Nov. 2009 | Spain | Completed. |
|  | ART GOLD – North Lebanon, Status of 2009 projects |
|  | Al-Minnieh Al Dinnieh Caza |
| 8 | North | Azqi | Rehabilitation of cultural centre | Social | Nov. 09 | Dec. 09 | Belgium | Progress to date: 80% |
|  |  |  |  |  |  |  | Spain |  |
| 9 | North | Bakhoun | Rehabilitation of primary health care centre | Health | Nov. 09 | Feb 10 | Belgium | Progress to date: 50% |
|  |  |  |  |  |  |  | Spain |  |
| 10 | North | Deir Nbouh | Establish youth IT center | Youth | Nov. 09 | Dec.09 | Belgium | Progress to date: 80% |
|  |  |  |  |  |  |  | Spain |  |
| 11 | North | Kfarchalan | Build a municipal playground | Youth | Dec-08 | Sep-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  | Akkar Caza |
| 12 | North | Abboudieh | Rehabilitation of Primary health Care center | Health | Nov. 09 | Feb.10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 13 | North | Akkar | Establishment of a laboratory for soil & water testing & analysis at the LARI- Aabdeh station located in Akkar | Agriculture /LED | Nov. 09 | Dec.10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 14 | North | Akkar Atika | Establish Youth IT Center | Youth | Nov. 09 | Dec. 10 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 15 | North | Fneidek | Establish a public park for children | Social | Oct-09 | Dec-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 16 | North | Halba | Establish a public park for children | Social | Oct-09 | Dec-09 | Italy | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 17 | North | Halba | Rehabilitation of cultural center | Social | Nov. 09 | Dec. 09 | Belgium | Progress to date: 80% |
|  |  |  |  |  |  |  | Spain |  |
| 18 | North | Qobayat | Establish Youth IT center | Youth | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
|  | Tripoli Caza |
| 19 | North | Tebbeneh | Rehabilitation of Primary health Care center | Health | Nov 09 | Feb 10 | Belgium | Progress to date: 50% |
|  |  |  |  |  |  |  | Spain |  |
| 20 | North | Tripoli | Support the Youth vocational Training project | Youth | Nov. 09 | Dec. 09 | Italy | Progress to date: 50% |
|  |  |  |  |  |  |  | Italian DC |  |
|  |  |  |  |  |  |  | Spain |  |
| 21 | North | Tripoli | Establish Youth IT center | Youth | Nov. 09 | Dec. 09 | Belgium | Completed |
|  |  |  |  |  |  |  | Spain |  |
| 22 | North | to be defined | Establish Youth IT center | Youth | To be defined | Belgium | Delays incurred due to the upcoming municipal elections. |
|  |  |  |  |  |  | Spain |  |
|  | ART GOLD- Beirut Southern Suburbs, Status of 2009 projects |
|  | Baabda Caza |
| 23 | Mount Leb | Al Chiah, | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Progress to Date (%): 70% |
| 24 | Mount Leb | Hadath | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Progress to Date (%):70% |
| 25 | Mount Leb | Furn El Chebbak | Social intervention addressed to youth | Social | Jan-09 | Dec-09 | Spain | Progress to Date (%): 70% |
| 25.1 |  |  | Provision of equipment for the social programme in Al-Chiah - Al-Hadath - Furn Al Chebbak |  | 2009 | Spain | Completed |
| 25.2 | Mount Leb | Al-Chiah - Al-Hadath - Furn Al Chebbak | Capacity Building within the 3 projects "Social development addressed to youth" |  | 2009 | Tuscany Region -ARCI network | Completed |
|  |  |  |  |  |  | Spain |  |
| 26 | Mount Leb | Al Mreyjeh | Scholastic maps of Risk and Ressources | Social | Feb-08 | Oct-08 | Spain | Completed |
| 26.1 | Mount Leb | Al Mreyjeh | Capacity Building within the project "Scholastic maps of Risk and Ressources" | Social | Feb-09 | Oct-09 | Spain | Completed |
| 27 | Mount Leb | Haret Hreik | Pilot Programme for strengthening the Public Health Care Centers (PHCC) in Beirut Southern Suburbs | Health | Jul-08 | Dec-09 | Spain | Completed |
| 28 | Mount Leb | Haret Hreik Ghobeiri Burj Al Barajneh | Capacity Building within the "Pilot Programme for strengthening the Public Health Care Centers (PHCC)" |  |  |  | Spain | Progress to date (%): 60% |
|  |  |  |  |  |  |  | Arezzo Municipality- Tuscany region |  |
| 29 | Mount Leb | Haret Hreik Ghobeiri Burj Al Barajneh | Provision of equipment within the "Pilot Programme for strengthening the Public Health Care Centers (PHCC)" | Health |  |  | Spain | Progress to date (%):30% |