## 3 months
YOUTH MOBILIZATION AND DEVELOPMENT
IN BEIRUT AND ITS SUBURBS
Project Starting Date: April 1st 2008
Project End Date: March 31st 2009
Overall Objective: Promote social equity and local stakeholders’ empowerment through local employment recovery and livelihood opportunities projects in Beirut and its immediate suburbs.
ACTION PLAN - Quarter VIII (January- March 2010)
OBJECTIVE | ACTIVITIES | OUTPUT | IMPACT | INDICATORS | Quarter 8 |  |  | ACTIVITY COST | ACTIVITIES involved
[5 empty] | Jan | Feb | Mar
Objective 1: Enhance implementation capacities of local stakeholders (NGOs and CSOs) in identifying and providing direct services to recover sustainable livelihoods. Local stakeholders can then select and implement community projects for recovery of livelihood.
1.3 Preparation of the Training manual | 1. Printing the manual and distributing it to serve as a reliable guide for local NGOs , along with its related materials (pamphlets, CDs and posters) | 2000 copies of the manual printed | Local NGOs equipped with better internal governance skills to better manage development projects | Copies printed Copies distributed |  |  |  | 10356 | A3
Objective 2: Skills training for unemployed youth and supporting job creation through employment/ job search centre matching demand and supply. The centre will act as the enabling structure to create, enhance and develop skills and competencies of the youths.
2.2 Establish an employment creation center | 2. Hold a job fair for the youth, especially those still in schools and the undergraduates, to guide them on the different jobs available in the local labor market. It will also serve as a mean to promote the job creation center. | Brochures, pamphlets and ads, press conference | Fresh graduates with enhanced knowledge on what to choose as a career. Unemployed youth with better opportunities to get a job | Nb of brochures Nb of pamphlets Ads program press conference |  |  |  | 30000 | A4
3. Prepare for an advertising campaign to promote the center. Its objective is to advertise the unique features and added values of the centre
Objective 3: Rehabilitate 2 green areas of Beirut neighbourhoods with a focus on the poor and multi-cultural neighbourhoods after providing the youth with the proper training on how to enhance the socio-economic capacities for local communities
3.1 Undertake a field survey to select the appropriate neighborhoods | 4. Develop and detail the final and comprehensive design for the sites under rehabilitation | A well developed project responsive to the most urgent needs of the inhabitants A network of youth that is able to act and respond to the needs of their surrounding and the community | Increase awareness among local inhabitants on the urgency to redress their surrounding community to be a better place for living Inhabitants able to live and interact socially in a better sustainable environment | Type of work conducted Rehabilitation activities achieved Agreement with the municipality and concerned parties Youth engaged in the beautification process of the city |  |  |  | 159865 | A2
| 5. Undertake the infrastructure and rehabilitation work in the sites, under the supervision of the AUB/HF team. | Well rehabilitated areas enabling inhabitants to live in a better sustainable environment taking in consideration security and sanitary conditions
TOTAL ACTIVITY COSTS | [7 empty] | 200221
FIXED COSTS available in several activities:
Remuneration of the project team for 3 months including: Project Manager ($6,000)- Accountant ($3,000)- Procurement Officer ($3,000)- Administrative Assistant ($2,400)- Project Coordinator for Training Component ($4,500) and Project Coordinator for the Employment Creation Center ($4,500)- driver ($525) |  |  | 23925 |  |  |  |  | 23925 | A1
Rental and Maintenance : office rental ($3,000) |  |  | 3000 |  |  |  |  | 3000 | A1
Remuneration of the project team of the job creation center for 3 months |  |  | 32550 |  |  |  |  | 36750 | A4
Rental cost for the job creation center ($4,200 for 3 months) |  |  | 4200 | [5 empty] | A4
TOTAL PROJECT COSTS FOR Jan- Mar 2010 | [7 empty] | 263896