ANNEX 4.1

# Liberia Peace building Fund

# Quarterly Status Report of the Liberia Volunteers for Peace Programme

# As of 15 April 2010

| Recipient UN Organization: | UNDP | PBF Priority Area: | Priority Area 2: Critical Interventions to promote peace and resolve conflicts. |
| --- | --- | --- | --- |
| Implementing Partner(s): | Ministry of Youth and Sports, UNMIL, and Federation of Liberia Youth (FLY) |
| Project Number: | PBF/LBR/A-3 (PP/R2/A2/06) |
| Project Title: | Volunteers for Peace Programme |
| Total Approved Project Budget | $450,000.00 |
| Project Objective and Scope | To diffuse potential conflicts at community levels and significantly reduce the numbers of reported incidents of youth conflicts in the 15 counties To achieve a cascading impact of skills transfer on conflict diffusion and non-violent resolution strategies through training of trainers for youth in the local communities of the counties; To improve mutual trust, social cohesion and community relations among youth; To incorporate the Liberia Volunteers for Peace Programme (VPP) into the activities of the Ministry of Youth and Sports (MYS) and make it an integral part of the Ministry’s youth programmes throughout the country The project focuses on building peace and resolving conflicts amicably among youth in communities at the county levels |
| Funds Committed: | $450,000.00 | Percentage of Approved: | 100% |
| Funds Disbursed: | $300,000.00 | Percentage of Approved: | 67% |
| SC Approval Date: | 22 January 2009 |
| Expected Project Duration: | 18 Months | Forecast Final Date: | September 2010 | Delay (Months): | One Month |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| Awareness campaigns in the communities, schools, clinics, NGOs, government ministries, and the public to inform them on the peace building activities that the Youth Peace Ambassadors are implementing (Peace Campaigns in the communities, Campaigns against Gender Based Violence, ToT workshops on peace building and conflict resolution for the community youth, etc). | Awareness continues to be an integral part of the VPP activities in all the counties. The VPP activities that the Youth Peace Ambassadors are implementing in the counties are usually preceded by radio talk shows that by the volunteers in their respective counties of assignment. These are conducted in English and in the local dialects to provide opportunities for the public especially the youth to be informed and involved. At the project office level in Monrovia, we conducted radio programme with UNMIL radio that was aired country wide in January informing the nation of the programmes the project has lined up for the year. Other awareness efforts that we are currently engaged in are the production and distribution of posters on our ToT programme country wide. The project will also soon produce high quality plastic banners and T-Shirts for distribution in all counties as a way of further sensitizing the public on our forthcoming activities. | 80% |
| 30 Volunteers for Peace recruited based on a transparent and decentralized procedure and in accordance with an established selection criteria | 31 Volunteers (or Youth Peace Ambassadors) have successfully been recruited under the Liberia Volunteers for Peace Programme. Please refer to the September 2009 quarterly report for details. | 100% |
| One month induction training on Peace building and conflict resolution conducted for 30 selected youth volunteers | One-month induction training on Conflict Resolution and Peace Building was successfully conducted for the Youth Peace Ambassadors in September, 2009 that prepared them for their one year field assignment in the counties. Please refer to the September, 2009 quarterly report for details on the training content. | 100% |
| 30 Youth Volunteers for Peace deployed to counties of assignment (two in each county comprising of women and men); and 10% of youth in the counties trained by the volunteers on how they can diffuse potential conflicts | Following the successful deployment of 31 Youth Peace Ambassadors to the counties, they, in January 2010 began, in addition to other activities, the ToT workshops for the youth in the communities. By the end of January 750 youth were trained in all counties. Another 1,350 youth will receive the training on peace building and conflict resolution in May, June and July. It is important to note that at the completion of the January 2010 ToT the volunteers established a youth peace committee in each of the 4 districts they are engaging. Each committee has a membership of six (3 men and 3 women). The members of the peace committees work together with the peace ambassadors in the implementation of the project activities including the ToT workshops. The main objective behind this is to build the capacity of the members transfer the peace building and conflict resolution skills they learn from the ambassadors to other youth. This will ensure the creation of the cascading impact of skills transfer as envisaged in the project document. There are a total of 360 Youth Peace Committee members country wide. Other activities implemented by the Youth Peace Ambassadors include in February, March and April include Peace Campaigns, Conflict Analysis in the communities, Motorbike training, mobilization and registration of participants for the 2nd and 3rd ToT workshops. The peace campaign was aimed at directly engaging the youth in the local communities on the significance of peace building and getting the people to actively take part in designated activities that would help them appreciate the role of peace in social cohesion and national development. It is also a raining to the community youth on the relevance of peace to their personal and communal progress. The peace ambassadors worked closely with the Youth Peace Committee members and organized various kinds of activities. These included cleaning campaigns, drama, dialogue, sports, speeches, debate, and etc. The campaigns were categorised in to 6 thematic areas namely, Youth Unity, Environment, Land Issues, Peace Building, Education and Gender. Please see appendix A for the peace campaign activities per county and Appendix B for the photos. The conflict analysis was aimed at getting a better understanding of the conflict causes and related issues in the communities that the ambassadors are working in. This will help in developing and implementing programmes that are more focused. The motorbike training was conducted for all the ambassadors in March 2010. This was to allow them begin using the motorbikes that the project procured for their work in the counties. All ambassadors participated in the training and are duly licensed by the Ministry of Transport. The Youth Peace Ambassadors have completed the mobilization of ToT participants for the upcoming workshop in May. They are completing the mobilization for the 3rd ToT. Please see Appendix C for the list of participants for the May 2010 ToT in all counties. | 65% |
| Volunteer for Peace Programme integrated into the activities of the Ministry of Youth and Sports | The project team has completed all implementation documents that will help the Ministry of Youth and Sports integrate the VPP in its activities. It was agreed during a meeting in March 2010 with the Ministry that the programme the VPP, at the end of the pilot phase, will be incorporated into the NYVS programme. A meeting schedule for May 2010 will discuss the details. | 40% |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Youth in the communities are trained on how to diffuse potential conflicts themselves, and are able to build peace as a result of the enhancement of their capacity. | The VPP has so far trained 750 youth leaders throughout the country, and 1,350 will be trained in May, June and July 2010. It is expected that the trained youth leaders will further disseminate the skills to the other youths in the communities. | n/a |
| Integration of the Volunteer for Peace programme into the Ministry of Youth and Sports activities in the counties enhanced | Documents that will assist the Ministry of Youth and Sports to manage programme have already been completed. A meeting of stakeholders is scheduled for May 2010 to discuss the details of integration. The ministry has however, during a meeting held in March 2010 indicated that it will incorporate VPP into the NYVS programme, and run both as one integral programme. | n/a |

Qualitative achievements against expected results:

The VPP project team is beginning to see a lot of qualitative improvements first in the way the youth peace ambassadors implement the project activities, and second in the communities’ response to the VPP activities. The ambassadors’ ability to prepare proposals and reports for their ToT workshops and other activities, and mobilize people for the activities is highly improved. The and the youth, especially the members of the Youth Peace Committees are highly involved in the VPP activities, and this is gradually scaling up the significance that youth are attaching to peace and its impact on social cohesion and nation building.

challenges (If necessary):

Internet access to facilitate the work of the peace ambassadors. The programme is experiencing logistical problems that are usually causing implementation delays. For example, the mobilization of participants for ToT workshops in the counties takes time because of the time period to conduct the appropriate protocols (going to the communities, calling for a meeting, discussing on the appropriate candidates, agreeing with the community people on who should participate, etc). These are important consultative processes that must take place in order to ensure a peaceful and healthy mobilization of participants that is sanctioned by the community. Distribution of project materials and other resources (e.g. food items for workshops) takes time and causes delays. Mobility. The volunteers up to March 2010 were using transport allowance to move around in the counties. During that period their mobility was restricted. This problem has now been solved as they have motorbikes and are given motorbike gasoline and maintenance allowance for their movements.

Appendices

Appendix A

List of Peace Campaign Activities in different districts and counties

Please See PAGE: 6

Appendix B

Peace Campaign photos

Please See Page: 7-11

Appendix C

List of participants for the upcoming ToT in May 2010 for All Counties

Please See Page 12-26

| Clean-up campaign in Bomi | Clean-up campaign in Bomi |
| --- | --- |
| Clean-up campaign in Bomi | Clean-up campaign in Bomi |
| During sports activity in Bong | During sports activity in Bong |
| During sports activity in Bong | During sports activity in Bong |

| During the preparation of March in Bong | Parade in Bong |
| --- | --- |
| Parade in Bong | Parade in Bong |
| Parade in Bong | Parade in Bong |
| After parade in Bong | Talk after parade in Bong |
| Dialogue between stakeholders and youth in Gbagpolu | Dialogue between stakeholders and youth in Gbagpolu |
| Dialogue between stakeholders and youth in Gbagpolu | Dialogue between stakeholders and youth in Gbagpolu |
| Dialogue between stakeholders and youth in Gbagpolu | Dialogue between stakeholders and youth in Gbagpolu |
| Dialogue between stakeholders and youth in Gbagpolu | Dialogue between stakeholders and youth in Gbagpolu |
| Picturecard Show in Grand Cape Mount | Picturecard Show in Grand Cape Mount |
| Picturecard Show in Grand Cape Mount | Drama in Grand Cape Mount |
| Drama in Grand Cape Mount | Drama in Grand Cape Mount |
| March in Margibi | March in Margibi |

| March in Margibi | March in Margibi |
| --- | --- |
| March in Margibi | March in Margibi |
| Talk after march in Margibi | Talk after march in Margibi |
| Play after march in Margibi | Play after march in Margibi |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Bomi County |
| No. | Name | Community | Gender | Age |
| 1 | George K. Karnley | Klay | M | 31 |
| 2 | Lusine Z. Freeman | Klay | M | 29 |
| 3 | Jarah Karnley | Klay | F | 20 |
| 4 | Sarah Karnley | Klay | F | 30 |
| 5 | Junior Coleman | Klay | M | 31 |
| 6 | Ruth Varney | Klay | F | 19 |
| 7 | Solomon M. Ballah | Klay | M | 26 |
| 8 | Moses Gbelly | Klay | M | 18 |
| 9 | Siatta Boimah | Klay | F | 32 |
| 10 | Marthaline Rromaa | Klay | F | 20 |
| 11 | Agatha Kromah | Klay | F | 20 |
| 12 | Oretha Richard | Klay | F | 21 |
| 13 | Martha Karnley | Klay | F | 24 |
| 14 | Bendu Taylor | Klay | F | 26 |
| 15 | Kaiva Sirleaf | Klay | M | 22 |
| 16 | Benzonic Coleman | Klay | M | 24 |
| 17 | Folley Boimah | Klay | M | 21 |
| 18 | Joseph B. Varney | Klay | M | 20 |
| 19 | Boakai V Momo | Kagacia | M | 22 |
| 20 | Lee Gray | Klay | M | 21 |
| 21 | W. Francis Ronah | Klay | M | 28 |
| 22 | G. Samuel Walton | Klay | M | 29 |
| 23 | Hawa Sirleaf | Klay | F | 31 |
| 24 | Alfred B.S.Carter | Klay | M | 27 |
| 25 | Junior Sirleaf | Klay | M | 34 |
| 26 | David Gbelly | Klay | M | 32 |
| 27 | Gotomo Daniel | Klay | M | 32 |
| 28 | J. Clarance Daniel | Klay | M | 32 |
| 29 | Lanssana Quaye | Malanah | M | 29 |
| 30 | Varney Samukah | Malanah | M | 34 |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Bong County |
| No. | Name | District | Gender | Age |
| 1 | T. miller Bondo | Salala | M |  |
| 2 | Bendu L. Bonar | Salala | F |  |
| 3 | Cecelia M Feiller | Salala | F |  |
| 4 | Nathern O Yah | Salala | M |  |
| 5 | Prince Kpainkpaz | Salala | M |  |
| 6 | Annie Pinneers | Salala | F |  |
| 7 | Alexander Dayway | Salala | M |  |
| 8 | Kamah Kollie | Salala | F |  |
| 9 | Matha Kolleh | Salala | F |  |
| 10 | Stephen A S Flomo | Salala | M |  |
| 11 | Yalafai K Thomas | Salala | F |  |
| 12 | J mason Sackie | Salala | M |  |
| 13 | Thoneo Harris | Salala | M |  |
| 14 | Winnie Thaomas | Salala | F |  |
| 15 | Anthony Gwee Jr. | Salala | M |  |
| 16 | Maisse T Marshall | Salala | M |  |
| 17 | Maxwell S Mulbah | Salala | M |  |
| 18 | Theophilus T Natee | Salala | M |  |
| 19 | Luwis T Sawyer | Salala | M |  |
| 20 | Jeromie K Thomas | Salala | M |  |
| 21 | Aliel T Konneh | Salala | M |  |
| 22 | Jerome D Welwolie | Salala | M |  |
| 23 | Emmanuel S K Lotern | Salala | M |  |
| 24 | Philip Perkins | Salala | M |  |
| 25 | Tete Marshall | Salala | F |  |
| 26 | J Henry Korgueh Jr | Salala | M |  |
| 27 | J Adolphus S Nyemah | Salala | M |  |
| 28 | Annie L Minor | Salala | F |  |
| 29 | Miatta T Francy | Salala | F |  |
| 30 | J Lincoln L Singbeh | Salala | M |  |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Gbarpolu County |
| No. | Name | District | Gender | Age |
| 1 | NELSON SINGBAY | MARLAKELLEH | M | 26 |
| 2 | ANTHONY SINGBAY | MARLAKELLEH | M | 29 |
| 3 | MULBAH KERKULA | MARLAKELLEH | M | 19 |
| 4 | SAMSON SUMO | WHIAMA | M | 26 |
| 5 | REMEMBER SUMO | GONOMEA | F | 20 |
| 6 | DAVID MULBAH | MARLAKELLEH | M | 29 |
| 7 | OBEREED MULBAH | MARLAKELLEH | M | 23 |
| 8 | BETTY SINGBAY | MARLAKELLEH | F | 19 |
| 9 | PAA GOTOLO | MARLAKELLEH | F | 21 |
| 10 | ANNIE SIMGBAY | MARLAKELLEH | F | 24 |
| 11 | MARK HOLDER | MARLAKELLEH | M | 34 |
| 12 | LENDA HOLDER | MARLAKELLEH | F | 25 |
| 13 | WATTA SUMO | MARLAKELLEH | F | 33 |
| 14 | MOSES FULLER | MARLAKELLEH | M | 23 |
| 15 | ALFRED ZABO | MARLAKELLEH | M | 25 |
| 16 | GEORGE KERKULA | MARLAKELLEH | M | 29 |
| 17 | ABRAHAM KOLLIE | MARLAKELLEH | M | 24 |
| 18 | BETTY FULLER | MARLAKELLEH | F | 19 |
| 19 | HARRIS TOKPA | MARLAKELLEH | M | 32 |
| 20 | HAWA CRAWN | WHIAMEA | F | 23 |
| 21 | EVELINE BALLAH | BELEGPKAYAMU | F | 24 |
| 22 | YASSAH FORD | MARLAKELLEH | F | 22 |
| 23 | MORGAN GAYFLOR | MARLAKELLEH | M | 24 |
| 24 | SARMAH ZIMAH | MARLAKELLEH | F | 23 |
| 25 | ANNIE FLOMO | MARLAKELLEH | F | 18 |
| 26 | NALTON HOMMAY | MARLAKELLEH | M | 27 |
| 27 | MAIME FLOMO | MARLAKELLEH | F | 18 |
| 28 | GOBEAH MULBAH | GONOMEA | F | 20 |
| 29 | JENNEH MULBAH | GONOMEA | F | 19 |
| 30 | SATTA KENNEDY | MARLAKELLEH | F | 22 |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Grand Bassa County |
| No. | Name | District | Gender | Age |
| 1 | Junior Delbeh | Compound #3 | M | 26 |
| 2 | Samuel Kota | Compound #3 | M | 27 |
| 3 | Issaac Roberts | Compound #3 | M | 25 |
| 4 | C;aremce Carter | Compound #3 | M | 27 |
| 5 | Olesomon Ben | Compound #3 | M | 28 |
| 6 | Fidel Tukue | Compound #3 | M | 26 |
| 7 | Jehu Chea | Compound #3 | M | 27 |
| 8 | Darlington Siaway | Compound #3 | M | 29 |
| 9 | Harris P Sumo | Compound #3 | M | 28 |
| 10 | Edwin Weljay | Compound #3 | M | 27 |
| 11 | Ruth Joseph | Compound #3 | F | 24 |
| 12 | Oliver O Yeaney | Compound #3 Lac | F | 26 |
| 13 | Musa Divid | Compound #3 | F | 25 |
| 14 | Josephine Ben | Compound #3 | F | 26 |
| 15 | Victoral S Josaph | Compound #3 Lac | F | 24 |
| 16 | Janet S Tamba | Compound #3 | M | 26 |
| 17 | Vivian Koogaor | Compound #3 | F | 25 |
| 18 | Onesimus Henries | Compound #3 | M | 28 |
| 19 | Tetee Nyounbol | Compound #3 | F | 25 |
| 20 | Prince Moore | Compound #3 | M | 27 |
| 21 | Cynthia Johnson | Compound #3 | F | 24 |
| 22 | Lengston Zangar | Compound #3 | M | 27 |
| 23 | Record Kweh | Compound #3 | F | 24 |
| 24 | Marry Kollie | Compound #3 | F | 28 |
| 25 | Venus Mulbah | Compound #3 | F | 23 |
| 26 | Emmanuel James | Barseegian Town | M | 22 |
| 27 | Daniel Peters | Barseegian Town | M | 22 |
| 28 | Harris Joe | Ceedyah Town | M | 33 |
| 29 | Vera Nathan | Ceedyah Town | F | 28 |
| 30 | Poemaheedee Doe | Ceedyah Town | M | 24 |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Grand Cape Mount County |
| No. | Name | District | Gender | Age |
| 1 | Toweh Shaerman | Bendu | M |  |
| 2 | Musu Kaohon | Bendu | F |  |
| 3 | Watta Kiabolu | Bendu | F |  |
| 4 | Tom K Sherman | Bendu | M |  |
| 5 | Miatta Kiadii | Bendu | F |  |
| 6 | A-Daoda Sherman | Bendu | M |  |
| 7 | Jebbeh Kallon | Bendu | F |  |
| 8 | Princess Gray | Bendu | F |  |
| 9 | Zoe G Kiahon | Mambo | F |  |
| 10 | Anna M Ben | Bendu | F |  |
| 11 | Felecia Kiakidole | Bendu | F |  |
| 12 | Veronica Kandokai | Bendu | F |  |
| 13 | Vannay Tarweh | Bendu | M |  |
| 14 | Boimah P Kiahan | Bendu | M |  |
| 15 | Maima Gray | Bendu | F |  |
| 16 | Lansana Freeman | Siema | M |  |
| 17 | Boima Kromah | Pursekoma | M |  |
| 18 | Famata Kamara | Pursekoma | F |  |
| 19 | Sando Harrey | Jingboh | M |  |
| 20 | Musu Krtu | Bendu | F |  |
| 21 | A Mambu Degboe | Bulu | M |  |
| 22 | Junior Brown | Bendu | M |  |
| 23 | Lamic Brown | Bendu | M |  |
| 24 | Linda L Sherman | Bendu | F |  |
| 25 | Watta Dukuly | Bendu | F |  |
| 26 | Jenii T Kiahon | Bendu | F |  |
| 27 | A Ben Fahnbulleh | Bendu | M |  |
| 28 | Abraham Sheriff | Bendu | M |  |
| 29 | Boima G Kahon | Bendu | M |  |
| 30 | Massa J Kiahon | Bendu | F |  |

| Liberia Volunteers for Peace Programme (VPP) List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Grand Gedeh County |
| --- |
| No. | Name | District | Gender | Age |
| 1 | J. Stanley W Karpeh | Putu | M |  |
| 2 | A Philip B Kamah Jr. | Putu | M |  |
| 3 | Felecia Roberts | Putu | F |  |
| 4 | Agatha Jolo | Putu | F |  |
| 5 | Rebecca Wallo | Putu | F |  |
| 6 | James Meanyeah | Putu | M |  |
| 7 | Cecelia Rue | Putu | F |  |
| 8 | Ebalyn Shaka | Putu | F |  |
| 9 | Reta Kamah | Putu | F |  |
| 10 | Maime Gee | Putu | F |  |
| 11 | Emmmanuel Williams | Putu | M |  |
| 12 | Annie Williams | Putu | F |  |
| 13 | Mary Blay | Putu | F |  |
| 14 | Maye Blayee | Putu | F |  |
| 15 | Jemior Jolo | Putu | M |  |
| 16 | Alfred Dennis | Putu | M |  |
| 17 | Nathaniel Pasibo | Putu | M |  |
| 18 | Klarty Tweh | Putu | M |  |
| 19 | Philip Barpee | Putu | M |  |
| 20 | Junior Flahn | Putu | M |  |
| 21 | Lovester Darue | Jawudee | F |  |
| 22 | Anthony Rue | Jawudee | M |  |
| 23 | Sam Jarlo | Pennu Ken | M |  |
| 24 | Anthony Jargbah | Pennu Ken | M |  |
| 25 | Sampson Gbalo | Pennu Ken | M |  |
| 26 | Junior Blayee | John Davis Town | M |  |
| 27 | Ssaydee Jelleh | John Davis Town | M |  |
| 28 | Albert Flahn | Pennu ken | M |  |
| 29 | D Jargbah | CVI | F |  |
| 30 | Lydia Klallo | Jawudee | F |  |

| Liberia Volunteers for Peace Programme (VPP) List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Grand Kru County |
| --- |
| No. | Name | District | Gender | Age |
| 1 | Jasper P Nah | Gbolebo | M | 28 |
| 2 | Peter n Dulu | Gbolebo | M | 31 |
| 3 | Lutricia S Odarbeh | Gbolebo | F | 20 |
| 4 | Rochel D Weleh | Gbolebo | F | 19 |
| 5 | Amos D Tuweh | Gbolebo | M | 21 |
| 6 | Paul K Gigba | Serroken | M | 19 |
| 7 | Koti S Tarbeh | Wutuken | M | 32 |
| 8 | Jeremiah Weah T | Wutuken | M | 30 |
| 9 | Clarence K Tarbeh | Wutuken | M | 22 |
| 10 | Pertience m Masah | Wutuken | F | 17 |
| 11 | Felicia D Toe | Serroken | F | 30 |
| 12 | Willie T Sebo | Newaken | M | 31 |
| 13 | Josiah N Blayon Jr | Newaken | M | 24 |
| 14 | Gatta G Wieh | Newaken | F | 22 |
| 15 | Martha C Davis | Dougbo | F | 14 |
| 16 | Phoelia K Nyemah | Behwan | F | 21 |
| 17 | Alexander G Teleh | Behwan | M | 30 |
| 18 | Peter K Doblah | Behwan | M | 30 |
| 19 | K Wilmont Nimely | Behwan | M | 22 |
| 20 | B marcus Dioh II | Behwan | M | 25 |
| 21 | Moses Q Wreh | Dougbo | M | 32 |
| 22 | Elizabeth T Davies | Dougbo | F | 31 |
| 23 | Josephine P Wreh | Dougbo | F | 14 |
| 24 | Moses N Dioh | Gbanken | M | 33 |
| 25 | John H Nyema | Gbanken | M | 30 |
| 26 | Mercy B Dioh | Newaken | F | 24 |
| 27 | Theophilus H Davis | Newaken | M | 23 |
| 28 | Mercy K Toe | Gblebo | F | 18 |
| 29 | Marcus Q Polley | Sorroken | M | 30 |
| 30 | Loretta k Nyeka | Sorroken | F | 22 |

| Liberia Volunteers for Peace Programme (VPP) List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Lofa County |
| --- |
| No. | Name | District | Gender | Age |
| 1 | Andrew Fallah | AG Compound | M |  |
| 2 | B Njamilah Saa Bornguoi | AG Compound | M |  |
| 3 | Hanna Jimmy | AG Compound | F |  |
| 4 | Morries N Varnie | AG Compound | M |  |
| 5 | Rebecca Fallah | AG Compound | F |  |
| 6 | Thamas F Bundor | AG Compound | M |  |
| 7 | Henry Bepual | AG Compound | M |  |
| 8 | Elizabeth Daramy | AG Compound | F |  |
| 9 | Felicia K Fayie | AG Compound | F |  |
| 10 | Marris Kollie | AG Compound | M |  |
| 11 | Elijah T Borbor | AG Compound | M |  |
| 12 | Christiane Saah | AG Compound | F |  |
| 13 | Prince M Boka | AG Compound | M |  |
| 14 | Elher Konon | AG Compound | F |  |
| 15 | Fatumata kemon | AG Compound | F |  |
| 16 | Joel Farmah | AG Compound | M |  |
| 17 | K Palloe F Sandukie | AG Compound | M |  |
| 18 | Thomas Fallah | AG Compound | M |  |
| 19 | Kumba Gbamah | AG Compound | F |  |
| 20 | David Bor Bor | AG Compound | M |  |
| 21 | Esther Hallie | AG Compound | F |  |
| 22 | Ellen Tumbay | AG Compound | F |  |
| 23 | Gabriel Saa | AG Compound | M |  |
| 24 | Musu Thomas | AG Compound | F |  |
| 25 | Siah Guissi | AG Compound | F |  |
| 26 | Charles Robert | AG Compound | M |  |
| 27 | Kefa Donun | AG Compound | M |  |
| 28 | Laurence Tamba | AG Compound | M |  |
| 29 | Rufus Tombay | AG Compound | M |  |
| 30 | Rita Bonkun | AG Compound | F |  |

| Liberia Volunteers for Peace Programme (VPP) List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Margibi County |
| --- |
| No. | Name | District | Gender | Age |
| 1 | Osei-tutu Gdasakollie | Weala | M | 27 |
| 2 | C. Yornah Gulley | Massakollie town | F | 18 |
| 3 | Jerry Sirleaf | Nyanaka | M | 33 |
| 4 | Sampson Marzar | Nyanaka | M | 32 |
| 5 | William Kerkulah | Nyanaka | M | 22 |
| 6 | Joseph J. Harmon | Nyanaka | M | 21 |
| 7 | Billion t. Boiman | Weala | M | 21 |
| 8 | Angeline cooper | Weala | F | 21 |
| 9 | Manie Dahn | Nyanaka | F | 27 |
| 10 | Princess peter | Weala | F | 22 |
| 11 | Blessing Tokpah | Nyanaka | F | 24 |
| 12 | Junior Vah | Weala | M | 22 |
| 13 | Otis Mepeh | Nyanaka | M | 27 |
| 14 | Bendu Foboi | Weala | F | 20 |
| 15 | Marwolo B. Kenneh | Weala | M | 26 |
| 16 | Tinapu Wormoh | Nyanaka | F | 28 |
| 17 | Blessing Morris | Nyanaka | F | 25 |
| 18 | Sam Eddie | Nyanaka | M | 18 |
| 19 | Florence Flomo | Weala | F | 19 |
| 20 | Juweala M.Gibson | Nyanaka | F | 22 |
| 21 | Ruth Sackie | Nyanaka | F | 18 |
| 22 | Manah Kandakai | Weala | F | 27 |
| 23 | Ishamel Koroma | Weala | M | 19 |
| 24 | Harrison Pokai Jr. | Massakollie town | M | 25 |
| 25 | Emmanuel Gibson | Weala | M | 27 |
| 26 | Robert Otto | Weala | M | 32 |
| 27 | Annie Tehmeh | Weala | F | 21 |
| 28 | Maryahn Kpangbai | Weala | F | 24 |
| 29 | Fatu North | Weala | F | 19 |
| 30 | Oretha Dewalt | Weala | F | 30 |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Maryland County |
| No. | Name | District | Gender | Age |
| 1 | J Gbarjulue Toe | Barrobo | M | 35 |
| 2 | Assey G W Weah | Barrobo | M | 31 |
| 3 | Sarah Toe | Barrobo | F | 25 |
| 4 | Patience Saweleh | Barrobo | F | 21 |
| 5 | Francess Clark | Barrobo | F | 20 |
| 6 | Joseph Davis | Karluway | M | 35 |
| 7 | Jerry Quire | Karluway | M | 34 |
| 8 | George Jugba Jr | Karluway | M | 31 |
| 9 | Estter Toe | Karluway | F | 30 |
| 10 | Lucy Brown | Karluway | F | 29 |
| 11 | Sammuel S Hoto | Sodoken | M | 32 |
| 12 | Chris Mulbah | Sodoken | M | 31 |
| 13 | Benedict Wesseh | Sodoken | M | 33 |
| 14 | Derrick D Duleh | Sodoken | M | 29 |
| 15 | Alphanso Stephen | Sodoken | M | 22 |
| 16 | Sam J NS Tuoh | Sodoken | M | 25 |
| 17 | Oliver PK Griffichs | Sodoken | M | 27 |
| 18 | Emmanuel Freeman | Sodoken | M | 28 |
| 19 | Mary W Mooney | Sodoken | F | 23 |
| 20 | Marcy Williams | Sodoken | F | 25 |
| 21 | Mamie Williams | Sodoken | F | 30 |
| 22 | Eliza Williams | Sodoken | F | 22 |
| 23 | Patience Sharmos | Sodoken | F | 20 |
| 24 | Cerena Toe | Sodoken | F | 22 |
| 25 | Beta Geply | Sodoken | F | 25 |
| 26 | Mary Sieh | Sodoken | F | 28 |
| 27 | Veronica Keeh | Sodoken | F | 27 |
| 28 | Teleson Felle | Sodoken | F | 26 |
| 29 | Emanuel Mensah | Sodoken | M | 21 |
| 30 | Nathaniel Wesley | Sodoken | M | 27 |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Montserrado County |
| No. | Name | Community | Gender | Age |
| 1 | Jerry D. Jubah | Nyehn | M |  |
| 2 | Francis Tengbeh | Nyehn | M |  |
| 3 | Larmie Momo | Goyah Town | M |  |
| 4 | Salome Seigh | Goba Town | F |  |
| 5 | Oliver Momo | Koon Town | M |  |
| 6 | Musu Tenabeh | Nyehn | F |  |
| 7 | Edwin Green | Nyehn | M |  |
| 8 | Quita Sluteh | Nyehn | F |  |
| 9 | Tennch Bondo | Nyehn | F |  |
| 10 | Jartu Bah | Goba Town | F |  |
| 11 | Naomi Sanpers | Nyehn | F |  |
| 12 | Sylvester Snow | Karto Town | M |  |
| 13 | Mary Karmo | Green Town | F |  |
| 14 | Agnes Holder | Nyehn | F |  |
| 15 | Kegeh Kolie | Nyehn | F |  |
| 16 | Ebeneler Simgbeh | Kpee town | M |  |
| 17 | Ramuna Moore | Zolupaye | F |  |
| 18 | Phebe Carmo | Zolupaye | F |  |
| 19 | Bendu Gargar | Pleemu | F |  |
| 20 | Cathrine Paul | Nyehn | F |  |
| 21 | Tenneh Gooding | Koon Town | F |  |
| 22 | Jonah Tokpah | Willie Town | M |  |
| 23 | Oretha Kamara | Molly Town | F |  |
| 24 | Patrick Saysay | Nyehn | M |  |
| 25 | Amos D. Sackie | Nyehn | M |  |
| 26 | Samuel Kollie | Gbino Town | M |  |
| 27 | Mentonor Wie | Sackie Town | M |  |
| 28 | Alfred Totaye | Kpeek Town | M |  |
| 29 | Geroge Washington | Nyehn | M |  |
| 30 | Emmanuel Binda | Nyehn | M |  |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Nimba County |
| No. | Name | District | Gender | Age |
| 1 | Alphonso Myers | Tappita | M |  |
| 2 | Victor M Playeah, Jr | Tappita | M |  |
| 3 | Marlinetha Kartoe | Tappita | F |  |
| 4 | Cestoe Toweh | Tappita | M |  |
| 5 | Ellena Johnson | Tappita | F |  |
| 6 | Neason Bantu | Zoutuo | F |  |
| 7 | Sam D Wehyee | Tappita | M |  |
| 8 | Ebenezer Strother | Tappita | M |  |
| 9 | Nula Musa | Tappita | F |  |
| 10 | Diana Karzon | Kwepea | F |  |
| 11 | Eddie Gaye | Dialah | M |  |
| 12 | Patience Yarmie | Tappita | F |  |
| 13 | Ishameal Bayorga | Tappita | M |  |
| 14 | Christaina Barleah | Tappita | F |  |
| 15 | Loise Beahn | Tappita | F |  |
| 16 | Julee Chie | Tappita | F |  |
| 17 | Jerry Sonkarlay | Ziah | M |  |
| 18 | Richard Wonblaker | Tappita | M |  |
| 19 | Jameson Zealu | Tappita | M |  |
| 20 | Lydia Davis | Tappita | F |  |
| 21 | BM Kesseley | Tappita | M |  |
| 22 | Lincoln Jackson | Tappita | M |  |
| 23 | Stanley Vonley | Tappita | M |  |
| 24 | Wonseh King | Tappita | F |  |
| 25 | Pricess Kruah | Tappita | F |  |
| 26 | Ellijah Lormie | Tappita | M |  |
| 27 | Hansan Carr | Tappita | M |  |
| 28 | Cecelia Dezuo | Tappita | F |  |
| 29 | Amos Sankalay | Camp#1 | M |  |
| 30 | Oldpa Sando | Tappita | M |  |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, River Cess County |
| No. | Name | District | Gender | Age |
| 1 | Victor Mamudee | Timbo Beach | M |  |
| 2 | Patience James | Timbo Beach | F |  |
| 3 | Dixon Tarflah | Timbo Beach | M |  |
| 4 | Alice Nagbe | Timbo Beach | F |  |
| 5 | Mary Weagba | Timbo Beach | F |  |
| 6 | Prosiah Debah | Timbo Beach | F |  |
| 7 | Paul Zeekor | Timbo Beach | M |  |
| 8 | Jesse Bordy | Timbo Beach | M |  |
| 9 | James B Edmards Jr | Timbo Beach | M |  |
| 10 | Ruth Harris | Timbo Beach | F |  |
| 11 | Sarah Kartogn | Timbo Beach | F |  |
| 12 | A Roosevelt Zarnie | Timbo Beach | M |  |
| 13 | Frankey David | Timbo Beach | M |  |
| 14 | Daniel Cephus | Timbo Beach | M |  |
| 15 | Bob Zamweh | Timbo Beach | M |  |
| 16 | Maybeth Faunfaun | Timbo Beach | F |  |
| 17 | Samuel Gbordoe | Timbo Beach | M |  |
| 18 | Joe Sammie | Timbo Beach | M |  |
| 19 | Amos Bonulein | Timbo Beach | M |  |
| 20 | Matthew B Harris | Timbo Beach | M |  |
| 21 | Joe Watson | Palm Bush | M |  |
| 22 | Nancy Miller | Palm Bush | M |  |
| 23 | Helena Wesseh | Palm Bush | F |  |
| 24 | Cyrus Quiateh | Palm Bush | M |  |
| 25 | James Cole | Palm Bush | M |  |
| 26 | Angie Reeves | Palm Bush | F |  |
| 27 | Chinesegirl Marzar | Palm Bush | F |  |
| 28 | Carmonie Morris | Little Liberia | M |  |
| 29 | Titus Harris | Little Liberia | M |  |
| 30 | Makey James | Yarpar Town | F |  |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, River Gee County |
| No. | Name | District | Gender | Age |
| 1 | Kulu Jarba | Jaytoken | M |  |
| 2 | Doris Toe | Jaytoken | F |  |
| 3 | Dweh Sawkan | Jaytoken | M |  |
| 4 | Paul Komothy | Jaytoken | M |  |
| 5 | Stephen Jarwee | Jaytoken | M |  |
| 6 | Beatrice Wesay | Jaytoken | F |  |
| 7 | Alfred Donmo | Jaytoken | M |  |
| 8 | Ida Wesseh | Jaytoken | F |  |
| 9 | Joe Barwee | Jaytoken | M |  |
| 10 | Lawrence Kambo | Jaytoken | M |  |
| 11 | Sophia Toe | Jaytoken | F |  |
| 12 | Aaron Massah | Jaytoken | M |  |
| 13 | Joseph Darpay | Jaytoken | M |  |
| 14 | Sabastine Blayee | Jaytoken | M |  |
| 15 | J Blayee Toe | Jaytoken | M |  |
| 16 | Joe Pyne | Jalipo | M |  |
| 17 | Alvan Daniels | Juwehpo | M |  |
| 18 | Geeba Wesseh | Bortriken | F |  |
| 19 | Ma Swen | Kurltown | F |  |
| 20 | Alice Frank | Jayproken | F |  |
| 21 | Francy Nyepan | Gbawreken | F |  |
| 22 | Sunnoh Wesseh | Chalitiken | M |  |
| 23 | James Nyepan | Saiken | M |  |
| 24 | T Willayor Sarkon | Pennoken | M |  |
| 25 | Victoria Nyan | Konken | F |  |
| 26 | Hazel Donah | Jaytoken | F |  |
| 27 | T Mush Kpaward | Jaytoken | F |  |
| 28 | Alice Tarsley | Jaytoken | F |  |
| 29 | Dorius Chea | Jaytoken | M |  |
| 30 | Vester Nyepan | Jaytoken | F |  |

| Liberia Volunteers for Peace Programme (VPP) |
| --- |
| List of Participants for the May 2010 ToT on Peace Building and Conflict Resolution, Sinoe Gee County |
| No. | Name | District | Gender | Age |
| 1 | Vasco F. Kambleh | Juazon | M | 35 |
| 2 | Levater Slewno | Bullibokree | M | 33 |
| 3 | Fedrick Koffa | Bullibokree | M | 30 |
| 4 | Myers Gayee | Karmeh town | M | 31 |
| 5 | Kaffa Shagbeh | Karmeh town | M | 35 |
| 6 | Justin Dweh | WCA | F | 29 |
| 7 | B Sunday Tarwho | Wedjah | M | 30 |
| 8 | Henry Cherwlue | Wedjah | M | 34 |
| 9 | Lhancie Jelleh | Wedjah | M | 25 |
| 10 | Jashua Fumah | Wedjah | M | 28 |
| 11 | George Tahhah | Wedjah | M | 32 |
| 12 | Synena Weah | Billibokree | M | 29 |
| 13 | Baby Girl Toybor | Billibokree | F | 27 |
| 14 | Lettee Kambleh | Karmeh’s town | M | 34 |
| 15 | Decontee Noah | Billibokree | M | 30 |
| 16 | Augustus Browne | Billibokree | M | 32 |
| 17 | Samuka O Bility | Billibokree | M | 34 |
| 18 | Browne Tugbah | Billibokree | F | 31 |
| 19 | Caine Tarwho | Wedjah | F | 28 |
| 20 | Emmanuel Kweteh | Karmeh’s town | F | 30 |
| 21 | Thomas Norman | Billibokree | F | 29 |
| 22 | Sargbeh Quiah | Billibokree | F | 30 |
| 23 | George Shagbeh | Karmeh’s town | M | 32 |
| 24 | Pomeo Kai | Karmeh’s town | M | 33 |
| 25 | Johnethan Karjleh | Billibokree | M | 36 |
| 26 | Gabriel Seoh | Karmeh’s town | M | 30 |
| 27 | Hilary Gborlue | Karmeh’s town | M | 31 |
| 28 | Patricia Ballay | Karmeh’s town | M | 32 |
| 29 | Victor Gberlue | Karmeh’s town | M | 33 |
| 30 | Archa Winshar | Karmeh’s town | M | 30 |