- Liberia Peacebuilding Fund

- QUARTERLY STATUS UPDATE

- as of 30 September 2009

| Recipient UN Organization: | UNDP |  | PBF Priority Area: |  | Priority Area 2: Critical Interventions to promote peace and resolve conflicts |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | Landmine Action (LMA), Ministry of Agriculture (MOA), Liberia Rubber Development Authority (LRDA), Central Agricultural Research Institute (CARI) |  |  |  |  |  |  |
| Project Number: | PBF/LBR/D-3 (00063760) |  |  |  |  |  |  |
| Project Title: | Tumutu Agricultural Training Programme |  |  |  |  |  |  |
| Project Objective & Scope | - To rehabilitate and reintegrate DDRR‐excluded ex‐combatants from areas of illegal natural resource extraction in order to reduce the possibilities of armed violence in Liberia - To reduce the incidence and impact of insecurity resulting from the presence of formed groups of ex‐combatants and the possibility of armed violence and illegal control of natural resources, through provision of agricultural skills training for ex‐combatants and supervised integration/reintegration into communities |  |  |  |  |  |  |
| Total Approved Project Budget | $1,123,500 |  |  |  |  |  |  |
| Funds Committed: | $1,123,500 |  | Percentage of Approved: |  | 100% |  |  |
| Funds Disbursed: | $676,433.08 |  | Percentage of Approved: |  | 60% |  |  |
| SC Approval Date: | 25 Sept 2008 |  |  |  |  |  |  |
| Expected Project Duration: | 18 months | Forecast Final Date: |  | April 2010 |  | Delay (Months): | n/a |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| Reduction of ex-combatant Populations participating in illegal natural resource extraction | 400 DDRR excluded ex-combatants per course removed from target natural resource areas to training site | completed |
| An increase in stability and legal economic activity in areas of natural resource extraction | Reduction in incidences of ex‐combatant related crime | completed |
|  | Increase in legal natural resource related activity | ongoing |
|  | Increase in normal, stable functioning of natural resource concession and areas | n/aongoing |
| Trainees are thoroughly trained in MOA approved agricultural techniques | Trainees absorb training and are able to implement taught techniques | n/aongooing |
| Trainees are economically and socially integrated/reintegrated employment | After graduation from TATP, trainees are: ‐ living peacefully in communities ‐ earning a living wage ‐ are contributing to the agricultural and social life of their receiving communities ‐ trainees are removed from the cycle of violence by their own volition and participation in a meaningful and peaceful life | ongoing |
| Increase in agricultural capacity in trainee‐ receiving communities/ sites of employment | Evidence of effective upturn of agricultural production and market activity in trainee receiving communities in the TATP trained sectors of: ‐ rubber ‐ rice ‐ vegetables ‐ animal husbandry ‐ tree crops | ongoingn/a |
| Increase in MOA capacity to plan and manage agricultural training | Improved participation, planning and decision making in project activities | ongoingn/a |
| TATP a self‐sustaining, MOA‐ funded national agricultural training centre | - MOA staff and fund the Centre - TATP food self sustaining by the end of the third cycle | n/a |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| Ex-combatant populations participating in illegal natural resource extraction reduced | 65% reduction in the number of ex-combatants | n/a |
| Stability and legal economic activity in areas of natural resource extraction enhanced | The plantation and surrounding areas stabile with income generation activities taking place | Ex-combatants and community members remained engaged in illegal activities in the area |
| Trainees trained in MOA approved agricultural techniques | Trainees are applying the skills acquired | ongoingn/a |

Qualitative achievements against expected results:

- Tumutu site was identified to host approximately 400 students - Tumutu site was visited in October 2006 and it was established that site offered the best possible agricultural potential, the size to absorb a residential training site for 400 students and met the location parameters for a safe distance from Guthrie Rubber Plantation and a major town but a sustainable distance from Monrovia - Landmine Action recruited a Liberian architect/construction manager and conducted site assessments and planning for the reconstruction of the site - 356 successfully graduated from the course on 6th September 2008

Challenges{If Necessary}:

- Most of the ex‐combatant students were traumatised from the war, sparking occasional incidents of problematic behavior during lessons. This was a common feature in the first three weeks of the training. Trainers admitted to some marked improvement in trainee behavior and attitude once they started the social reintegration classes. Once again this reinforces the lesson that social integration and psycho‐social counseling work with trainees is of considerable value within the whole training process - Sometimes training material for the practical work was delivered late or the wrong equipment was bought. This necessitated the need for trainers to join the logistics team for procurement of agricultural equipment. This collaboration needs to be strengthened for future courses as the logistics team does not have the technical levels of expertise required - The amount of quality assurance given to the delivery of lessons was not adequate on the first course and will be increased from the second and subsequent courses. It is hoped that this will be undertaken by the Ministry of Agriculture as LMA staff do not have the agricultural expertise necessary to appraise the quality of lesson content

Hard men, Guthrie ex‐combatants, Feb 07

Rubber Tapper, Guthrie Oct 06