- Liberia Peace Building Fund

- QUARTERLY STATUS REPORT AS OF 31 MARCH 2010

| Recipient UN Organization: | UNDP |  | PBF Priority Area: |  | 3.1, 3.2 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Implementing Partner(s): | The Judiciary, Republic of Liberia |  |  |  |  |  |  |
| Project Number: | PBF//R3/A3/09 (PBF/LBR/E-4) |  |  |  |  |  |  |
| Project Title: | “Strengthening Public Defense” |  |  |  |  |  |  |
| Total Approved Project Budget | $750,066 USD |  |  |  |  |  |  |
| Project Objective and Scope | Long term war and insecurity has led to the disintegration of the Liberian legal system. Efforts to rebuild the trust of the Liberian people are ongoing by ensuring the rights of suspects, detainees and accused can be respected and provided access and opportunity for free and fair trials. One key area however, has not been adequately addressed: the rights of prisoners and defendants in the legal system. Pre-trial detainees are languishing in jail as a result of poor case management procedures, lack of transportation, and lack of legal representation. It is the responsibility of the Public Defenders’ Office to represent indigents, yet the office is poorly equipped to do so. The Public Defenders’ Office lacks both the logistical support and proper capacity to provide services so desperately needed by unrepresented indigents. While much emphasis has been placed on prosecution of the accused, the defence has not been given similar consideration. A fully functioning and just legal system should place equal emphasis on prosecution and defence and upholding the right to due process. This project duration is 12 months. |  |  |  |  |  |  |
| Funds Committed: | $682,844 USD |  | Percentage of Approved: |  | 91.0% |  |  |
| Funds Disbursed: | 369,958 |  | Percentage of Approved: |  | 54.2 |  |  |
| SC Approval Date: | January 22, 2009 |  |  |  |  |  |  |
| Expected Project Duration: | 12 Months | Forecast Final Date: |  | April 2010 |  | Delay (Months): | 4 Months |

| Outputs: | Progress: | Percentage of planned: |
| --- | --- | --- |
| 1. Identify and recruit a Public Defense Training Coordinator to be assigned with the Judicial Training Institute (JTI) to coordinate the development of a curriculum for training. 2. A comprehensive training manual and program established to train public defender through the Judicial Institute (JI) | - Public Defense training coordinator has been recruited and consultations for the development of curriculum initiated. ( 3rd quarter achievement) - Training Coordinator has initiated consultations aimed at developing a comprehensive training manual (3rd quarter initiation) | - 100% - 50% |
| 3.Office space for 8 public defenders is identified/refurbished | Offices for four public defenders identified and equipments, logistics including 14 pick-up trucks have been handed to Public Defenders. Salaries is being processed for PDs, Coordinator, PD’s Assistant for 3 months- January to June, 2010 | 100% |
| 4.Public defenders are available and dedicated to represent and protect the legal interest of individuals declared indigents 5. Public Defence monitor recruited to provide oversight monitoring of public defenders alongside the Training Coordinator on a roving basis. | Public defenders have been identified and recruited by the Judiciary and deployed into counties. First out of 4 comprehensive trainings for 21 public defenders held in Monrovia in collaboration with the JI ( 4th quarter achievement) Achieved | 100% 0% |

| Outcomes: | Progress: {In terms of Indicators} | Comments/Remarks: |
| --- | --- | --- |
| outcomes: Peace building Impact: An effective and accessible public defence system that underprivileged and economically challenged individuals, though accused of crimes, can rely and trust for adequate legal representation and protecting the right to due process. Key Outcomes: Citizens will have increasing confidence in public defence system and will begin to seek and rely on trained and equipped public defender to have their day in court. | Public defenders are already visiting the Monrovia Central Prison and taking on cases involving pre-trial detentions, non trial due to lack of representation, etc. Several motions have already been filed in favour of these indigent clients. Even though this is encouraging progress towards outcome, however, this progress is minimal and negligible at this stage Citizens are seeking legal assistance of public Defenders in the underprivileged Counties. Public defenders are actively representing indigents in Lofa, Bong, Grand Gedeh, Grand Kru, River Gee, Maryland and other counties. There are total of 21 public Defenders assigned in the 15 Counties | N/A |
| Number of prolong pre-trial detentions in withholding centres and at the Central Prison will decrease. Citizens rights to due process protected with greater appreciation of the cliché – “an accused is deemed innocent until proven guilty | As part of term of reference; public defenders are visiting courts and prisons in their respective assigned areas to review cases and provide legal services for indigent where required. |  |
| ”. A functional, trained and equipped criminal justice system comprising both strong and effective prosecution and public defence system. Citizens develop confidence in the fairness of the criminal justice system and its capacity to respect basic human rights. | The newly recruited Public Defenders are competent and young Law School graduates. Several trainings are scheduled which also match the level of support to improve and strengthen prosecutors. |  |

Qualitative achievements against expected results:

Key Achievements: Public Defenders assigned around the country continue to represent the interest of indigents clients free of charge. Next Steps: A series of 3 trainings are being scheduled for Public defenders. A consultant is being recruited to work with the Training Coordinator to develop and compile a training curriculum. A second consultant will be recruited to vet the draft curriculum with stakeholders

Challenges{If Necessary}:

- The late start of project implementation activities due to delay in funds being made available will impact heavily on the completion of the project as originally planned. - Respond of national partner to project timeline and activities –compiling and presenting reports in a timely manner remains an issue; - UNDP procurement processes continue to present some bottlenecks when recruiting and procuring services and logistics

Annex 1 (Additional elements such as photos, list of workshop participants etc

Public Defenders in training session