SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

31 MARCH 2010

| Project No & Title: | PBF/SLE/A-4 Support to the Implementation of the Reparations Program as part of the Recommendations of the Truth and Reconciliation Commission |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Recipient UN Organization: | IOM |  | Priority Sector: | Democracy and Good Governance |  |  |
| National Authority: | National Commission for Social Action (NaCSA) |  |  |  |  |  |
| Location: | Nationwide |  |  |  |  |  |
| Project Cost: | USD 3,000,000 |  |  |  |  |  |
| SC Approval Date: | 15 July 2008 | Starting Date: | November 2008 |  | Completion Date: | Extended to March 2010 |
| PBF Outcome priority area | Priority 2. Good governance and national reconciliation. Outcome 6: national reconciliation |  |  |  |  |  |
| Project Description: | There is a compelling need to urgently provide remedies to those persons identified by the TRC as victims of the war. This project is aimed at establishing a Reparations Unit within NaCSA (the agency recommended by the TRC to take the lead in implementing the reparations program) that will operationalize the strategy and plans developed by the Reparations Task Force to identify victims and provide the necessary support and/or socials services to them.. It is envisaged that the success of this program will invaluably contribute to national reconciliation and enhance the peace consolidation process. This fulfils Government’s legal obligation in the Lomé Peace Agreement of 7th July 1999. |  |  |  |  |  |
| Immediate Objective: | - Contribute to an improved capacity of the Reparations Directorate of National Commission for Social Action (NaCSA) for the implementation of the Reparations Program. - Contribute to improved human dignity of the victims of the conflict through a reparations program |  |  |  |  |  |
| Project Progress as at March, 2010 |  |  |  |  |  |  |
| Funds disbursed: | USD 2, 968,370.52 |  |  |  |  |  |
| Delivery rate: | 98.95% |  |  |  |  |  |
| Outputs delivered: | - Five years strategy developed. - Draft project proposal for the 2010 second phase of the current project developed - Database for 29,733 established and uploaded exceeding the 19,000 anticipated. - Special Fund for War Victims established - NaCSA sensitized direct and indirect stakeholders for the following purposes: 1) payments of grants; 2) establishment of the War Victims Trust Fund; 3) successfully defended a budget request for appropriation by Parliament in the fiscal year 2010. - Payments of the first installment of micro grants and educational support continued. Out of the 20,107 eligible, 750 did not show-up during the payment window. The payment window was extended and payments to the outstanding caseload are ongoing. The project already obliged funds for this purpose. - 215 victims of sexual violence were screened and provided with financial assistance to treat various gynecological and fistula problems bringing the total number of victims of sexual violence assisted so far to 235. - Forty community symbolic reparation activities have been carried out. - Community psychosocial support activities were completed in four communities in the country (north, south, east and west). |  |  |  |  |  |
| Achievements and challenges | - The educational and micro grants support which was provided close to the re-opening of schools assisted majority of the war affected families to pay school fees on time. However, recent monitoring visits show that majority of the micro grants were also converted to educational support. - The emergency fistula operations, the treatment of other STIs and the removal of bullets from war wounded have contributed to postwar healing processes. - Data base: the estimated numbers of beneficiaries at the beginning of the project was 19,000. The registration process identified 29,733 war victims. During and after payment window, more potential beneficiaries approached NaCSA requesting late registration. While the estimated number has been achieved, the excess number and incoming requests indicate that a mechanism to handle late registration and verification must be established. The ICTJ Report recommends the finalization of the registration process. - NACSA is now being challenged by the issues of follow-up on the benefits received from victims to gather and record success stories. They are most importantly being challenged with the possibility of immediate funding opportunities to continue support for not only verified cases but also new cases. This poses a risk of increasing the feeling of disillusionment and neglect from the victims, making it a potential threat to sustained peace. - IOM is now awaiting final narrative and financial report for disbursement of the outstanding funds. |  |  |  |  |  |