SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

31 DECEMBER 2009

| Project No & Title: | PBF/SLE/A-5 Capacity building for Sierra Leone Parliament for enhanced performance of its core functions of representation, oversight and legislative enactment. |
| --- | --- |
| Recipient UN Organization: | IOM | Priority Sector: | Democracy and Good Governance |
| National Authority: | Sierra Leone Parliament |
| Location: | Freetown |
| Project Cost: | USD 700,000 |
| SC Approval Date: | 3 June 2009 | Starting Date: | August 2009 | Completion Date: | July 2010 |
| PBF Outcome priority area | Priority 2. Good governance and national reconciliation. Outcome 6: national reconciliation |
| Project Description: | Since Sierra Leone gained independence from Britain in April 1961, its Parliament has been a major player in the building, strengthening and expansion of pluralistic democracy in the country. However, Parliament’s contribution and overall impact on democracy building and governance reform has been marginal and overshadowed by the country’s much troubled political history of insecurity and instability consequent on many years of poor political and economic governance, exacerbated by military misadventure Throughout this long interlude of political turbulence, Parliament experienced a hemorrhage of its well trained and experienced technical, legal and administrative professionals that seriously depleted its institutional capacity thereby effectively disabling it to discharge its core oversight and legislative functions. This project therefore intends to strengthen the capacity and capability of the secretariat of parliament and the newly elected parliamentarians to be able to effectively carry out the basic functions of parliament (representation, oversight and legislation. The project shall provide trainings for 124 parliamentarians and 25 secretariat staff and provide basic logistics to the secretariat. It shall also provide books, computers and shelves for a resource centre. |
| Immediate Objective: | Contributing to a better serviced and more efficient legislative process as a result of improved capacity of the secretariat of Parliament being exposed to modern management practices Contribute to improved capability of newly elected parliamentarians for enhanced representation, oversight and legislative enactment. |
| Project Progress as at December, 2009 |
| Funds disbursed: | USD 141,722.50 |
| Delivery rate: | 20.24%% |
| Outputs delivered: | Recruitment of 8 parliamentary researchers. Recruitment of 12 Clerks for committees Vehicles and mini buses been clared computers supplied for library liberay been rehabilitated and books been ordered Contract awarded for planning and execution of trainings. |
| Achievements and challenges | Due to technical reasons outside the control of the recipient agency, the vehicles and motor bikes, will physically reach the IOM premises during the first two weeks of January 2010. IOM is coordinating with UNIPSIL a formal handover ceremony during the first part of the first quarter of 2010. |