SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

31 DECEMBER 2009

| Project No & Title: | PBF/SLE/B-1 Improved Public Order Management Capacity |
| --- | --- |
| Recipient UN Organization: | UNDP | Priority Sector: | Justice and Security |
| National Authority: | Sierra Leone Police |
| Location: | Country wide |
| Project Cost: | USD 1,042,564.91 |
| SC Approval Date: | 11 May 2007 | Starting Date: | June 2007 | Completion Date: | March 2008 |
| PBF Outcome and Priority area | Priority 1. Implementation of peace agreement. Outcome 1: Strengthen security sector |
| Project Description: | The project is designed to strengthen the Sierra Leone Police’s capacity to ensure public order and reduce criminality especially during the parliamentary and presidential elections of August and September 2007. |
| Immediate Objectives: | The immediate objective of the project is to provide adequate and modern equipment for the Operational Support Division and the Crowd Control Units of the SLE Police force |
| Project Completed in March 2008 |
| Funds disbursed: | USD 1,042,564.91 |
| Delivery rate: | 100% (Project operationally closed) |
| Outputs delivered: | Public order during the electoral period was ensured with an increased capacity and morale of SLP through timely delivery of police uniforms, helmet, torch, extinguishers, shields, etc. |
| Achievements and challenges | Public order during the electoral period was ensured with an increased capacity and morale of SLP through the timely delivery of police uniforms, helmet, torch, extinguishers, shields etc. The project was initially unable to take delivery of some armed equipment of about $256,000 after commitments were made through the Bank of Sierra Leone to the vendor due to export restrictions. Concerted efforts through the UN, the Government and other bilateral interests including the UK have finally yielded dividend. The equipments have now been delivered. |