SIERRA LEONE

PEACEBUILDING FUND

PROJECT STATUS REPORT

30 JUNE 2009

| Project No & Title: | PBF/SLE/B-3 Emergency Support to the Security Sector |
| --- | --- |
| Recipient UN Organization: | UNDP | Priority Sector: | Justice and Security |
| National Authority: | Ministry of Finance |
| Location: | Nationwide |
| Project Cost: | USD 1,822,823.94 |
| SC Approval Date: | 11 July 2007 | Starting Date: | July 2007 | Completion Date: | July 2008 (One year) |
| PBF Outcome and Priority area | Priority 1. Implementation of peace agreements Outcome 1. Strengthened security sector |
| Project Description: | Approved in July 2007, the objective of the project was to fill the gap in funding from unforeseen shortfalls in domestic revenues and external support during the period prior and leading to the 2007 parliamentary and presidential elections through |
| Immediate Objective: | Emergency support to the security sector, Republic of Sierra Leone Armed Force (RSLAF), Sierra Leone Police, and the Prisons, to ensure the peaceful conduct of the Presidential and Parliamentary elections. |
| Project Progress as at June 2009 |
| Funds disbursed: | $1,822,823.94 |
| Delivery rate: | 100% (Project completed about one year ago) |
| Outputs delivered: | The logistics capacity and the physical state of the SLP, prisons department and RSLAF improved through the timely delivery of fuel and lubricants, medical and diet rations, stationery and uniforms, which ensured the peaceful conduct of the Presidential and Parliamentary elections. |
| Achievements and challenges | All items have successfully been delivered and the project is operationally closed Price increase during the elections was experienced, but UNDP identified alternative vendor to keep the original price Government had already commenced procurement process prior to project launch, but rigorous joint process ensured the transparency of the process and value for money. |