Annex 2.1

UNITED NATIONS PEACE FUND FOR NEPAL

PROJECT DOCUMENT COVER SHEET

| Participating UN Organization: UNIFEM and OHCHR |  | Priority/Cluster: Nepal PBF Priority area (when appropriate): 2.8 Strengthening State Capacity for Sustaining Peace |
| --- | --- | --- |
| Project Manager Name: Yamun Yadav Address: UNIFEM, Thapathali, Kathmandu Telephone: 977-1-4255110 E-mail: yamun.yadav@unifem.org |  | Funding round Strategic Outcome the proposal will contribute towards: Strategic objective 4: capacity enhancement of national institutions to promote women’s participation in peace process and protect the rights of women affected by conflict in line with UNSCRs 1325 and 1820. |
| Project Title: Partnership for Equality and Capacity Enhancement (PEACE): Towards Implementation of UNSCRs 1325 and 1820 UN Fund Project Number:__________________ (assigned by the Executive Committee Support Office) |  | Project Location: National level |
| Project Description: Support the capacity enhancement of the government and civil society at the central level for effective implementation of UNSCRs 1325 and 1820 and thereby contribute to the promotion of women’s participation in peace processes and protection of the rights of women affected by conflict. This will eventually contribute to consolidation of peace in Nepal. Adjustment |  | Total Project Cost: USD 595,000 PBF funds (if earmarked): USD 525,000 Funding available through other sources: USD 70,000 Total requested from the UNPFN in this submission: USD525,000___________________________________ |
|  |  | Project Duration: 24 months Envisaged start date: 1 April 2010 |
| Goal, immediate objectives and anticipated peacebuilding impact: Contribute to consolidation of peace in Nepal through facilitating the implementation of national commitments to gender equality and women’s human rights. |
| Outcomes and key activities Outcome1: State entities create enabling institutional environments to promote and protect women’s human rights in line with UNSCRs 1325 and 1820, and other human rights instruments especially CEDAW. Key activities: Orientation to HLSC on UNSCRs 1325 and 1820; developing the NPA on UNSCRs 1325 and 1820; supporting HLSC in reporting on UNSCRs 1325 and 1820; strengthening HLSC Secretariat; train the key government ministries’ staff on CEDAW and UNSCRs 1325 and 1820; mainstreaming gender in policies and programmes of MOPR; assist NWC in strengthening the monitoring mechanism; and orientation for civil society on NPA on UNSCRs 1325 and 1820. |
| Executive Committee Support Office Review Date: Expert Group Review Date: Executive Committee Approval Date: |

On behalf of the Participating UN Organization:

_____________________________	Sangeeta Thapa, UNIFEM Program Coordinator

Signature				Name and Title

_____________________________	Richard Bennet, Representative of High Commissioner for Human Rights

Signature				Name and Title

Endorsed by the Executive Committee

Robert Piper

Chair- UN Resident Coordinator for Nepal

_____________________________	___________________________

Signature		Date

Annex 2.2

Full Project Document - Outline (max. 7 pages)

1. Background and problem statement The Comprehensive Peace Accord (CPA) signed between the State and the then Communist Party of Nepal-Maoist (CPN-M) in November 2006 resulted in officially ending a decade long armed conflict (1996-2006) in Nepal. During the decade long conflict and in post conflict period, women have been highly affected and impacted due to their gendered roles and responsibilities. The impact of conflict on women have been significant particularly due to the increased sexual and gender based violence (SGBV), displacement, loss of family members and loss of livelihoods among many, and more so on traditionally excluded groups of women (Dalits, Janajatis, Madhesis and other minorities). The country is passing through a critical phase of transition to peace process. The constituent assembly (CA) election in April 2008 resulted in 33% representation for women, 27% for indigenous people, 9% for Dalits, 28% for Madhesis, and 5% for disabled – a historical achievement nationally, regionally and internationally. However, the violation of women’s human rights and widespread prevalence of SGBV and discrimination against women remain unabated. Hence, it is of utmost importance that the state takes appropriate measures for the protection of women and girls from all forms of discrimination and SGBV, and promotes their participation in the prevention, management, and resolution of conflict through effective implementation of various national and international conventions and agreements. Among others, the implementation of Convention on the Elimination of All forms of Discrimination Against Women (CEDAW) and United Nations Security Council Resolutions (UNSCRs) 1325 and 1820 is of particular importance at this juncture of peace process as the focus of UNSCR 1325 is on the disproportionate impact of armed conflict on the lives of women and girls and the necessity to increase their participation in all processes concerning conflict prevention, management, and resolution. UNSCR 1820 builds on and strengthens UNSCR 1325 in respect of rape and other forms of SGBV in armed conflict situations. It recognizes that sexual violence is both a cause and consequence of women’s low participation in decision making. UNSCRs 1888 and 1889, which were adopted in 2009 by the Security Council further strengthens the commitment of member states for implementation, monitoring and reporting of UNSCRs 1325 and 1820. CEDAW with its wider scope – and, more importantly, as a convention ratified by the Government of Nepal and thus legally binding – therefore provides a stronger framework for stopping violence (and all types of discrimination) against girls and women in Nepal. The creation of linkages between CEDAW implementation and advocacy on UNSCR 1325 would benefit both processes - and the overall fight against violence against women. In Nepal, the Ministry of Peace and Reconstruction (MOPR) is the lead government agency for the implementation of UNSCRs 1325 and 1820. The MOPR, with the technical and financial assistance from United Nations Development Fund for Women (UNIFEM), has been undertaking a range of activities for the implementation of UNSCR 1325 and 1820. Some of the key steps of the Government towards the implementation of UNSCRs 1325 and 1820 are: initiation of the preparation of National Plan of Action (NPA) on UNSCRs 1325 and 1820; the formation of a High Level Steering Committee (HLSC) on UNSCRs 1325 and 1820; and the organization of workshops and training programmes on UNSCRs 1325 and 1820. The HLSC consists of 18 members of which about 45% are women including the chairperson. The HLSC is mandated for developing required policies for gender mainstreaming in conflict management and peace processes; preparing the NPA on UNSCRs 1325 and 1820 and coordinating its implementation including mustering support of international communities; and reporting to the United Nations on the implementation of UNSCRs 1325 and 1820; among others. Currently, this Ministry is in the process of forming Local Peace Committees (LPCs) in all the 75 districts of Nepal and 67 district level LPCs have been formed so far. After much advocacy, the Terms of Reference for LPC now has a provision for 33% representation of women in LPCs. Monitoring the implementation of UNSCRs 1325 and 1820 is one of the key focus areas of National Women’s Commission’s (NWC) strategic plan, which was developed with technical support of UNIFEM. Recently, the NWC has initiated the process for monitoring women’s human rights situation in collaboration with civil society networks in 20 districts representing the 14 zones, 5 development regions and 3 ecological zones of Nepal; and has expressed the need for technical support to establish information management system for effective monitoring. Despite their firm commitments, the capacities of the national institutions, including MOPR, for the effective implementation of these resolutions remain a critical challenge. The Capacity Assessment of MOPR (2009) has revealed that there are only few women within the MOPR and there is need for promoting them at the decision making level. Social inclusion and gender mainstreaming comes up very prominently in the MOPR’s capacity development strategy (draft), which has emphasized on the need for ministry-wide training and orientation on Gender Mainstreaming and Inclusiveness, which will serve as an input for allocating 45 percent of open positions for marginalized groups including women, janjatis, madhesis, dalits among others. Further, the recently created HLSC needs technical and logistical support to effectively take forward its mandate; and this has been communicated to UN including UNIFEM and other development partners during various formal and informal meetings. It is, therefore, important to assist the Government of Nepal for capacity enhancement of relevant national mechanisms/institutions - such as HLSC, MOPR, Ministry of Women, Children and Social Welfare (MWCSW), NWC and civil society organizations (CSOs) for the effective implementation and monitoring of UNSCRs 1325 and 1820. At the same time, efforts should also be made to increase the awareness of women and men about their human rights, particularly outlined under UNSCRs 1325 and 1820. In Nepal, UNIFEM has been actively supporting sensitization and awareness raising programmes on UNSCRs 1325 and 1820 both at the policy level and the grassroots level. Information, educational and communication (IEC) materials have been developed in simple language to demystify and share the information on UNSCR 1325 and 1820. The resolutions have also been a guiding document for UNIFEM’s support on promoting women’s participation in the CA and promoting a gender sensitive Constitution. The MOPR and UNIFEM have been working together for promoting women’s participation in peace and rebuilding processes, with special focus on enhancing capacity of the government machinery on UNSCRs 1325 and 1820 since November 2007. The work for the development of NPA on UNSCR 1325 and 1820 has been initiated by the MOPR with support from UNIFEM; there exists some funding gaps to accomplish this work. UNIFEM is also supporting a gender sensitive Transitional Justice (TJ) process in Nepal to bring voices of women in the TJ mechanisms and addressing concerns through reparations, and other forms of healing. More recently, it has initiated interventions for mainstreaming gender equality and women's human rights in the policies, programmes and operations of security forces. UNIFEM has been actively involved in the Peace Support Working Group (PSWG) on UNSCRs 1325 and 1820, which comprises representatives from UN and donor agencies. PSWG is responsible for coordinating UN and donor agencies to provide support to the government to ensure implementation of UNSCR 1325 and 1820. On its part, Office of the High Commissioner for Human Rights-Nepal (OHCHR-Nepal) has supported the MOPR in organizing regional and cluster consultations to ensure that women and children voices are represented in the Truth and Reconciliation Commission (TRC) consultations. It has also supported the NWC to promote women’s participation in the decision making processes. Similarly it has also conducted trainings on the general human rights framework including specific trainings on CEDAW, UNSCR 1325 to stakeholders including government, civil society and national institutions. In South Asia, devising policies, programmes and interventions in accordance with UNSCR 1325, and thus protecting the human rights of women in conflict and post conflict situations has been identified as one of the priority areas for immediate action by the governments of the region. In this context and the above-mentioned background, the present project proposal has been developed in consultation with the concerned government authorities, in particular the MOPR, Ministry of Foreign Affairs (MOFA), MWCSW and NWC. All these government authorities have welcomed the project concept and expressed their commitment for cooperation. Building upon UNIFEM's and OHCHR-Nepal’s experiences and their ongoing work on women's empowerment and gender equality including UNSCRs 1325 and 1820, this project proposal has been developed to address the capacity development needs of the government and civil society for effective implementation of UNSCRs 1325 and 1820. This is also in line with the focus of the Interim Plan as well as Nepal United Nations Development Assistance Framework (UNDAF) - peace and development for an inclusive society. The beneficiaries of the project include the duty bearers, particularly HLSC, MOPR, MOFA, MWCSW, NWC and civil society; and the rights holders, mainly women affected by conflict. Enhanced capacities of these stakeholders will lead to the promotion of women’s participation in peace processes and protection of the rights of women affected by conflict through effective implementation of UNSCRs 1325 and 1820. This will eventually contribute to consolidation of peace in Nepal. 2. Project approach and expected results The overall goal of the project is to ensure that the concerned stakeholders, specifically, State entities, are taking decisive and appropriate action to fulfil their obligations under UNSCR 1325, 1820, CEDAW and other human right instruments that Nepal is party to, and thereby, creating enabling institutional environment to promote and protect women’s human rights. Within this context, the formation of the HLSC is an important step; however, there is a need for further strengthening of the institutional capacities of this mechanism to fulfil its mandate. At the same time, initiatives at the Central level need to be replicated or complemented at the district or local levels to ensure that the decisions taken at the central level are disseminated and implemented at the local levels. Therefore, developing and pilot-testing training package and workshop model for capacity development towards effective implementation of NPA on UNSCRs 1325 and 1820 have been proposed through this project. The overall programme strategy will be guided by a human rights based approach with focus on forging strategic partnerships, inclusive participation, capacity development, lobbying and advocacy, linkages and coordination, programme integration and sustainability. The inclusive participatory process will strengthen ownership and commitment of involved stakeholders and contribute in improving the design and relevance of interventions, their effective implementation and their integration into the regular programmes of concerned stakeholders. In collaboration with PSWG on UNSCR 1325 & 1820 and PSWG on Reintegration (formerly called the security sector transition), UNDAF thematic groups on consolidating peace and gender equality and social inclusion, coordination and linkages with other relevant donor supported programmes will be strengthened to avoid duplication and gain synergy and also to ensure technical support as needed. Emphasis will be placed on linking the elements of this project with other ongoing programmes of UN agencies and other development partners, particularly in the areas of governance, peace and security to ensure programme effectiveness and synergy. This will be achieved through the regular meetings of the Project Coordination Committee as described under Coordination Arrangement, Section 4. The MOPR’s capacity development strategy being supported by UNDP will serve as the guiding document to ensure coordinated and harmonized support towards capacity enhancement of the ministry. Through strengthening the capacities of policy, service delivery and media institutions at the national level, the project addresses Nepal PBF Priority 2.8: Strengthening State Capacity for Sustaining Peace and the strategic objective 4 of the UN Peace Fund Nepal (UNPFN), which emphasises on capacity enhancement of national institution to promote women’s participation in peace process and protect the rights of women affected by conflict in line with UNSCRs 1325 and 1820.The project is aimed at capacity enhancement of the duty bearers and rights holders; and thereby improving downward and horizontal accountability towards the rights of conflict affected women and men. The project seeks to make significant contribution towards sustainable peace through inclusive development, which is the key priority of the current Interim Plan of the Government of Nepal as well as UNDAF. The capacity development of central level stakeholders will strengthen the national commitment for the implementation of UNSCRs 1325 and 1820 and lead to the finalization of the NPA on UNSCRs 1325 and 1820 and resource allocation for its implementation. The implementation of the NPA will ensure coherent and harmonized action towards addressing the needs of conflict affected women and girls and promoting and protecting their rights. The collaboration with the women’s caucus in CA will strengthen the political commitment to implementation of UNSCRs 1325 and 1820. The endorsement of the NPA on UNSCRs 1325 and 1820 will ensure the availability of resources and capacity development of stakeholders for its implementation will lead to delivery services and benefits to the conflict affected women and girls; and thereby contributing to the consolidation of peace and sustainability of project results. Further, the involvement of media and civil society in the process and annual reporting will enhance the accountability of the government towards the implementation of UNSCRs 1325 and 1820. The training package and workshop model for integrating the activities of NPA on UNSCRs 1325 and 1820 into the regular programmes of sectoral ministries will be developed and pilot-tested in selected districts followed by rigorous assessment and documentation of processes and lessons with a view to develop models for replication. With the improved policy and programme frameworks for gender mainstreaming in conflict management and peace processes, increased level commitment and capacity for the implementation of UNSCRs 1325 and 1820; the NPA will be effectively implemented resulting in increased participation of women in peace processes and promotion and protection of women’s human rights. It is expected that after the project interventions, involved agencies will mainstream gender and women’s human rights issues into their planning and programming. The key expected results of the project include the following: Outcomes: State entities create enabling institutional environments to promote and protect women’s human rights in line with UNSCRs 1325 and 1820, and other human rights instruments especially CEDAW. Outputs: Output1.1: Enhanced capacity of HLSC to successfully implement its mandate. Output-1.2: Enhanced understanding of concerned government authorities on UNSCR 1325, 1820 and CEDAW for mainstreaming of women’s rights in government programmes and policies. 3. Analysis of risks and assumptions Despite the ongoing fluid socio-political situation and associated challenges, UNIFEM Nepal is confident to take forward the project processes by utilizing its comparative advantages in terms of its core competencies in promoting gender equality and women’s human rights, its catalytic role, its innovative approaches and its congenial functional relations with the government, civil society, media and private sector organizations. Further, this project has been developed through an interactive participatory process involving a series of consultations with the concerned government authorities. The strategic focus of this project is on participatory process during implementation. Through ensuring the participation of the government and other stakeholders throughout the project cycle and thereby, strengthening their ownership, UNIFEM will able to guarantee effective implementation of the project. The analysis of specific risks/assumptions, their probability and mitigation measures are presented in the table below. Assumptions Risks Probability Mitigation Measures 1. The new constitution will be promulgated and adopted in May 2010 The adoption of the new constitution may lead to changes in the governance structures; and hence can affect the implementation of the project Medium The project design will be revised to take into account the structural changes in the governance mechanism to ensure smooth implementation of project activities 2. The present government continues to work smoothly The level of government commitment to implementing UNSCRs 1325 and 1820 may change with the change in the government leadership; and adversely affect project implementation Medium UNIFEM will mobilize strategic support based on its existing memorandum of understanding (MOUs) and letter of agreements (LOAs) with the Government authorities such as MOPR, MWCSW, MLD and Ministry of Labour and Transport Management (MOLTM) to ensure that change in government does not affect the project 3. The government is responsive to expertise support from civil society Implementation will be adversely affected if the government does not welcome expertise support from civil society Low Identify civil society partners and experts through mutual consent with the concerned government authorities UNIFEM has got Memorandum of Understanding (MOUs) and Letter of Agreements (LOAs) with the key Government authorities (MOPR, MWCSW, MLD and MOLTM) and is in the process of signing an MOU with the Ministry of Defence. All these will help further strengthen partnerships for smooth implementation of the project. 4. Partnerships and Management Arrangement Partnerships UNIFEM Programme Office Nepal with technical assistance from OHCHR-Nepal will have the overall responsibility for executing the project. The project activities will be carried out through partnership with the government and civil society actors including the media. The MOPR and MOFA will be the main implementing partner for this project. During the implementation, cooperation will be sought from the relevant government authorities, which would include the Office of the Prime Minister and Council of Ministers, relevant Ministries (Defence, Foreign Affairs, Home Affairs, Women, Children and Social Welfare, Law and Justice, Local Development) and the NWC. Similarly, CSOs may also be involved in implementation, if needed, for providing technical inputs. Such organizations will be selected through competitive bidding process based on the agreed upon criteria. Management Arrangement A project team comprising of a Project Manager, a Project Assistant and an Administrative and Finance Assistant will be appointed by UNIFEM for day to day operation of the project. The Project Manger will be responsible for overall management of the project and provide technical backstopping to the implementing partners. The Project Assistant will assist the Project Manager in overall execution of the project with particular focus on ensuring communication and flow of information among the partners, compilation of monitoring information and preparing for training and workshop events. The Administrative and Finance Assistant will be responsible for disbursement of fund, account keeping, procurement, keeping inventory, and logistic arrangements. The incumbent will also provide backstopping to partners on administrative and financial matters. The UNIFEM Programme Coordinator and the Programme Support Manager will provide the overall strategic and technical guidance to the project team and will also coordinate with UNIFEM South Asia Regional Office (SARO), based in New Delhi and UNIFEM Headquarters for drawing on relevant regional and global experiences, technical inputs and advice. A Project Management Unit (PMU) will be set up at UNIFEM comprising of the project team, UNIFEM Programme Coordinator and Programme Support Manager and a representative from OHCHR-Nepal, who will bring in national and international experiences particularly from human rights perspectives. The PMU will be headed by the UNIFEM Programme Coordinator and will provide the overall guidance to the project team and monitor the project activities. Coordination Arrangement To facilitate and coordinate the work of HLSC on UNSCRs 1325 and 1820, a Project Officer and a Project Secretary will be appointed by the project and placed in the Secretariat of HLSC. While the Secretary will be responsible for ensuring logistic support, the Project Officer under the guidance of the Member Secretary of the HLSC will coordinate with the members of HLSC, relevant sectoral ministries, civil society organizations and development partners; support in preparing for the HLSC meetings; and liaise with the PMU in relation to implementation of project activities. The HLSC will provide the overall strategic guidance, programmatic direction and ensure inter-ministerial coordination and cooperation for smooth implementation of the project. This project will also develop linkages with the relevant working committees/subcommittees under HLSC to seek guidance and advice. With a view to avoid duplication and build synergy with other ongoing relevant initiatives through fostering programme linkages, a Project Coordination Committee (PCC) will be established at the onset of the project. The PCC will be chaired by the Joint Secretary, MOPR, who is also the member Secretary of HLSC, and co-chaired by UNIFEM Programme Coordinator. The members of PCC will include the Chair and Co-Chair of PSWG on UNSCR 1325 and representatives from MOFA, MWCSW, UNIFEM and OHCHR, The Project Manager of this PEACE project will work as the member secretary of PCC. The Chair and Co-Chair of PSWG on UNSCR 1325 and 1820 will be expected to share the information about the PEACE project with the members of PSWG through appropriate mechanisms. The PCC will provide strategic guidance and ensure inter-agency coordination and cooperation for smooth implementation of the project. It will enable a broad consultative base where each stakeholder will be able to express its concerns and considerations regarding the project workplan, implementation, and progress. The information collected during the meetings will be incorporated into the project workplan and implementation. The meeting of PCC will be held on quarterly basis. 5. Monitoring & Evaluation Monitoring and evaluation (M&E) will be based on gender sensitive participatory approach involving target group, partners and other relevant stakeholders. UNIFEM, OHCHR-Nepal and the partners will design and adopt result based M&E framework for monitoring the project results in line with the indicators defined in the attached logframe. At the onset of the project, participatory capacity assessment of intended institutional beneficiaries will be carried out to identify the capacity development needs in terms of knowledge and skills for implementation of UNSCRs 1325 and 1820 and establish benchmark for monitoring and evaluation. Based on the results of capacity assessments, an M&E plan will be developed through a consultative workshop involving the partners and other relevant stakeholders. During this workshop, indicators and activities will be further refined in line with the findings of the capacity assessment of intended institutional beneficiaries. Project processes and activities will be regularly monitored and reviewed by implementing partners together with UNIFEM and OHCHR. The PMU at UNIFEM will have overall responsibility to monitor the project activities. Based on the monitoring, it will provide technical support and backstopping to project partners. The PMU will organise six-monthly and annual review meetings involving the implementing partners to review the achievements and identify the challenges. During this meeting, experiences of different partners working with the project will be shared for learning from each other and incorporating lessons into action plan of the next year. The implementing partners will compile gender disaggregated monitoring information, and prepare progress report and submit to PMU on six-monthly basis. The Project Manager will consolidate the progress reports received from the project partners and share the consolidated report with the Project Coordination Committee to get their feedback. The outstanding constraints and challenges encountered during the reporting period will also be discussed in the PCC meeting to find out appropriate solutions. The feedback and suggestions from the PCC meeting will be incorporated in the final progress report to be submitted to the UNPFN. The project completion report will be prepared and submitted towards the end of the project. An internal midterm self assessment of the project will be conducted towards the end of the first year. Towards the end of the project, an independent evaluation will be carried out by a team of experts to assess the achievements of the project objectives and document lessons learnt. The successful experiences and lessons learnt through the implementation of the proposed programme will be widely disseminated to concerned stakeholders. 6. Sustainability of the project The overall programme strategy will be guided by a rights based approach with focus on partnership, capacity enhancement, participation of the concerned stakeholders and promotion of transparent mechanisms and two-way accountability at all levels. The project will support the capacity enhancement of the involved partners and the conflict affected women and men through the provision of technical assistance, training programmes, workshops, and exposure visits. The collaboration with the women’s caucus in CA will strengthen the political commitment to implementation of UNSCRs 1325 and 1820. The endorsement of the NPA on UNSCRs 1325 and 1820 will ensure the availability of resources and capacity development of stakeholders for its implementation will lead to delivery services and benefits to the conflict affected women and girls; and thereby contributing to the consolidation of peace and sustainability of project results. All these elements will contribute to national capacity building as well as shared ownership of project interventions, processes and results. The project interventions at the central level combined with pilot testing of training and workshop models at district level will foster linkages and feedback mechanism between national policies and local realities; and will contribute to both vertical and horizontal dimensions of sustainability. 7. Logical Framework (Annex 2.3) 8. Project Budget (Annex 2.4) 9. Detailed work-plan (Annex 2.5)

Annex 2.3

THE LOGICAL FRAMEWORK

| Results | Measurable indicators | Means of verification | Important assumptions |
| --- | --- | --- | --- |
| PEACEBUILDING IMPACT Contribute to consolidation of peace in Nepal through facilitating the implementation of national commitments to gender equality and women’s human rights | At least 33% women’s representation in all conflict management and peace building structures % reduction in reported number of incidence of women’s human rights violations | Final evaluation report Reports of OHCHR, National Human Rights Commission, NWC and Informal Sector Service Centre (INSEC) CEDAW Report | The government and international organizations continue their commitment to gender equality and women’s empowerment The parties to CPA will be committed to its effective implementation |
| Outcome1: State entities create enabling institutional environments to promote and protect women’s human rights in line with UNSCRs 1325 and 1820, and other human rights instruments especially CEDAW. | The NPA on UNSCRs 1325 and 1820 developed and endorsed by the government within 2010 At least 80 percent of annual budget estimated for implementation of NPA made available and spent in 2011 Number of conflict affected women benefited from reintegration and reparation mechanisms | Final evaluation report Mid-term self-assessment report | (Outcome to peace building impact) The government commitment to implementing USSCRs 1325 and 1820 continues Enhanced capacity of concerned authorities will result in increased commitment and actions for promotion and protection of women's human rights That NPA will have budget allocated for its implementation. |
| OUTPUTS: Output1.1: Enhanced capacity of HLSC to successfully implement its mandate. | At least 80% of the HLSC members are able to identify 4 prime focus areas of UNSCR 1325 and 1820 Change in levels of understanding among HLSC members on implementation of UNSCRs 1325 and 1820 over time. Timely submission of annual report to UN on implementation of UNSCRs 1325 and 1820 Training package for district stakeholders focusing on NPA on UNSCRs 1325 and 1820 developed, pilot tested and endorsed by PCC and HLSC | Progress reports Consultation/ workshop reports Training reports Randomized training impact assessment survey | (Output to outcome) The present government continues to work smoothly |
| ACTIVITIES: | INPUTS: | (Activity outputs to outcome) |
| 1.1.1 Conduct project introductory workshop with central level stakeholders | 2,500 |  |
| 1.1.2Hold consultations with HLSC members to assess support needs. | 2,000 |  |
| 1.1.3 Provide orientation to HLSC members on the elements of UNSCRs 1325 and 1820. | 3,500 |  |
| 1.1.4 Support HLSC in developing the NPA on UNSCRs 1325 and 1820. | 40,000 |  |
| 1.1.5 Support HLSC to hold workshop on the key elements of NPA on UNSCRs 1325 and 1820 with decision making officials of sectoral ministries and the ministries’ roles and responsibilities in its implementation. | 2,500 |  |
| 1.1.6 Support HLSC to hold workshop on the key elements of NPA on UNSCRs 1325 and 1820 with civil society and media and their roles and responsibilities in its implementation | 3,000 |  |
| 1.1.7 Integrating the experiences of activities 1.1.5 & 1.1.6, prepare training package for district stakeholders to be involved in the implementation of NPA on UNSCRs 1325 and 1820. | 10,000 |  |
| 1.1.8Pilot-test the training package in 5 selected districts and refine the training package for replication | 40,000 |  |
| 1.1.9Provide technical assistance to HLSC to prepare and submit periodic report to UN on implementation status of UNSCRs 1325 and 1820. | 2,400 |  |
| 1.1.10 Equipment, furniture and other amenities for effective functioning of the HLSC Secretariat. | 22,400 |  |
| 1.1.11 human resources (1 project Secretary and Project Officer) for smooth functioning of the HLSC Secretariat | 50,400 |  |
| 1.1.12 Logistic support for meetings of HLSC on UNSCRs 1325 and 1820. | 5,000 |  |
| Output-1.2: Enhanced understanding of concerned government authorities on UNSCR 1325, 1820 and CEDAW for mainstreaming of women’s rights in government programmes and policies. | % of staff of MOPR, MOFA able to identify 4 prime focus areas of CEDAW and UNSCRs 1325 and 1820 Change in level of understanding among government staff on implementation of UNSCRs 1325 and 1820 NWC provides required data in time for preparation of annual report on implementation of UNSCRs 1325 and 1820 Workshop model for integrating the activities of NPA on UNSCRs 1325 and 1820 into the regular programmes of district line agencies developed, pilot tested and endorsed by PCC and HLSC | Randomized training impact assessment survey Progress reports Consultation/ workshop reports Training reports |  |
| ACTIVITIES: | INPUTS: | (Activity outputs to outcome) |
| 1.2.1 Train the staff of MOPR, MWCSW and MOFA on CEDAW, UNSCRs 1325 and 1820 and mediation skills. | 8,600 |  |
| 1.2.2 Technical support to MOPR for preparing gender-responsive policies and programmes. | 4,500 |  |
| 1.2.3 equipment support to NWC for compilation and processing of M & E information | 12,500 |  |
| 1.2.4 the services of Information Management Expert to design and implement information management system for tracking the implementation of UNSCRs 1325 and 1820 | 6,000 |  |
| 1.2.5 Provide training to NWC staff and its partners on M&E mechanisms, information collection and processing techniques for monitoring the implementation of UNSCRs 1325 and 1820 | 4,300 |  |
| 1.2.6 Provide orientation to peace and gender focal points of sectoral government ministries on the objectives and scope of NPA on UNSCRs 1325 and 1820 and their roles and responsibilities in its implementation | 5,000 |  |
| 1.2.7 Organize training-cum- workshops for planning focal points of sectoral government ministries on integrating the activities of NPA on UNSCRs 1325 and 1820 in their regular programmes as per their roles and responsibilities in its implementation | 15,000 |  |
| 1.2.8 Integrating the experiences of activity 1.2.7,develop workshop model for district level line agencies of sectoral ministries for integrating the activities of NPA on UNSCRs 1325 and 1820 in their regular programmes | 10,000 |  |
| 1.2.9 Pilot-test the workshop model in 5 selected districts and refine the model for replication | 45,000 |  |
| 1.2.10 Support women’s caucus in CA in holding orientation and advocacy consultations to ensure political commitment to implementation of UNSCRs 1325 and 1820 | 25,000 |  |

Annex 2.4

THE PROJECT BUDGET(Budget Revision date 29/3/2010)

The budget will be submitted in a spreadsheet with all necessary details under the categories below:

| CATEGORY | ITEM | UNIT COST | NUMBER OF UNITS | TOTAL COST |
| --- | --- | --- | --- | --- |
| 1. Supplies, commodities, equipment and transport |  |  |  |  |
| Desktop computers | 1 | 1000 | 1 | 1,000 |
| Laptop computer | 1 | 1200 | 2 | 2,400 |
| Printer | 1 | 1000 | 1 | 1,000 |
| Furniture & furnishing | 1 | 1600 | LS | 1,600 |
| Vehicle | 1 | LS | 1 | 23,364 |
| Vehicle Fuel & Maintenance | 2 | 100 | 24 | 4,800 |
| Stationery | 1 | 3500 | LS | 3,000 |
| Sub-total |  |  |  | 37,164 |
| 2. Personnel (staff, consultants and travel) |  |  |  |  |
| Consultant for M&E | 1 | LS | LS | 7,500 |
| Programme Manager | 1 | 1615 | 24 | 38,760 |
| Programme Assistant | 1 | 540 | 24 | 12,960 |
| Admin & Finance Assistant | 1 | 540 | 24 | 12,960 |
| National Travel | 1 | LS | LS | 7,000 |
| DSA - national staff | 1 | LS | LS | 5,000 |
| Sub-total |  |  |  | 84,180 |
| 3. Training of counterparts |  |  |  |  |
| Central level training-cum-Workshop (three days) | 1 | 15000 | LS | 15000 |
| Training at Central level (one-day ) | 1 | 2500 | 8 | 20,000 |
| Training at Central level (two-days ) | 1 | 4300 | 3 | 12,900 |
| Pilot TestTraining package at Districts level (two-days ) | 1 | 7000 | 5 | 35,000 |
| Pilot Test Training-cum-Workshop model at Districts level (Three-days) | 1 | 9000 | 5 | 45,000 |
| Sub-total |  |  |  | 127,900 |
| 4. Contracts |  |  |  |  |
| Support to develop NPA on UNSCRs 1325 and 1820 | LS | LS | LS | 40,000 |
| Equipment and staff for HLSC Secretariat | LS | LS | LS | 80,200 |
| Others (Training package, workshop model, support to women’s caucus, dissemination seminar) ) | LS | LS | LS | 90,200 |
| Sub-total |  |  |  | 210,400 |
| 5. Other direct costs |  |  |  |  |
| Office rent | 1 | 500 | 24 | 12,000 |
| Office utilities (communication, electricity, etc.) | 1 | 500 | 24 | 12,000 |
| Security cost |  |  |  | 7,010 |
| Sub-total |  |  |  | 31,010 |
| Total Programme Costs |  |  |  | 490,654 |
| Indirect Support Costs (7% of total programme cost) |  |  |  | 34,346 |
| TOTAL |  |  |  | 525,000 |
| Contribution from UNIFEM for developing NPA on UNSCR 1325 and 1820 |  |  |  | 70,000 |
| TOTAL PROJECT COST |  |  |  | 595,000 |

Annex 2.5

Detailed Work Plan for 24 Months

| Outcome/Output | Activities | Inputs | Budget | Delivery Date |
| --- | --- | --- | --- | --- |
| Outcome1: State entities create enabling institutional environments to promote and protect women’s human rights in line with UNSCRs 1325 and 1820, and other human rights instruments especially CEDAW. |
| Output1.1: Enhanced capacity of HLSC to successfully implement its mandate. | 1.1.1 Conduct project introductory workshop with central level stakeholders |  | 2,500 | March 2010 |
|  | 1.1.2Hold consultations with HLSC members to assess support needs. | Staff’s and partners’ time, consultants, resource persons | 2,000 | April 2010 |
|  | 1.1.3 Provide orientation to HLSC members on the elements of UNSCRs 1325 and 1820. |  | 3,500 | April 2010 |
|  | 1.1.4 Support HLSC in developing the NPA on UNSCRs 1325 and 1820. |  | 40,000 | April-June 2010 |
|  | 1.1.5 Support HLSC to hold workshop on the key elements of NPA on UNSCRs 1325 and 1820 with decision making officials of sectoral ministries and the ministries’ roles and responsibilities in its implementation. |  | 2,500 | August –October 2010 |
|  | 1.1.6 Support HLSC to hold workshop on the key elements of NPA on UNSCRs 1325 and 1820 with civil society and media and their roles and responsibilities in its implementation |  | 3,000 | September-November 2010 |
|  | 1.1.7 Integrating the experiences of activities 1.1.5 & 1.1.6, prepare training package for district stakeholders to be involved in the implementation of NPA on UNSCRs 1325 and 1820. |  | 10,000 | January-March 2011 |
|  | 1.1.8Pilot-test the training package in 5 selected districts and refine the training package for replication |  | 40,000 | April-June 2011 |
|  | 1.1.9 Provide technical assistance to HLSC to prepare and submit periodic report to UN on implementation status of UNSCRs 1325 and 1820. |  | 2,400 | November-December 2010 & 2011 |
|  | 1.1.10 Equipment, furniture and other amenities for effective functioning of the HLSC Secretariat. |  | 22,400 | March-April 2010 |
|  | 1.1.11 human resources (1 project Secretary and Project Officer) for smooth functioning of the HLSC Secretariat |  | 50,400 | March-April 2010 |
|  | 1.1.12 Logistic support for meetings of HLSC on UNSCRs 1325 and 1820. | Staff’s time | 5,000 | As per the decision of HLSC in 2010 & 2011 |
| Output 1.2: Enhanced understanding of concerned government authorities on UNSCR 1325, 1820 and CEDAW for mainstreaming of women’s rights in government programmes and policies. | 1.2.1 Train the staff of MOPR, MWCSW and MOFA on CEDAW, UNSCRs 1325 and 1820 and mediation skills. | Staff’s and partners’ time, consultants, resource persons | 8,600 | April-May 2010 & March-April 2011 |
|  | 1.2.2 Provide technical support to MOPR for preparing gender-responsive policies and programmes. |  | 4,500 | Ongoing through 2010 & 2011 |
|  | 1.2.3 Provide equipment support to NWC for compilation and processing of M & E information | Staff’s time | 12,500 | September-October 2010 |
|  | 1.2.4 Provide the services of Information Management Expert to design and implement information management system for tracking the implementation of UNSCRs 1325 and 1820 | Staff’s and partners’ time, consultants, resource persons | 6,000 | March-May 2011 |
|  | 1.2.5 Provide training to NWC staff and its partners on M&E mechanisms, information collection and processing techniques for monitoring the implementation of UNSCRs 1325 and 1820 |  | 4,300 | May-June 2011 |
|  | 1.2.6 Provide orientation to peace and gender focal points of sectoral government ministries on the objectives and scope of NPA on UNSCRs 1325 and 1820 and their roles and responsibilities in its implementation |  | 5,000 | September-November 2010 |
|  | 1.2.7 Organ e training-cum- workshops for planning focal points of sectoral government ministries on integrating the activities of NPA on UNSCRs 1325 and 1820 in their regular programmes as per their roles and responsibilities in its implementation |  | 15,000 | January-March 2011 |
|  | 1.2.8 Integrating the experiences of activity 1.2.7,develop workshop model for district level line agencies of sectoral ministries for integrating the activities of NPA on UNSCRs 1325 and 1820 in their regular programmes |  | 10,000 | April-June 2011 |
|  | 1.2.9 Pilot-test the workshop model in 5 selected districts and refine the model for replication |  | 45,000 | July-September 2011 |
|  | 1.2.10 Support women’s caucus in CA in holding orientation and advocacy consultations to ensure political commitment to implementation of UNSCRs 1325 and 1820 |  | 25,000 | July 2010-June 2011 |
| Management Activities |
|  | PMU meetings | Staff’s time | 0 | Quarterly from March 2010 |
|  | Recruitment of project staff | Staff’s time | 0 | March-April 2010 |
|  | Procurement of vehicle, equipment and furniture | Staff’s time | 29,364 | March-April 2010 |
|  | Monitoring and reporting | Staff’s and partners’ time; fund for workshops, travel and DSA | 4,000 | Ongoing and 6-monthly from August 2010 |
|  | Conduct internal midterm self assessment |  | 7,000 | February-March 2011 |
|  | Prepare and submit project completion report | Staff’s and partners’ time; Consultants | 5000 | November-December 2011 |
|  | Final evaluation | Consultants | 12,000 | December 2011-January 2012 |
|  | Workshops/seminars to disseminate lessons and best practices resulted from the project | Staff’s and partners’ time; consultants, fund for workshops, travel and DSA | 22,600 | February 2012 |
|  | Personnel and other operational costs |  | 91,090 |  |
|  | Administrative support (7%) |  | 34,346 |  |
| Grand Total |  |  | 525,000 |  |

| Dates | 6 Month Benchmarks | Indicators of Progress |
| --- | --- | --- |
| First 6 Months | Initiate preparatory activities such as recruitment of project staff; procurement of equipment and furniture.. Design training programmes based on training need assessment ofconcerned stakeholders with specific focus on women’s rights and gender equality, especially UNSCRs 1325 and 1820 and NPA on the same. Technical support to MOPR for preparing gender responsive policies and programmes Equipment, furniture, other amenities and human resources for effective functioning of the HLSC | Project team in place 4 types of training programmes designed for of central level stakeholders based on training need assessment. 2 training events completed for central level stakeholders The secretariat of HLSC equipped with necessary amenities and human resources The NPA on UNSCRs 1325 and 1820 developed |
| Second 6 Months | Conduct trainings for central level stakeholders on NPA on UNSCRs 1325 and 1820 Prepare and submit to UN annual report on implementation of UNSCRs 1325 and 1820 Conduct internal midterm self assessment | 3 central level training completed Annual report on implementation of UNSCRs 1325 and 1820 submitted Assessment report prepared |
| Third 6 months | Conduct trainings for central level stakeholders on key elements of NPA on UNSCRs 1325 and 1820, mediation skills and M&E mechanism. Disseminate IEC materials on relating to NPA on UNSCRs 1325 & 1820 Technical support to MOPR for preparing gender responsive policies and programmes. prepare training package for district stakeholders to be involved in the implementation of NPA on UNSCRs 1325 and 1820 Pilot-test the training package in 5 selected districts and refine the training package for replication Organize training-cum-workshops for planning focal points of sectoral government ministries on integrating the activities of NPA on UNSCRs 1325 and 1820 in their regular programmes develop workshop model for district level line agencies of sectoral ministries for integrating the activities of NPA on UNSCRs 1325 and 1820 in their regular programmes | 2 central level training completed training package for district stakeholders developed training package pilot tested and refined training-cum-workshops conducted for planning focal points of sectoral government ministries workshop model developed for integrating the activities of NPA in regular programmes of line agencies |
| Fourth 6 months | Pilot-test the workshop model in selected districts and refine the model for replication Prepare and submit to UN annual report on implementation of UNSCRs 1325 and 1820 Prepare and submit to UNPFN the project completion report Prepare project completion report Undertake final evaluation | workshop model pilot tested and refined Annual report on implementation of UNSCRs 1325 and 1820 submitted Project completion report submitted Final evaluation report prepared and disseminated |

Annex 2.6

# UNPFN

# Project Summary

| Participating UN Organization: | UNIFEM and OHCHR | UN Fund cluster and/or Nepal PBF Priority area: | 2.8 Strengthening State Capacity for Sustaining Peace |
| --- | --- | --- | --- |
| Implementing partner(s): | MOPR, MOFA, MWCSW and Civil Society |
| Project number: |  |
| Project title: | Partnership for Equality and Capacity Enhancement (PEACE): Towards Implementation of UNSCRs 1325 and 1820 |
| Total approved project budget: | US $ 525,000 |
| Location: | National level |
| Executive Committee approval date: | 11 March 2010 |
| Project duration: | 24 months | Starting date: | 1 April 2010 | Completion date: | 31 March 2012 |
| Project’s Strategic Outcome: | Capacity enhancement of national institution to promote women’s participation in peace process and protect the rights of women affected by conflict in line with UNSCRs 1325 and 1820. |
| Project description: | Support the capacity enhancement of the government and civil society at the central level for effective implementation of UNSCRs 1325 and 1820 and thereby contribute to the promotion of women’s participation in peace processes and protection of the rights of women affected by conflict. This will eventually contribute to consolidation of peace in Nepal. |
| Peacebuilding Impact: | Contribute to consolidation of peace in Nepal through facilitating the implementation of national commitments to gender equality and women’s human rights. |
| Project Outcome(s): | State entities create enabling institutional environments to promote and protect women’s human rights in line with UNSCRs 1325 and 1820, and other human rights instruments especially CEDAW. |
| Outputs and key activities: | Enhanced capacity of HLSC to successfully implement its mandate (Orientation to HLSC on UNSCRs 1325 and 1820; developing the NPA on UNSCRs 1325 and 1820; supporting HLSC in reporting on UNSCRs 1325 and 1820; strengthening HLSC Secretariat). Enhanced understanding of concerned government authorities on UNSCR 1325, 1820 and CEDAW for mainstreaming of women’s rights in government programmes and policies (train the key government ministries’ staff on CEDAW and UNSCRs 1325 and 1820; mainstreaming gender in policies and programmes of MOPR; assist NWC in strengthening the monitoring mechanism; and orientation for civil society on NPA on UNSCRs 1325 and 1820). |
| Indicator and benchmarks: | Change in levels of understanding among HLSC members on implementation of UNSCRs 1325 and 1820 over time. Timely submission of annual report to UN on implementation of UNSCRs 1325 and 1820 Training package for district stakeholders focusing on NPA on UNSCRs 1325 and 1820 developed, pilot tested and endorsed by PCC and HLSC Workshop model for integrating the activities of NPA on UNSCRs 1325 and 1820 into the regular programmes of district line agencies developed, pilot tested and endorsed by PCC and HLSC |
| Procurement: |  |

Abbreviations

| CA | Constituent Assembly |
| --- | --- |
| CEDAW | Convention on the Elimination of all Forms of Discrimination Against Women |
| CPA | Comprehensive Peace Accord |
| CPN-M | Communist Party of Nepal-Maoist |
| CSO | Civil Society Organisation |
| GRB | Gender Responsive Budget |
| HLSC | High Level Steering Committee |
| IEC | Information, Education and Communication |
| INSEC | Informal Sector Service Centre |
| LOA | Letter of Agreement |
| LPC | Local Peace Committee |
| M&E | Monitoring and Evaluation |
| MLD | Ministry of Local Development |
| MOD | Ministry of Defence |
| MOF | Ministry of Finance |
| MOFA | Ministry of Foreign Affairs |
| MOLTM | Ministry of Labour and Transport Management |
| MOPR | Ministry of Peace and Reconstruction |
| MOU | Memorandum of Understanding |
| MWCSW | Ministry of Women, Children and Social Welfare |
| NPA | National Plan of Action |
| NWC | National Women’s Commission |
| OHCHR | Office of the High Commissioner for Human Rights |
| PCC | Project Coordination Committee |
| PEACE | Partnership for Equality and Capacity Enhancement |
| PMU | Project Management Unit |
| PSWG | Peace Support Working Group |
| SARO | South Asia Regional Office |
| SGBV | Sexual and Gender Based Violence |
| TJ | Transitional Justice |
| TRC | Truth and Reconciliation Commission |
| UNDAF | United Nations Development Assistance Framework |
| UNDSS | United Nations Department of Safety and Security |
| UNIFEM | United Nations Development Fund for Women |
| UNPFN | United Nations Peace Fund for Nepal |
| UNSCR | United Nations Security Council Resolution |

# Footnotes

Reviewing the Implementation of UNSCRs 1325 and 1820: what will it Take? “Women in the land of conflict”, Conference, Voksenaasen, Oslo, Nov 2008. Charles Abugre.

The Committee is chaired by the Honorable Deputy Prime Minister and Minister of Foreign Affairs with the Minister for Peace and Reconstruction as Co-Chair and the Minister for Women, Children and Social Welfare as member. Other members of the Committee include the Secretaries from MOFA, MOPR, MWCSW, MOD and MOHA, and representatives from women’s organizations and development partners.

http://www.peace.gov.np/admin/doc/LPC-ToR-Eng-%202065-10-20.pdf

India Forward Moving Strategies for Gender Equality 2008, Adopted at Commemorating Beijing, Sixth South Asia Regional Ministerial Conference, 17-19 January 2008, New Delhi, India

This project concept was discussed in detail with Secretary, Joint Secretary, and other key officials of MOPR, MOFA, MWCSW, and the Advisor of Foreign Minister. This proposal has been developed in consultation with them along with other stakeholders.

Building gender justice in democratic governance in stable and fragile states, UNIFEM Thematic Strategy: Governance, Peace and Security 2008 – 2011

The UNSCRs 1888 and 1889 will be taken into account in the preparation and the implementation of the NPA on UNSCRs 1325 and 1820.

Management and operational costs not included.

For this joint programme, it has been agreed between UNIFEM and OHCHR-Nepal that the funds will be solely handled by UNIFEM. OHCHR-Nepal shall only provide technical assistance for the implementation and evaluation as requested. Therefore, agency wise break-down of budget may not be applicable.

As per the work plan of MOPR, NPA will be finalized by June 2010.