EIGHTH Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| ## Participating UN Organization: (if joint programme, indicate the lead agency) |  | ## Old Cluster: Cluster B – Education and Culture |
| --- | --- | --- |
| UNHABITAT & UNICEF (lead agency) |  | New Sector: Education Sector Outcome Team |

| ## Project No. and Project Title: |  | ## Report Number: |
| --- | --- | --- |
| B1-22 (a &b) School Rehabilitation and Capacity Building for School Maintenance |  | 4 |

| ## Reporting Period: |  | ## Project Budget [and revision if applicable]: |
| --- | --- | --- |
| 1 January – 30 June 2008 |  | UNDG ITF: US$15,660,938 UNICEF: US$ 9,029,120 UN-HABITAT: US$ 6,631,818 |

| ## List Implementing Partners: |  | ## Geographic Coverage/Scope: |
| --- | --- | --- |
| - UNICEF - UN-HABITAT - Ministry of Education/ Directorates of Education and Local Contractors |  | Babil, Baghdad, Diyala, Dohuk, Erbil, Kerbala, Kirkuk, Muthanna, Najaf, Ninevah, Qadissiyah, Salaheldin, Suleimaniyah, Thiqar, Missan, Basra, and Wasit |

| ## Abbreviations and Acronyms: |  | ## Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| DoEs: Directorates of Education PTA: Parent Teacher Association BoQs: Bills of Quantities MoE: Ministry of Education PM: Programme Manager PMO: Programme Management Officer HQ: Headquarters |  | Project Duration: - 24 months (16 July 2006 – 30 June 2008) Project Extensions: - One (From 31 December 2007 till 30 June 2008) |

# Purpose

a.	Provide the main objectives, outcomes, outputs of the programme/project

The main objective of the programme is to increase access to primary, intermediate and secondary education for school age children (grades 1 to 12) with emphasis on rural areas and girls’ education. Secondly, to enhance the capacity of DoEs on school maintenance, and school sanitation and hygiene promotion.

Immediate Objectives:

- Improvement of the physical environment of 160 schools in 18 governorates, including water and sanitation facilities;

- Enhance the capacity of DoEs to undertake the maintenance of schools and promote hygiene practices;

- Reduce the number of shifts and reduce the number of students in crowded classrooms by adding new classrooms;

- Building capacity of local contractors under several categories using local materials, which will contribute to improving the economical conditions of the local communities;

- Contribute to the reduction of the number of unemployed people in local remote communities.

Outputs:

- Rehabilitation of 160 schools in 18 governorates benefiting about 80,000 school age children; 70 schools by UNHABITAT in 3 Southern governorates benefiting about 35,000 school age children and youth, and 90 schools by UNICEF in 15 governorates benefiting 45,000 school age children and youth.

- 55 DoE technical staff, 160 head teachers and 320 PTA representatives of the rehabilitated schools trained on best practices in the school maintenance programme and improved sanitation and hygiene practices.

- Manual on asset management of school maintenance, and guidelines on school sanitation and hygiene practices produced.

Outcomes:

- Improved teaching and learning environment for about 80,000 students in 160 schools;

- Strengthened capacities of DoE technical staff in maintenance of school buildings, water and sanitation facilities and in hygiene promotion;

- Improved capacities of local contractors and young engineering professionals involved in rehabilitation activities;

- Enhanced employment opportunities within the local communities.

- Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq

The project is part of the reconstruction and development programmes presented in the Joint UN-Iraq Assistance Strategy 2005-2007 and implemented by the UN agencies through national partners and counterparts, and via the Cluster B approach.

- MDGs

Reference to the project main objective and immediate objectives (see above), the project plans to achieve Universal Primary Education indicated in goals 2 and 3 in the Millennium Development Goals, which aim, by 2015, to have all children in primary schools, and provide girls with the same educational opportunities as boys.

- Iraq NDS

The NDS for 2005-2007 emphasized on improving quality of life by developing required policies based on current and future needs. Achieving definite aims till 2015 requires hard efforts and developed policies in all aspects of life such as economic, social, environmental and educational. The project is in line with the NDS Goal 2, Target 4 as illustrated hereunder:

  - Goal (2): Achieve primary education for all: Everyone will have the opportunity for education and necessary skills to be able to enter world economy and have citizen rights and obligations. Educational levels are measured based on rates in the primary and postgraduate levels. According to living standards surveys, illiteracy is wide spread in Iraq; 39% in rural areas, 22% among adults who never joined school, and 9% in secondary schools; the highest educational level for them.

  - Target (4): Dialogue continues with MoE regarding a rapid assessment of the impact of insecurity on school attendance, after UNICEF voiced its concern over the increasing number of children out of school. The education sub-cluster continues to make a significant contribution to the long term goal through programmes on physical rehabilitation of schools, and provision of essential education and recreation materials.

- International Compact with Iraq (ICI)

ICI aims to strengthen their partnership to improve the lives of the Iraqi people, and to complete the reconstruction of Iraq. The project is designed to achieve the following goals:

- Invest in people and their abilities to ensure optimal contribution to the economy

- Achieve significant progress towards: i) full primary completion by 2015; ii) gender parity in education by 2015

- Human Resources

a.	National Staff & Consultants: Provide the number and role (operation/programme)

For UNHABITAT, the total number of national operations staff is 17, distributed according to the operations' needs as follows:

- Senior engineers(Amman office)				 3

- Database expert (Amman office)				 1

- Consultant engineers (Basrah Communication Base)  	 1

- Consultant engineers (Nassiriyah Communication Base) 2

- Consultant engineers (Missan Communication Base)	 4

While for UNICEF, a total of 15 persons are currently working on the project in the field, as follows:

- Civil/Construction engineers inside Iraq			 6

- Facilitators inside Iraq					 6

- National staff inside Iraq					 2

- National Officers (Engineer)  in Amman			 1

b.	International Staff: Provide the number and role (operation/programme)

The total number of international operations staff is as follows:

- Programme Manager (UNHABITAT)			 1

- Rehabilitation Expert (UNHABIBAT)			 1

- Programme Management Officer (UNHABITAT)	 1

- Rehabilitation Specialist (UNICEF) 			 1

- Education Specialist (UNICEF) 				 1

- Methods of Operating

a.	Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

National consultants of the two agencies (UNICEF and UNHABITAT), with the active participation of DoEs, carry out a detailed assessment of the facility to be rehabilitated. An assessment report is prepared based on discussions among all stakeholders to agree on priority needs. As soon as consensus is reached on the broad scope of rehabilitation works, BoQs are prepared by the consultants who set out, in precise detail, the scope of work and specifications.

BoQs and technical specifications are sent to UNHABITAT and UNICEF Offices for review by Rehabilitation Divisions. Once approved, the agencies authorize the preparation of the tender documents and invitation to bid.

The two agencies maintain a register of - now over 700 - Iraqi Contractors with different specialties. Normally, between 10 and 20 Iraqi contractors are invited to tender for each rehabilitation contract depending on the estimated amount of each contract.

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

The tender evaluation process included a system of checks and balances with a clear segregation of functions. Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate Tender Evaluation Committee. A separate technical team based in Erbil prepares the agency estimated cost for each contract, using a specifically designed database system, which generates priced BoQs using monthly updated market prices. The process occasionally based on comparison with market survey done by other UN Agencies.

For UNHABITAT contracts, which exceed US$150,000 the tender evaluation report is subject to review and approval by the Local Contracts Committee in the Headquarters / Nairobi and the UN Office in Nairobi (UNON)/ Procurement, Travel and Shipping Section. Contracts less than US$150,000 are reviewed and approved by the Programme Manager under the terms of a delegation of authority.

As for UNICEF, bidding evaluation is submitted to a Contract Review Committee (CRC) who after vetting and evaluation submits recommendations to the Special representative of UNICEF for authorization.

c.	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Rehabilitation works are supervised and monitored by Iraqi national consultants and facilitators. The progress of works monitored and approved through time-series photographs, daily briefings from the consultants, videos and telecommunication and laboratory test reports for quality control of construction materials. In addition, an initial handing over certificate is issued upon completion and receipt of the rehabilitated facility by the DoEs.

Interim payments are only released to the contractors upon the work progress and quality accepted by the Senior Engineer and the Rehabilitation Expert in the Amman office, certified by PMO and then approved by PM as a final stage before being sent to the Headquarters for processing.

Liquidated damages apply for any unjustified work delay and violation of the contract period.

During the maintenance period, constant surveillance of the implemented work is carried out by the consultants/engineers and facilitators to guarantee implementation sustainability and defect repair. This is normally enhanced by interviews with local authority staff and beneficiaries for addressing their remarks on the work and responding to any justified request before the final handing over takes place in order to ensure the public good reputation and impressions of the agency achievements. All contracts incorporate a defect liability clause so that any defects, which emerge after completion are repaired by the contractor.

Before the rehabilitated school facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the local authority, the beneficiaries, the relevant department of the Government and UNHABITAT and UNICEF staff and consultants. The final payment is not released until the Acceptance Committee certifies that all work has been satisfactorily completed.

- Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

During the reporting period UNICEF collected post implementation data from 45 schools, which indicate positive changes such as school enrolment particularly that of girls, student’s access to safe water and sanitation facilities, etc.

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

- During the reporting period, comprehensive rehabilitation of 29 schools and improvement of water and sanitation facilities in 10 schools were completed benefiting 28,111 students (45% boys and 55% girls. Rehabilitation included complete renovation of school buildings, construction of additional classrooms, improvement of water and sanitation facilities and playgrounds, and construction of surrounding walls. Completion of the mentioned 39 schools brings the total number of completed schools in this project to 167 schools out of 173 (163 comprehensive and 10 improvement of water and sanitation facilities).

| Governorate | T. no of schools | Completed | Ongoing |
| --- | --- | --- | --- |
| Baghdad | 13 | 13 | - |
| Babil | 6 | 6 | - |
| Diyala | 5 | 5 | - |
| Dohuk | 6 | 6 | - |
| Erbil | 6 | 6 | - |
| Kirkuk | 16 (6 comp + 10 WES) | 16 | - |
| Kerbala | 6 | 6 | - |
| Muthanna | 6 | 2 | 4 schools (60-90% completed). |
| Najaf | 6 | 6 | - |
| Ninevah | 6 | 4 | The 2 schools completed 50 & 80% then stopped because of explosions and insecurity. |
| Qadissiyah | 6 | 6 | - |
| Salaheldin | 6 | 6 | - |
| Suleimaniyah | 6 | 6 | - |
| Thiqar | 16 | 16 | - |
| Missan | 40 | 40 | - |
| Basra | 14 | 14 | - |
| Wasit | 9 | 9 | - |

- MOE in Baghdad and KRG prepared first draft of school maintenance manual in Arabic. The draft is being reviewed by UNICEF and UN-HABITAT technical staff and is considering bringing in a consultant to develop it further.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

- Comprehensive rehabilitation of 29 schools and improvement of water and sanitation facilities in 10 schools completed during the reporting period. 28,111 students (45% boys and 55% girls) are the beneficiaries of the Child-Friendly schools. Rehabilitation included complete renovation of school buildings, construction of additional classrooms, improvement of water and sanitation facilities and playgrounds, and construction of surrounding walls.

- Project implementation has contributed to an increase in enrolment of students and reduction of crowding in schools by adding a number of classrooms in crowded schools. The increased number of classrooms also helped headmasters in enrolling more children.

- Rehabilitation of water network and sanitation facilities ensured students’ access to safe potable drinking water and hygienic sanitation facilities and encouraged families to send their children, especially girls, to school. Data from 45 school sites (some mixed and others only for girls or boys) indicates an increase of 3 % in enrolment (from 22,720 pre-rehabilitation to 23,296). Despite the lack of specific data it is believed that access to safe drinking water and improved sanitation facilities played a positive role in the reduction of water related diseases among students and teachers.

- The survey result also indicates an increase in the number of guest schools using the newly rehabilitated schools. For example only 6 six out of 45 (sample size) targeted schools were used by guest schools in different shifts before rehabilitation with a total of 2,647 students while after rehabilitation the number of guest schools reached to 16 with 9,628 students.

- In addition to the above, it is estimated that the project has offered around 22,500 man-days employment for skilled and unskilled labourers. In addition a large number of people benefited indirectly through their involvement in transportation and loading/unloading construction materials.

- The project has so far achieved the concept of increasing local capacity and supported government strategy in targeted communities.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

A number of factors contributed to delays in project implementation such as poor security in some of areas; curfews and military operations; several religious occasions; selection of schools and approval of BoQs by education departments. Therefore the both agencies have proposed a project extension for a period of six months, which will facilitate the smooth completion of ongoing activities including release of warranty payments. The extension was approved by SCSO.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

MoE, DoEs, UNICEF and UNHABITAT: Close coordination and collaboration between UNICEF and UNIHABITAT field Engineers and DoE staff was key for project implementation. DoEs select all schools for rehabilitation and approve BoQs and payment requests. DoE technical staff was actively involved in project planning, implementation and monitoring. This has helped to ensure transparency and greater sense of responsibility and commitment as well as sustainability of the project after its completion.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

- Human Rights and Gender

The project has been successful in achieving stated objectives such as increased enrolment of students; improved attendance; improved teaching and learning space for children; improved hygiene practices in school. Particularly, provision of sanitation facilities for girls separately from boys will further enhance girls’ enrolment and completion in primary education.

- Employment

Regarding employment opportunities, as mentioned above, the project implementation has supported government efforts in creating employment opportunities in targeted communities. Over a hundred contractors were hired to facilitate and implement the project. In addition to that, it is estimated that around 22,500 man-days employment for skilled and unskilled labourers employed through the project implementation. Also, a large number of people benefited indirectly through their involvement in transportation and loading/unloading construction materials.

- Environment

The project rehabilitated or established water and sanitation facilities in each school, including sewage systems. These facilities have ensured better environments in targeted schools.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2008 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

- Complete comprehensive rehabilitation of the remaining 4 schools

- Finalize the school maintenance strategy and guideline