Ninth Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| ## Participating UN Organization: |  | ## Old Cluster: Cluster B – Education and Culture |
| --- | --- | --- |
| UNICEF (lead agency) and UNHABITAT |  | New Sector: Education Sector outcome Team |

| ## Project No. and Project Title: |  | ## Report Number: |
| --- | --- | --- |
| B1-29 (a&b): School Rehabilitation and Capacity Development for Enhanced Access and Retention in Primary Education ATLAS Project Number: 66863 ATLAS Award Number: 54863 |  | 3 |

| ## Reporting Period: |  | ## Project Budget [and revision if applicable]: |
| --- | --- | --- |
| 1 July 2008 – 31 December 2008 |  | UNDG ITF: US$ 11,325,596 UNICEF: US$ 7,312,914 UN-HABITAT: US$ 4,012,682 |

| ## List Implementing Partners: |  | ## Geographic Coverage/Scope: |
| --- | --- | --- |
| - UNICEF, UNHABITAT - Ministry of Education - Directorates of Education - Local Construction Companies |  | Muthanna, Kirkuk, Missan, Najaf, Anbar and Dohuk |

| ## Abbreviations and Acronyms: |  | ## Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| DoEs: Directorates of Education MoE: Ministry of Education PTA: Parent Teacher Association BoQs: Bills of Quantities CRC: Contract Review Committee |  | Project Duration: - 12 months (4 July 2007 – 4 July 2008). Official start date was 15 October 2007, based on MoE’s request Project Extensions: - First: 04 Jul 08 – 31 Dec 08 - Second: 31 Dec 08 - 31 Mar 09 - Third: 31 Mar 09 - 30 Jun 09 |

# Purpose

a.	Provide the main objectives, outcomes, outputs of the programme/project

The developmental goal of the project is to demonstrably improve access to and quality of primary education and intermediate levels of education, with particular focus on girls and girls’ schools and mixed schools in 200 disadvantaged rural schools throughout Iraq.

- Immediate Objectives:

- To upgrade 200 girls’ schools and mixed schools to child-friendly status;

- To create awareness among community and religious leaders on the importance of girls’ education and gender issues;

- To equip teachers with innovative teaching methods, and promote gender-sensitive attitudes;

- To equip the principals and educational supervisors with supervisory and leadership skills;

- To increase parent participation through strengthening of the Parent Teacher Associations (PTA’s);

- To include health and hygiene activities in the school curriculum.

Outcomes:

- 200 schools in five governorates equipped with appropriate furniture, learning materials, sanitary kits, playgrounds, and safe water and sanitation facilities.

- Major repair of school buildings including roofing, doors and windows, electrical works, and painting of classrooms realized.

- 200 community members sensitized on the importance of girls’ education.

- 600 teachers of the 200 selected schools trained in child-centred and gender-sensitive teaching methods and applying them in classrooms.

- Principals and educational supervisors of the 200 selected schools trained in school and classroom-based management, and leadership skills and strategies.

- Four meetings of each PTA realized at the 200 selected schools, e.g. addressing issues of safety and privacy of girls in schools and on their way to school.

- Teachers and students equipped with skills to take care of their personal health and hygiene and maintain a healthy school environment.

Outputs:

- A total of 200 schools are physically rehabilitated in five governorates.

- The 200 schools are equipped with appropriate furniture, learning materials, sanitary kits, playgrounds and safe water and sanitation facilities.

- 25 educational staff are trained on multi purpose schools.

- Principals and educational supervisors of the 200 selected schools are trained on school and classroom-based management, and leadership skills and strategies.

- Four meetings of each PTA are conducted at the 200 selected schools, e.g. addressing issues of safety and privacy of girls in schools and on their way to school.

- Teachers and students are equipped with skills to take care of their personal health and hygiene and maintain a healthy school environment

b.	Explain how the programme/project is relevant to the following benchmarks:

UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI

- UN Assistance Strategy for Iraq

The project is part of the reconstruction and development programmes presented in the Joint UN-Iraq Assistance Strategy 2005-2007 and implemented by UN agencies through national partners and counterparts and via the Cluster approach.

- MDGs

Reference to the project main objective and immediate objectives (see above), the project plans to achieve Universal Primary Education indicated in goals 2 and 3 in the MDGs, which aim, by 2015, to have all children in primary schools, and provide girls with the same educational opportunities as boys.

- NDS

The 2005-2007 NDS emphasized on improving quality of life by developing required policies based on current and future needs. Achieving definite aims till 2015 requires hard efforts and developed policies in all aspects of life such as economic, social, environmental and educational. The project is in line with NDS Goal 2, Target 4 as illustrated hereunder:

  - Goal (2): Achieve primary education for all: Everyone will have the opportunity for education and necessary skills to be able to enter world economy and have citizen rights and obligations. Educational levels are measured based on rates in the primary and postgraduate levels. According to living standards surveys, illiteracy is wide spread in Iraq; 39% in rural areas, 22% among adults who never joined school, and 9% in secondary schools; the highest educational level for them.

  - Target (4): Dialogue continues with the Ministry of Education (MoE) regarding a rapid assessment of the impact of insecurity on school attendance, after UNICEF voiced its concern over the increasing number of children out of school. The education sub-cluster continues to make a significant contribution to the long term goal through programmes on physical rehabilitation of schools, and provision of essential education and recreation materials.

- ICI

The project relates to ICI Goal 4.4.1, which focuses on delivering basic services in order to achieve the Government’s interim 2011 MDGs in an efficient and sustainable way. This will be achieved through improvement of adult literacy and school completion rates by 25%; achieving gender parity at all levels of education; and increasing the education budget from 3.5% to a minimum of 5% of GDP.

- Human Resources

a.	National Staff & Consultants: Provide the number and role (operation/programme)

For UNHABITAT, the total number of national operations staff is 17, distributed according to the operations' needs as follows:

- Senior national engineers 				 	3

- Database expert (Amman office)					1

- National staff inside Iraq (Baghdad and Erbil offices)	 	4

- Consultant engineers (Kirkuk Communication Base)	 	1

- Consultant engineers (Najaf Communication Base)	 	3

- Consultant engineers (Missan Communication Base)  	 	4

- Consultant engineers (Muthanna Communication Base) 	4

While for UNICEF, a total of 11 people are currently working on the project in the field, as follows:

- Engineers inside Iraq					 	6

- National staff inside Iraq						4

- National Officer (Engineer) in Amman			 	1

b.	International Staff: Provide the number and role (operation/programme)

The total number of international operations staff is as follows:

- Programme Manager (UNHABITAT)				 1

- Rehabilitation Expert (UNHABIBAT)				 1

- Programme Management Officer (UNHABITAT)		 1

- Rehabilitation Specialist (UNICEF)				 1

- Education Specialist (UNICEF)					 1

- Methods of Operating

a.	Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

National consultants of the two agencies (UNICEF and UNHABITAT) carry out a detailed assessment of facilities planned for rehabilitation, with the active participation of Directorates of Education (DoEs). An assessment report is prepared which forms the basis for discussion among all stakeholders to agree on priority needs. As soon as consensus is reached on the broad scope of rehabilitation works, BoQs are prepared by the consultants who set out, in precise detail, the scope of work and specifications.

BoQs and technical specifications are sent to UNHABITAT and UNICEF Offices for review by Rehabilitation Divisions. Once approved, the agencies authorize the preparation of the tender documents and invitation to bid.

The two agencies maintain a register of - now over 700 - Iraqi Contractors with different specialties. Normally, between 10 and 20 Iraqi contractors are invited to tender for each rehabilitation contract depending on the estimated amount of each contract.

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

The tender evaluation process included a system of checks and balances with a clear segregation of functions. Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate Tender Evaluation Committee. A separate technical team based in Erbil prepares the agency estimated cost for each contract, using a specifically designed database system, which generates priced BoQs using monthly updated market prices. The process is occasionally based on comparison with market surveys done by other UN Agencies.

For UNHABITAT contracts, which exceed US$150,000, the tender evaluation report is subject to review and approval by the Local Contracts Committee in the Headquarters / Nairobi and the UN Office in Nairobi (UNON)/ Procurement, Travel and Shipping Section. Contracts less than US$150,000 are reviewed and approved by the Programme Manager under the terms of a delegation of authority.

As for UNICEF, bidding evaluation is submitted to a Contract Review Committee (CRC) who after vetting and evaluation submits recommendations to the UNICEF representative for authorization.

c.	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Rehabilitation works are supervised and monitored by Iraqi national consultants and facilitators. The progress of works is monitored and approved through time-series photographs, daily briefings from the consultants, videos and telecommunication and laboratory test reports for quality control of construction materials. In addition, an initial handing over certificate is issued upon completion and receipt of the rehabilitated facility by the DoEs.

Interim payments are only released to the contractor upon acceptance of work progress and quality by the Senior Engineer and the Rehabilitation Expert at the UNICEF Iraq Support Centre in Amman (ISCA), certified and then approved by the Project Manager (PM) as a final stage before being sent to Headquarters for processing.

Liquidated damages apply for any unjustified work delay and violation of the contract period.

During the maintenance period, constant surveillance of the implemented work is carried out by the consultants/engineers and facilitators to guarantee implementation sustainability and defect repair. This is normally enhanced by interviews with local authority staff and beneficiaries for addressing their remarks on the work and responding to any justified request before the final handing over takes place. All contracts incorporate a defect liability clause so that any defects, which emerge after completion are repaired by the contractor.

Before the rehabilitated school facility is finally accepted, a final inspection is undertaken by an Acceptance Committee, which comprises representatives of the local authority, the beneficiaries, the relevant department of the Government and UNHABITAT and UNICEF staff and consultants. The final payment is not released until the Acceptance Committee certifies that all work has been satisfactorily completed.

d.	Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

No assessment, evaluation or study was conducted during the reporting period.

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries. Please also fill the table in section VI on six monthly performance indicators assessment.

Rehabilitation of 200 schools

- During the reporting period, rehabilitation works of WES facilities was completed in 136 schools (81 by UNICEF and 55 by UNHABITAT), bringing the total number of schools completed to 159 (91 by UNICEF and 68 by UNHABITAT) schools (79.5% completed). Around 85,590 students (62% girls) are benefiting from the improved school environments.

- Rehabilitation works are ongoing in 4 schools (1 by UNICEF and 3 by UNHABITAT), and 37 schools are under bidding (8 by UNICEF and 29 by UNHABITAT).

Provision of Supplies

- During the reporting period, the distribution of school furniture was commenced. As of the 31st of December 2008, 12,847 desks were distributed to 59 schools in 5 governorates.

- Other supply items will be distributed as soon as the items arrive in Iraq.

Community Mobilization for Girls’ Education

- Community mobilization will continue in 2009

Teacher Training on Child-Centred Methods

- 540 teachers, 187 headmasters and 23 educational supervisors were trained on child-centred and active learning methods.

Training on School-Based Management

- 187 headmasters and 23 supervisors were trained on school-based management.

PTA activities

- Partnership with an INGO initiated for the implementation of a pilot project for the PTA activities.

Teacher Training on School Health, Hygiene and Sanitation

- In addition to the original plan of training teachers on school health, hygiene and sanitation, the prevention of Avian Flu, HIV/AIDs and Cholera was added to the training component. 488 teachers were trained on these subjects.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

- Rehabilitation of WES facilities separate for girls improved school environments, which will encourage girls to enrol and retain in the school.

- Training of educational staff is another important component of Child-Friendly Schools. Training on school hygiene and sanitation and child-centred methods will contribute to improve quality of education in the selected schools.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

UNICEF

UNICEF cancelled one contract for rehabilitation of eight schools in Kirkuk when the progress of works had reached an average of 68%, as the contractor failed to complete the project as per the terms and conditions of the contract. Physical assessment for the evaluation of the remaining volume of work in these schools was completed and bidding took place in January 2009.

UNHABITAT

DoEs of Najaf, Kirkuk and Muthanna changed two schools when the physical assessment and bidding was completed for two schools and contract for the rehabilitation of another two schools was signed because the MoE selected these schools for rehabilitation by the Government.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

- The project has been implemented in close coordination and consultation with MoE and DoEs in Kirkuk, Najaf, Muthanna, Dohuk, Anbar and Missan. MoE and the local Education Directorates continue to be involved in all aspects of the project such as identification of schools, planning, monitoring and endorsement of all payments based on the activities completed. The continuous partnership helped to ensure transparency and greater sense of responsibility, ownership, commitment and sustainability of the project after its completion.

- Partnership was established with STEP, an INGO, which conducted the teacher training on child-centred methods in schools in the Kurdistan Region (KR).

- Partnership with the International Rescue Committee (IRC) was initiated. IRC is going to continue PTA activities. This will not only ensure optimal cost performance but also the efficient implementation of these activities, with broader views of the situation of Iraq.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

- Gender: Data from the 159 schools shows that 62% of the project beneficiaries are female students as a result of careful selection, with gender perspectives considered. Establishment/rehabilitation of separate WES facilities for girls will further encourage girls to complete their primary education.

- Employment: The project supported government efforts in creating employment opportunities inside Iraq. Provision of school furniture created around 153,000 work-days employment in support of the government employment strategy.

- Environment: School rehabilitation includes installment of water and sanitation facilities in the 200 selected schools, which ensures better environment in schools.

- Future Work Plan

  - Summarize the projected activities up to the end of June 2009 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

- Complete rehabilitation of water and sanitation facilities in 41 (9 by UNICEF and 32 by UNHABITAT) schools and handover to the relevant DoEs.

- Complete the distribution of school furniture.

- Provision of recreational kits, sanitation kits, teaching / learning materials

- PTAs were not re-activated as planned due to delays in reconstruction of schools. Therefore, the project started with a pilot project in both centre/south and KR. For the centre/south, 13 schools which had been rehabilitated by UNICEF under another ITF project (B1-32) were selected to be pilot schools in partnership with the NGO PIN, using different funding sources.

- UNICEF plans to implement this PTA pilot project in KR by using the remaining fund for PTA activities under B1-29 through IRC. IRC will establish PTAs in 10 schools in Erbil and provide technical support to the MoE for the development of PTA guidelines and training of 100 PTA members. 5000 parents and 10, 000 children will benefit from activities planned and implemented by these PTAs.

- Based on findings and lessons learned from the above mentioned 2 pilots, the PTA activities will be expanded to the 200 targeted schools under this project with different funding sources.

- Performance Indicators assessment as of 31 December 2008

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Means of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: 200 girls’ schools and mixed schools upgraded to Child-Friendly status in Missan, Muthanna, Najaf, Kirkuk and Dohuk |  |  |  |  |  |  |
| Output 1.1 200 schools in 5 governorates equipped with appropriate furniture, learning materials, sanitation kits, playground and safe water and sanitation facilities, in addition to basic repair of school premises | Indicator 1.1.1 # of schools with upgraded WES facilities | 0 | 200 | 159 | PM |  |
|  | Indicator 1.1.2 # of schools provided with furniture | 0 | 200 | 59 | PM |  |
|  | Indicator 1.1.3 # of schools provided with recreational kits | 0 | 200 | 0 | PM |  |
|  | Indicator 1.1.4 # of students provided with student kits | 0 | 60,000 | 0 | PM |  |
|  | Indicator 1.1.5 # of students provided with teacher kits | 0 | 600 | 0 | PM |  |
| Outcome 2: Awareness raised among community and religious leaders on the importance of girls’ education and gender issues |  |  |  |  |  |  |
| Output 2.1 Community and religious leaders in the selected areas mobilized to support girls’ education and parents encouraged to send their daughters to school | Indicator 2.1.1 # of communities promoting girls education | 0 | 200 | 0 | PM |  |
| Outcome 3: Teachers equipped with innovative teaching methods, child-centred learning techniques, subjects for girls and gender-sensitive attitudes |  |  |  |  |  |  |
| Output 3.1: 600 teachers of 200 selected schools trained in child-centred and gender-sensitive teaching methods and applying them in the classrooms | Indicator 3.1.1 # of teachers trained (by type) | 0 | 600 (child-centred methods) | 540 teachers, 187 headmasters, 23 supervisors (child-centred methods) | List of participants |  |
| Outcome 4: The principals and educational supervisors with supervisory and leadership skills and school and classroom-based management |  |  |  |  |  |  |
| Output 4.1 Principals of the 200 selected schools and educational supervisors trained in school and classroom-based management, and leadership skills | Indicator 4.1.1 # of ministry staff trained (by type) | 0 | 200 (school based management) | 187 (school based management) | List of participants |  |
| Outcome 5: Parents participation increased through strengthening of PTAs |  |  |  |  |  |  |
| Output 5: Four meetings of each PTA realized at the 200 selected schools, e.g. addressing issues of safety and privacy of girls in schools and on their way to school. | Indicator 5.1.1 # of schools which hold PTA meetings minimum twice a year | 0 | 200 | 0 | PM | Pilot PTA activities will be started in Erbil and Basra and the PTA activities will be expanded to the 200 targeted schools in the future, using different funding sources. |
| Outcome 6: Health and hygiene activities in the school curriculum in order to equip teachers and students with personal hygiene practices and skills to create and maintain healthy school environment. |  |  |  |  |  |  |
| Output 6.1: Teachers and students equipped with skills to take care of their personal health and hygiene and maintain a healthy school environment | Indicator 6.1.1 # of teachers trained (by type) | 0 (school health, hygiene and sanitation) | 600 (school health, hygiene and sanitation) | 488(school health, hygiene and sanitation) | List of the participants |  |