Ninth Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: |  | Old Cluster: Education and Culture |
| --- | --- | --- |
| UNICEF |  | New Sector: Education Sector Outcome Team (SOT) |

| Project No. and Project Title: B1-32: Integrated Community-Based Services in Basra ATLAS Project Number: 66865 ATLAS Award Number: 54865 |  | Report Number: 3 |
| --- | --- | --- |

| Reporting Period: |  | Project Budget [and revision if applicable]: |
| --- | --- | --- |
| 1 July 2008 – 31 December 2008 |  | US$ 1,755,155 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| UNICEF WHO Ministry of Education (MoE) in collaboration with Ministry of Health (MoH), Ministry of Municipalities and Public Works (MMPW), Mayoralty of Basra (MoB) and Ministry of Labour and Social Affairs (MoLSA) |  | Basra Central, Al Zubair, Al Qurna, and Shat Al Arab Districts in Basra Governorate |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| WHO: World Health Organization DoEs: Directorates of Education PTA: Parents and Teacher Association BoQs: Bill of Quantities ISRB: Iraq Strategic Review Board GDW: The General Directorate for Water |  | Original Project Duration: 12 months (15 October 2007 – 15 October 2008 ) Project Extensions: First (extended to 31st December 2008) Two (extended to 15th April 2009) |

# Purpose

a.	Provide the main objectives, outcomes, outputs of the programme/project

The main project goal is to improve access and quality of basic social services in disadvantaged communities through an integrated community approach. In selected communities in Basra governorate, Iraqi authorities will be able to fulfill their obligations towards vulnerable populations in terms of responding to their immediate needs for basic social services in a transparent and equitable manner in line with democratic principles and international human rights standards, contributing to the achievement of the following MDG goals: enrolling all children in primary school (MDG2), eliminating gender disparities in primary and secondary education (MDG3), reducing by half the proportion of people without access to safe drinking water (MDG7), reducing child mortality (MDG4), and poverty reduction (MDG1).

Immediate Objectives:

- Improve participation and retention as well as access to and quality of education in 13 schools in Basra Governorate;

- Improve access to potable water and sanitation services in the communities around the selected schools;

- Improve the quality of basic primary health and nutrition services in the communities around the selected schools;

- Assist parents, teachers, health workers, youth volunteers and other community members to provide psychosocial wellbeing for children.

Outputs:

- The overarching output will be to upgrade 13 schools to Child-Friendly status;

- School participation and retention as well as access of primary school children will improve;

- Availability and improved quality of water and wastewater disposal will increase;

- Sanitary facilities for school children, especially for girls will be available;

- Selected Primary Health Care (PHC)/Maternal Child Health (MCH) units will be equipped with essential vaccines, basic medicines, and medical supplies/equipment;

- Two PHC centres (PHCCs) serving the 13 local communities will be physically rehabilitated;

- The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities;

- Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities;

- Local authorities’ capacities for planning, managing and monitoring the project will be 	   strengthened, and communities will exercise ownership of the project. Parent Teacher Associations (PTAs) will be engaged in project implementation.

b.	Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI

UN Assistance Strategy for Iraq: The project is fully in line with the UN Country Team (UNCT) Strategic Cooperation with Iraq and the Joint Priority Action Plan and conforms closely to the priorities expressed by the Iraqi Authorities during the March 2007 Donors’ conference - embracing education, water and sanitation and health needs, contributing to the overall targets of reducing morbidity and mortality.

Specifically the project addresses the following clusters and matrix outcomes from the Joint UN-Iraq Assistance strategy:

| Cluster-B (Education and Culture) | To enhance access to all levels of education with special reference to disparity reduction (gender, geographic, ethnic, socio-cultural, economic and other disparities); To improve rates of retention, completion and participation at all levels of education; To improve learning outcomes at all levels of education. |
| --- | --- |
| Cluster-D (Health and Nutrition) | 50% reduction in under five and infant mortality; 15% reduction in maternal mortality; Increase access to quality health care services especially for vulnerable groups and un-reached populations; Enhance disease prevention and control including HIV/AIDS. |
| Cluster-E (Infrastructure Rehabilitation) | Availability of stable and safe drinking water and improved sanitation |

MDGs: The project contributes to the attainment of the following MDGs:

- Enrolling all children in primary school (MDG2)

- Eliminating gender disparities in primary and secondary education (MDG3)

- Reducing the proportion of people without access to safe drinking water by half (MDG7)

- Halting and reversing the incidence of malaria (MDG6)

- Reducing child mortality (MDG4)

- Poverty reduction (MDG1)

NDS Goals: The project relates to the following goals:

Goal (2): Achieve primary education for all

- “Everyone will have the opportunity for education and necessary skills to be able to enter world economy and have citizen rights and obligations.”

- Target 3: Ensure that, by 2015, children everywhere, boys and girls alike, will be able to complete a full course of primary schooling.

Goal (7.2): Eradicate Extreme Poverty and Undertake Area Based Development:

- “Diversify social protection programmes to increase effectiveness in addressing needy people at the local level, decentralize processes and involve NGOs in assisting the poor with socio-medical services”

ICI:

- The project relates to ICI Goal 4.4.1 of delivering basic services in order to achieve its interim 2011 Millennium Development Goals in an efficient and sustainable way, through improvement of adult literacy and school completion rates by 25%, achieving gender parity at all levels of education and increasing the education budget from 3.5% to a minimum of 5% of GDP;

- The project will also enable effective coordination between national and sub-national governance units on service delivery with specific regard to the function of planning and service management;

- Promote area-based development strategies which:

- Ensure service provision to the most vulnerable segments of the Iraqi population including internally displaced people (IDPs), returnees, refugees, stateless persons, the disabled and widows;

- Increase income generation opportunities at community level;

- Are gender-sensitive and responsive to the needs of youth;

- Build the planning and executive capacity of sub-national governance institutions.

- The project contributes to 4.4.1.5 of ICI Benchmarks (as per the Joint Monitoring Matrix 2008) - Reduce population without access to safe drinking water to 10% in urban areas (Baseline: UNDP Unmet Basic Needs Survey - 40.4% population without access to safe drinking water of which 20% in urban and 60.4% in rural); and also contributes to the following WatSan sector outcomes:

1: Increase sustainable access to safe water for urban and rural populations in 10 governorates, especially for the vulnerable;

2: Increase sustainable access to improved sanitation for urban and rural populations, especially for the vulnerable;

3: Capacities for effective management of WatSan enhanced.

Joint Needs Assessment:

The 2004 Iraq Living Conditions Survey (ILCS) indicates that over 70% of Basra residents do not have access to safe water. Irregularity in the supply of water affects between 4.9% and 11.1 % of households in Basra Centre and Al Qurna districts, which results in increased reliance on tankered water by the residents. Nearly 5% of family members in Al Qurna district reported having experienced diarrhoea in the two weeks preceding the survey (Food Security and Vulnerability Analysis in Iraq, COSIT/WFP/UNICEF 2005). The sanitary situation in Basra is highly inadequate as 58% of the households in Basra do not have access to improved sanitation, while another 19% reported problems with their sewer connections (ILCS, 2004).

The education sector still faces serious failures and suffers from significant shortcomings. Major deterioration in both access to and quality of education is evidenced by declines in most of the basic indicators of development, as clearly brought out in the Ministry of Education (MoE)/UNICEF school survey (2003/2004), ILCS 2004 and the Iraq NDS (2007-2010). The situation is particularly acute in the southern Iraqi governorates, and especially for girls. Figures show that gender disparities in the South are high compared to the Centre and the North, and that in rural areas 44% of children need more than 15 minutes to get to school. Distance from school is one of the major impediments to girls’ attendance, especially in rural areas. According to the Ministry of Labour and Social Affairs (MoLSA) study ‘Social Elements of the Phenomenon of Violence against Children’ (2004), anxiety has become a major psychosocial concern for the children of Iraq.

- Human Resources

  - National Staff & Consultants: Provide the number and role (operation/programme)

- National Officer WESH					one

- National Officer, Monitoring & Evaluation		one

- National Officer, Basic Services				one

- Chief Facilitator Basra					one

- Education Facilitator					one

- WESH Facilitator						one

- Child Protection Facilitator				one

- Health Facilitator						one

  - International Staff: Provide the number and role (operation/programme) .

International staff in UNICEF provided support for the design and implementation of various activities, as and when required. International WESH Specialist contributed towards the design, implementation and evaluation of WatSan training programmes.

- Methods of Operating

a.	Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

During 2008, UNICEF Iraq continued to operate from the Iraq Support Centre in Amman (ISCA) for security reasons, and to avoid any possible negative repercussions to staff and premises. However, international staff based in Amman continued to provide guidance and support to national staff and facilitators/engineers operating within Iraq. International staff missions were undertaken to Baghdad and Erbil throughout the year with increasing frequency, to ensure continued presence. This provided an opportunity for frequent interactions with Iraqi government counterparts at national and governorate levels.

Unfortunately, missions to Basra could not be undertaken specifically for this project. However, national UNICEF officers based in Basra provided necessary guidance to the facilitators to ensure the smooth implementation of the project, with periodic support from the international specialist based in Amman. A senior level technically qualified national Iraqi Chief Facilitator was specifically contracted for this project through a corporate contract. The Chief Facilitator is responsible for liaising with various departments, other partners, and the community, as well as coordinating sectoral activities on the ground on a day-to-day basis. In addition technical facilitators for WESH, Health, Education and Child Protection were hired to supervise and monitor the implementation of project activities and provide periodic reports to the respective sections in ISCA.

The ICIC Governorate team at Basra Governorate Council played a crucial part in coordinating, supervising and monitoring of activities at the local level, under the leadership of the Deputy for local Councils in the Basra Governorate Council. The team also comprises members of Directorate of Health (DoH), Directorate of Education (DoE), Water Directorate, Directorate of Labour and Social Affairs, local council representative of Al Qurna, Al Zubair and Shat Al Arab districts and selected community members.

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

UNICEF administrative and procurement procedures are in accordance with quality management practices. UNICEF has extensive global procurement facilities managed by its global supply division based in Copenhagen. The procurement of supplies/ equipment is carried out by a highly experienced Supplies and Logistics unit to ensure cost effective and timely procurement of all supplies under the project. Again, given UNICEF’s vast logistics management experience in emergency programming across the globe as well as in Iraq, UNICEF is able to ensure efficiency and speed in all logistics operations, despite the many challenges on the ground. UNICEF has been working in Iraq for more than two decades now and thus has close collaboration with many line ministries and other local partners, which will further ensure local appropriateness, acceptability and ownership. Supplies delivered are distributed through the Government, with the UNICEF contracted facilitators overseeing and securing end-use distribution. UNICEF’s stringent monitoring, tracking, supervision, and auditing mechanisms are applied throughout the supply chain management.

Rehabilitation of facilities is overseen by the Rehabilitation Unit in collaboration with the Supply, Logistics and Contracting Unit at ISCA and UNICEF staff in Basra. The selection of schools for rehabilitation is carried out in close collaboration with the DoE Basra. Detailed assessment of school facilities are conducted based on DoE priorities and assessment reports are prepared. Based on the assessment report, the team prepares Bills of Quantities (BoQs) to set out exact details of work in each school.

BoQs and technical specifications are sent to ISCA for review by the Rehabilitation Unit. After their approval, the tender documents are prepared and Iraqi contractors are invited to bid by the Contract Unit, in accordance with UNICEF’s rules and regulations for contracting. The tender evaluation process includes a system of checks and balances with a clear segregation of functions. Tenders are opened publicly by a Tender Opening Committee and evaluated by a separate Tender Evaluation Committee. A separate technical team inside Iraq prepares the agency estimated cost for each contract, using a specifically designed database system, which generates priced BoQs using monthly updated market prices. The process is occasionally based on comparison with market surveys done by other UN Agencies. Bidding evaluation is submitted to a Contract Review Committee (CRC) who after vetting and evaluation submits recommendations to the UNICEF representative for authorization.

Similarly for overseas training programmes in WatSan sector, Request for Proposals (RFP) are posted on the IRFFI website to solicit wider responses from specialist training institutes/ Agencies. A two stage evaluation process is followed with 60% weightage given to the technical offer and 40% to the financial offer. The selection is then made on the best techno-economically acceptable offer.

c. 	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

The monitoring of project activities was done through a monthly reporting system by the Facilitators. During 2008, the Facilitators system of UNICEF was redesigned and improved to incorporate standard quality reporting of project progress and inclusion of specific indicators to track project progress. School records, health facility reports, records of WatSan directorates, and routine reports and surveys were taken into account to monitor the progress of the project.

WatSan sector pre-selection tests were carried out in Iraq to select suitable candidates for the training courses. Visits were made to the training centres including interactions with the participants and faculty, for the conduct of pre-course and post-course tests, and evaluation of training programmes in the WatSan sector.

d.	Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

None

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries. Please also fill the table in section VI on six monthly performance indicators assessment.

- Rehabilitation of WatSan facilities and minor repair of buildings completed in five schools bringing the total number of completed schools to 13 as planned. The activities included rehabilitation of water networks and installation of water taps and water tanks, rehabilitation of sanitation facilities including sewage systems and construction of new toilets and minor repair of school buildings.

- Rehabilitation and renovation of Al-Qurna PHCC, was completed on 15 December 2008. The warranty payment will be made in June 2009.

- An assessment of existing Community Child Care Units (CCCUs) is currently underway, supervised by the Nutrition Research Institute (NRI) of Basra; based on identified needs new CCCUs will be established. The training package for PHCC staff on nutrition and management of malnourished children has been developed; a special software for data collection, monitoring and analysis of malnourished children will be developed for use of PHCC staff, and monitoring and supervision activities by NRI- Basra. Plans are being developed for supporting home health visitors programme to raise caregivers’ awareness of appropriate child feeding practices and promotion of breastfeeding. This activity is expected to be completed by June 2009.

- Supplies and equipment for two PHCCs in the project area have been procured; delivery and distribution to the facilities is expected to be completed in June 2009.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

| Outputs | Nature of Activities | % completion | Beneficiaries |
| --- | --- | --- | --- |
| Quality Learning and Development Sector |  |  |
| The overarching output will be to upgrade 13 schools to Child-Friendly status : 1.1 School participation and retention as well as access of primary school children will improve. | 1.1 .1 Procurement from inside Iraq and distribution of school furniture, recreational materials, school sanitation kits and garden kits to all selected schools; 1.1.2 Establishment of safe recreational areas in all the selected schools; 1.1.3 Creation of school gardens at all selected schools. | 90% Completed - distribution to schools after completion of rehabilitation work in all schools 100% for 13 schools 100% for 13 schools | 21,000 school children including 8,469 girls in 13 schools |
| 2.1 Availability and improved quality of water and wastewater disposal will increase; | 2.1.1 Training of all teachers in the selected schools in health and hygiene promotion; 2.1.2 Hygiene promotion and community awareness campaigns in select communities. | 50% completed ToT for members of local councils, municipalities and WatSan district level staff in communication & mobilization completed | 178 school teachers trained in health and hygiene promotion |
| 2.2 Sanitary facilities for school children, especially for girls will be available. | 2.2.1 Rehabilitation/ construction of water and sanitary facilities in schools where required. | 100% for 13 schools | 21,000 school children including 8,469 girls in 13 schools |
| Survival Growth and Development Sector |  |  |
| 3.1 Selected PHC/MCH units will be equipped with essential vaccines, basic medicines, and medical supplies/ equipment; 3.2 Two PHCCs serving the 13 local communities will be physically rehabilitated; | 3.1.1 Procurement and distribution of essential/basic medical supplies and equipment for PHC/MCH units; 3.2.1 Physical rehabilitation of some PHCCs if required (based on the preliminary assessment of facilities considered for this project); 3.2.2 Training of PHC health workers on basic health and nutrition services, including growth monitoring and counseling activities for parents of children suffering from malnutrition, including systematic referral of all severe cases of malnutrition to nutrition rehabilitation centres; | UNICEF Basra field office following up with local health authorities to finalize the list of supplies to be procured by UNICEF. Rehabilitation of Al-Qurna PHCC completed 70% achieved | 50,000 population under the catchments area of Al-Qurna PHC PHC Nutrition Units’ staff |
| 3.3 The quality of health and nutrition services will be enhanced through high quality training courses for 100 health workers serving the local communities. | 3.3.1 Support community health and nutrition programmes through community volunteers (former CCCUs), in order to strengthen growth monitoring, health and nutrition promotion and referral to PHCCs. This output will also be supported by the UNICEF national country programme | An assessment of existing CCCUs in Basra is currently underway, under supervision of NRI. Training of PHCC staff on nutrition and management of malnourished children has been designed (30% completed) | CCCUs’ Community volunteers in Basra DoH |
| Child Protection & Participation Sector |  |  |
| 4.1 Quality psychosocial interventions will be available in child friendly spaces to support the holistic well-being of children in 13 communities. | 4.1.1 Supporting psychosocial training for teachers, health workers, parents, youth and other community members in psychosocial intervention and care for children and youth and provide supplies for use in existing spaces (such as schools, health centres and youth centres) in establishing child friendly paces/psychosocial activities. | 74 % achieved | Officials from MoE, MoLSA and Ministry of Higher Education have been provided on-the- job training to manage the project and build a model for teacher training for supporting children with psychosocial problems. 92 school teachers (19 M and 73 F) from 5 ICIC schools in Basra were trained, and are providing psychosocial support to 2364 children (979 boys, 1385 girls) |
| 4.2 Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project. PTAs will be engaged in project implementation. | 4.2.1 Conducting capacity building courses for relevant government authorities on planning, management and monitoring of area-based programmes; | 100% completed | Training of trainers for local level participatory community-based Planning Methodology conducted for governorate level staff from DoH, DoE, MoLSA and planning staff at Governorate council. Plans for district level training of staff developed by the Governorate Council Team. |
|  | 4.2.2 Conducting social mobilization around the selected schools to activate the PTAs and get them involved in the planning, implementation and monitoring of the project to the extent possible; while at the central level advocating for government support to the expanded role of the PTAs | Scheduled for October 2008 onwards through partnership with PIN (see section V below) |  |
| Water , Environmental Sanitation and hygiene |  |  |
| Availability and improved quality of water and wastewater disposal will increase | Rehabilitation of Al Faihaa Compact Treatment Unit (200 m3/hr) in Shatt Al Arab district in Basra governorate | 10% Implementation will begin in 2009. | 32,000 people will have access to safe water post completion. |
| Local authorities’ capacities for planning, managing and monitoring the project will be strengthened, and communities are exercising ownership of the project, PTAs will be engaged in project implementation. | Provision of Laboratory Supplies and Equipment for the wastewater quality control laboratory in Basra Training in different thematic areas (water & wastewater quality monitoring; operation & maintenance of WatSan facilities; Hygiene Promotion; Implementation/ Supervision, etc.) Provision of WaterCAD and SewerCAD design software Hygiene Promotion | Overall 80 % Most of the planned supplies have been procured (85%) 8 participants from the Sewerage Authority, trained on “Operation & Maintenance of Sewers and Sewage Pumping Stations”. 2 laboratory staff from Basra trained on the “Sampling/Testing of Basic Parameters for Wastewater”. 2 laboratory staff from Basra trained on “Quality Assurance & Quality Control in Wastewater Analyses”. Another 2 laboratory staff from Basra trained on “Advanced Wastewater Quality Testing”. 4 participants from Basra trained on “Implementation/ Supervision of Water Distribution Networks”. Supplier has been selected. Contract will be issued in early 2009. (50% progress) 13 participants from Basra trained as Master Trainers on Hygiene Promotion in July 2008. 30 Water Authority Engineers participated in the two day Hygiene Awareness workshop in October 2008. Five thousand promotional notepads with messages on diarrhoea prevention and hand washing developed as part of the Global Hand washing Day. | The receipt of supplies/ equipment will enable the conduct of routing testing of wastewater benefiting a large section of Basra city. 18 Water and Sewerage Authority staff have strengthened skills in different thematic areas. Installation of WaterCAD and SewerCAD software at the training centres will especially benefit the Water and Sewerage Engineers from Basra 43 government staff have increased awareness of hygiene practices |

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

There has been a delay in the implementation of Al Faihaa Compact Treatment Unit (CU) due to the following main reasons: a) the initial plan to construct a new intake structure for the CU resulted in a cost far exceeding the available budget leading to a re-look into other possible options, b) after prolonged assessment, a cost-effective technically suitable solution was found that made use of an existing intake structure from a nearby treatment plant and c) Bills of Quantities were accordingly revised and bids were issued thereafter prolonging the implementation.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

UNICEF Iraq works in the context of harmonious UNCT interaction and coordinates closely with other UN Agencies for humanitarian and development interventions, through the established SOT mechanism. By virtue of its overall coordination roles in the Education and WatSan SOTs, and as deputy coordinator of the Health and Nutrition SOT, UNICEF plays a very active/collaborative role within the SOT system of the UN for Iraq. UNICEF also closely coordinates the implementation of its own country programme-related activities through facilitating and coordinating effective responses to localized emergencies by all concerned humanitarian actors.

UNICEF is actively collaborating with a range of partners within the Iraqi administration, the UN family and the NGO community in development and implementation of its education, health and nutrition, and WatSan programmes. UNICEF continues to enjoy very close collaboration with the ministries of Education, Health, Municipalities and Public Works, through all Directorates in the Governorates where the project is implemented. UNICEF works very closely with these partners, from the assessment of needy areas to the joint preparation of BoQs, handing over of sites to contractors, and supervision of ongoing works, to final taking over of the project from the contractor after the successful completion of the project, including the warranty period. The training programme will be designed in close consultation with the Government taking into account the current capacities of staff and relevance to the situation in Iraq. For instance, they will be involved in defining the training needs, preparing Terms of Reference for the training courses and selection of participants. It is worth mentioning that all partners are very conversant with UNICEF’s modus operandi and have benefited from multiple capacity building opportunities in the integration of WatSan, education and health sector programming.

Based on lessons learnt from the successful implementation of the Integrated Basic Services Project (B1-19), the project has been re-designed and expanded by UNICEF Iraq as Integrated Community Initiative for Children (ICIC) to ensure an increased focus on integration, community involvement and participation of local level partners, especially children. To improve coordination of activities at the local level, the ICIC Governorate Team will be established as a multi-sectoral coordinating body responsible for coordinating and overseeing the implementation and supervision of the project activities. The UNICEF Facilitator in Basra will be a member of the ICIC Governorate Team and serve as the main link between this body and UNICEF ISCA. The project envisages full partnership with local stakeholders, PTAs and school children, where feasible, to ensure efficient project implementation and sustainability of the project.

The ICIC Governorate Team in Basra, representatives of local DoE, DoH and city council, as well as other directorates are involved in project planning and implementation. They have played a major role in identification and selection of schools for rehabilitation, and development of the BoQs; their participation will ensure transparency, ownership and sustainability for the project.

Close cooperation with the government has helped in obtaining appropriate candidates for training courses, including nominations of women candidates.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Overall, the percentage of women participating in the various WatSan training programmes was 26%. Though this is less than the 50% envisaged, it is a positive step considering that the number of women involved in some areas like Operation and Maintenance is limited, and some were less inclined to travel.

- Future Work Plan

  - Summarize the projected activities up to the end of April 2009 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

- Completion of rehabilitation of an additional 4 schools (as per 2nd extension).

- Rehabilitation of Al Faihaa CU will be completed by June 2009.

- 4 participants from Basra will be trained on the use on “Laboratory Information Management System” in 2009.

- WaterCAD and SewerCAD software will be installed in the Training Centres in Basra and at the central ministry. 16 Water and Sewerage Authority Engineers will also be trained on its use in Amman.

- Impact of psychosocial training of teachers will be studied through the results of M&E activities.

- Workshop for Model Building to review the implementation of the project and outputs achieved so far, as well as recommend amendments and prepare the plan for handing handover the school-based psychosocial support to the MoE.

- Completion of training and provision of supplies for PHCCs.

- Performance Indicators assessment as of 31 December 2008

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Means of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: To promote the upgrading of 13 schools to Child-Friendly status |
| Output 1.1 | Indicator 1.1.1 | No. of schools upgraded to child-friendly status. | 13 | 17 | DoE reports/ UNICEF Facilitators report/ UNICEF records for rehabilitation & contracting units |  |
|  | Indicator 1.1.2 | No. of selected schools provided with furniture, recreational materials and sanitation kits. | 13 | 17 |  |  |
|  | Indicator 1.1.3 | No. of selected schools provided with recreational areas. | 13 | 17 |  |  |
|  | Indicator 1.1.4 | Well maintained WatSan facilities in schools. | 13 | 17 |  |  |
| Outcome 2: To improve access to WatSan services in the communities around the selected schools |
| Output 2.1 | Indicator 2.1.1 | No. of people with access to safe water | 28,000 | 0 | UNICEF Field Reports, Government records | Implementation will begin in 2009. |
|  | Indicator 2.1.2 | No. of water treatment plants rehabilitated | 1 | 0 | UNICEF Field Reports, Government records |  |
|  | Indicator 2.1.3 | Km’s of water distribution network rehabilitated | Not Applicable | Although originally anticipated at the proposal stage, these components could not be taken up due to limited funds. |
|  | Indicator 2.1.4 | Km’s of sewer networks laid |  |  |
|  | Indicator 2.1.5 | No. of sewage pumping stations rehabilitated |  |  |
|  | Indicator 2.1.6 | Quantity of chlorine distributed and used at the facilities |  |  |
|  | Indicator 2.1.7 | No. of staff (Water and Sewerage Authority) trained in different thematic areas related to WatSan Sector | 71 | 61 | Training Completion Reports, Contracts with training institutes, government records | Another 16 government staff will be trained in early 2009. |
|  | Indicator 2.1.8 | Type and no. of design aids/ advocacy documents provided | WaterCAD software SewerCAD software 5000 promotional notepads | 0 0 5,000 | UNICEF Purchase Orders, Government Receipts | Supplier has been selected. Contract will be issued in early 2009. |
|  | Indicator 2.1.9 | No. of wastewater laboratories equipped with equipment and essential supplies | 1 | 0 | UNICEF Purchase Orders, Government Receipts | 85% of the supplies/ equipment have been procured |
| Outcome 3: To assure basic health services in the communities around the selected schools |
| Output 3.1 | Indicator 3.1.1 | % of selected health facilities adequately equipped and providing improved quality services | 1 | 1 | DoH reports/ UNICEF Facilitators report/ UNICEF records for rehabilitation & contracting units |  |
|  | Indicator 3.1.2 | Vaccinations, antenatal visits coverage in the beneficiary population | Not applicable | Not applicable |  |  |
|  | Indicator 3.1.3 | % of health facilities in the selected areas covered with basic medical supplies | 2 | 2 |  |  |
|  | Indicator 3.1.4 | No. of health workers from PHC/MCH units trained on quality health and nutrition services | 260 | 40 |  | The activity is ongoing |
| Outcome 4: To assist parents, teachers, health workers, youth volunteers and other community members to provide psychosocial wellbeing for children with focus on strengthening their resiliency |
| Output 4.1 | Indicator 4.1.1 | No. of teachers, community members trained on psychosocial wellbeing for children | 320 | 145 teachers from 8 ICIC schools trained in January 2009 | Steering committee reports/ implementing partner reports/ Facilitators reports | 237 teachers from 13 ICIC schools in Basra are trained so far, around 85 from 5 schools will be trained in the coming few weeks |
|  | Indicator 4.1.2 | No. of PTAs activated in the communities | 13 | 13 PTAs being activated with support from NGO PIN | PIN and DoE reports | Activity being funded through other UNICEF resources |