Ninth Six-month progress report for project

IRFFI/UNDG IRAQ TRUST FUND (UNDG ITF)

| Participating UN Organization: WFP |  | Old Cluster: D – Health and Nutrition |
| --- | --- | --- |
|  |  | New Sector: Health and Nutrition |

| Project No. and Project Title: D2-22 Enhancing the Iraqi Institutions’ Capacity in Analyzing and Reporting Food Security and Vulnerability in Iraq |  | Report Number: ATLAS Project Number: 66903 ATLAS Award Number: 54903 |
| --- | --- | --- |

| Reporting Period: |  | Project Budget [and revision if applicable]: |
| --- | --- | --- |
| 1 July – 31 December 2008 |  | USD $1,151,317 |

| List Implementing Partners: |  | Geographic Coverage/Scope: |
| --- | --- | --- |
| Ministry of Planning and Development Cooperation (MoPDC) – COSIT & KRSO Ministry of Health (MoH) - NRI |  | All 18 governorates of Iraq |

| Abbreviations and Acronyms: |  | Project Status: Duration/ Timeline Extension/Closed Project: |
| --- | --- | --- |
| Ministry of Planning and Development Cooperation (MoPDC) Central Organisation for Statistics and Information Technology (COSIT) Kurdistan Regional Statistics Office (KRSO) World Food Programme (WFP) National Development Strategy (NDS) Millennium Development Goal (MDG) Ministry of Health (MoH) Nutrition Research Institute (NRI) |  | Project duration: March 25, 2008 – March 25, 2009 Timeline Extension: 6 months, new project end date – September 25, 2009 |

# NARRATIVE REPORT FORMAT

# Purpose

a.	Provide the main objectives, outcomes, outputs of the programme/project

Development Goal

Sustainable community based food security through informed and maintained social safety net strategy.

Immediate objectives

- Capacity of the Government of Iraq to conduct a comprehensive, nationwide survey on Food Security and Vulnerability enabled.

- An information analysis mechanism created to be used by planners and decision-makers to combat food insecurity, vulnerability and malnutrition.

b.	Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq, MDGs, Iraq NDS and ICI

The National Development Strategy (NDS) is established on 4 major pillars, the third of which is "Improving the quality of life". This requires the enactment of "a social safety net program for the poor and vulnerable".

This WFP assistance to Iraq specifically addresses this requirement of the NDS through building the capacity of the Ministry of Planning and Development Cooperation and giving them the necessary tools to build its own food safety net programme.

The results of this survey also relate directly to two of the goals outlined in the International Compact with Iraq, launched in May 2007:

- Social Safety Net – Taking care of the poor and vulnerable

- Reforming Subsidies – Phase out inefficient, large-scale subsidy programs while ensuring delivery of services to the poorest

This project identifies the locations of the most food insecure people inside Iraq.  This data is available for the Government of Iraq in fulfilling the two goals above as set out in the Compact.  The data can be used to create a social safety net, targeting the poorest with food.  The data can also be used to reform the Public Distribution System (PDS) to target only vulnerable groups, shifting from blanket coverage to targeting only the most food insecure.  Currently, the government-run PDS aims to deliver a monthly food ration to all citizens of Iraq.

This project also addresses the first Millennium Development Goal: “Eradicate extreme poverty and hunger”.  The safety net would target the most vulnerable residents for food assistance, eradicating hunger.

- Human Resources

a.	National Staff & Consultants: Provide the number and role (operation/programme)

93 national staff including 64 based inside Iraq (programme and logistics staff).  The 29 staff in Jordan and Syria are also comprised of programme and logistics staff as well as ICT, administration, finance, HR, security and drivers.

b.	International Staff: Provide the number and role (operation/programme)

14 international staff, including two senior advisors based in Baghdad and Erbil, plus 2 management, 1 finance/administration, 1 security, 3 logistics, 4 programme, 1 public information

- Methods of Operating

a.	Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

WFP is implementing this project directly with the Ministry Planning and Development Cooperation’s (MoPDC) Central Organisation for Statistics and Information Technology (COSIT) and the equivalent in the north – the Kurdistan Regional Statistics Office (KRSO), and the Ministry of Health’s Nutrition Research Institute (NRI).  Technical assistance is being provided by UNICEF and WHO.

b.	Provide details on the procurement procedures utilized and explain variances in standard procedures.

All procurement follows WFP’s standard procurement procedures.

c.	Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

This is the third survey that WFP has undertaken with the Government of Iraq.  Lessons learnt from previous surveys have been incorporated into all stages of this project.

d.	Report on any assessments, evaluations or studies undertaken relating to the project and how they were used in support of the project(s).

WFP has been working closely with the Ministry of Planning’s Central Organization for Statistics and Information Technology (COSIT) since 2003 in building their capacity in food security monitoring and analysis.  WFP has helped set up a Food Security Unit within COSIT dealing specifically with this issue.  Two comprehensive food security and vulnerability surveys were previously completed with this unit, one published in 2004 and the second in 2006.

This project supported a follow-up Comprehensive Food Security and Vulnerability Analysis for Iraq, covering nearly 26,000 households across all 115 districts of Iraq’s 18 provinces.  The results of this survey were published in November 2008.

This comprehensive survey, found that the overall food security situation inside Iraq had improved since the last survey - some 930,000 people were without adequate access to food last year, down from around four million in 2005. Moreover, there are a further 6.4 million people who would slide into food insecurity if it were not for safety nets, such as the Public Distribution System (PDS).  As well as surveying the food security situation of people across the country, the CFSVA also examined the nutritional status of 24,000 children under five. It found an improvement in national acute malnutrition rates and little change in chronic malnutrition rates. However, in five districts, stunting rates among children were described as alarming.

The full report can be found on-line at:

http://documents.wfp.org/stellent/groups/public/documents/ena/wfp192521.pdf

- Results

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries. Please also fill the table in section VI on six monthly performance indicators assessment.

| 1.2.1 Training on Food Security Analysis | Training of COSIT, KRSO, and NRI staff. | % of planned | 100% |
| --- | --- | --- | --- |
| 2.1.2 Consolidate data and publish the survey | Data consolidation is complete and the final report launched in Baghdad and Erbil in November 2008. | % of planned | 100% |

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period and explain any variance in achieved versus planned outputs and outcomes during the six month reporting period.

The two immediate objectives of this project were achieved during the reporting period:

- Capacity of the Government of Iraq to conduct a comprehensive, nationwide survey on Food Security and Vulnerability enabled.

- An information analysis mechanism created to be used by planners and decision-makers to combat food insecurity, vulnerability and malnutrition.

Data from this survey has been widely disseminated within the Government, UN, donor and civil society.  All the data has been provided to the inter-agency Information Analysis Unit, which has further disseminated the findings through its website:  www.iauiraq.org

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints and actions taken to mitigate future delays and lessons learned in the process.

This project has started quickly as there is a high level of interest from GoI counterparts.  The principal constraint was delays in the approval process of IRFFI funds.  The GoI expressed their commitment to this project in February 2007, but funds were only received in March 2008.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

This is the first time that WFP is working with the Kurdistan Regional Statistics Office (KRSO) and bringing them together with their counterpart, the Central Organisation for Statistics and Information Technology (COSIT), who WFP has been working closely with since 2003.  Developing consensus between these two bodies has been instrumental for a comprehensive, nation-wide survey.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

The Comprehensive Food Security and Vulnerability Analysis has been designed to consider cross-cutting issues such as gender and status.  Data has been disaggregated by gender, urban vs rural, IDP and employment status.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2009 indicating any major adjustments in strategies, targets or key outcomes and outputs planned.

This project was scheduled to end in March 2009, but extended for 6 months with no change in project budget to allow for operational closure.  Most activities have been completed during the current reporting period of July-December 2008.  For the remaining months, further dissemination of the survey findings will take place as well as completion of financial commitments.

- Six monthly Performance Indicators assessment

|  | Performance Indicators | Indicator Baselines | Planned Indicator Targets | Achieved Indicator Targets | Means of Verification | Comments (if any) |
| --- | --- | --- | --- | --- | --- | --- |
| IP Outcome 1 - Capacity of the Government of Iraq to conduct a comprehensive, nationwide survey on Food Security and Vulnerability enabled. |
| IP Output 1.1 Household food security, including anthropometric component, conducted and data processed. | Indicator 1.1.1 Number of households surveyed | 0 | 25,000 | 25,875 | Survey data |  |
|  | Indicator 1.1.2 Number of children measured anthropometrically | 0 | 24,000 | 24,231 | Survey data |  |
| IP Output 1.2 MoPDC and MoH analysts produced a high quality analysis showing understanding of the geographic dimensions of food insecurity, poverty and malnutrition. | Indicator 1.2.1 Consolidate data and publish the survey | 0 | 1 | 1 | Report published |  |
|  | Indicator 1.2.2 |  |  |  |  |  |
| IP Outcome 2 - An information analysis mechanism created to be used by planners and decision-makers to combat food insecurity, vulnerability and malnutrition. |
| IP Output 2.1 Improved targeting of food aid through emergency assistance and/or a reformed PDS, and enhanced staff ability to perform food security M&E and reporting. | Indicator 2.1.1 Number of COSIT, KRSO and NRI staff trained on food security concepts | 0 | 29 (trainers) + 320 (roll-out) | 29 (trainers) + 400 (roll-out) | Attendance at training sessions |  |
|  | Indicator 2.1.2 Number of COSIT, KRSO and NRI staff trained on food security analysis | 0 | 30 | 30 | Attendance at training session |  |
| IP Output 2.2 Governments plans improved to include better management of food-based programmes, recommendations and strategies including addressing malnutrition among young children and other vulnerable groups. | Indicator 2.2.1 Report published | 0 | 1 | 1 | Published report |  |
|  | Indicator 2.2.2 Survey findings disseminated | 0 | 1 press release | 1 press release |  |  |

# Text boxes

Report Formatting Instructions:

- Number all sections and paragraphs as indicated below.

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

- Attach any available photos relevant to the project.