Sixth Six-month progress report for project

# REPORT COVER PAGE

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| United Nations Environment Programme |  | Health |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| D2-08: Hazardous Waste Chemicals collection and Storage: Al Qadissiya and Al Suwaira sites |  | 4 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | 905,000 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| UNOPS Ministry of Environment |  | Al Qadissiya (20 km south of Baghdad) Al Suwaira |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| UNEP : United Nations Environmental Programme PCAU : Post Conflict Assessment Unit PCoB : Post Conflict Branch MoEN : Ministry of Environment, Iraq UNOPS : United Nations Office for Project Services DEPI : Division for International Policy Implementation (UNEP) ROWA : Regional Office for West Asia (UNEP) |  | 18th September 2006 Closure report being prepared |

Hazardous Waste Chemicals collection and Storage:

Al Qadissiya and Al Suwaira sites

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

The main objectives and outcomes as approved in the project document are:

The main objective of this project are twofold a) to put the largest pesticides warehouse complex in Iraq back into safe use (Al Suwaira) and b) to decrease immediate public health risks by removing and safely storing sodium cyanide, a highly hazardous waste chemicals from the derelict Al-Qadissiya manufacturing site, currently accessible to the public.

Key Immediate Objectives/Outcomes as formulated are:

- Cyanide and other toxic waste removed from the derelict Al Qadissiya metal treatment works site and Al Suwaira warehouses.

- On site secure storage sites designed and created for storage of hazardous waste from Al Qadissiya and Al Suwaira

- Capacity developed within the Ministry of Environment in the field of hazardous waste management and site clean up.

The outputs expected from the project are:

- The Al Suwaira pesticide warehouse complex cleaned and ready for re-use for pesticide storage.

- Toxic cyanide waste removed from Al Qadissiya and stored.

- Capacity built to coordinate and implement clean up works.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The Programme/Project contributes to the UN Assistance Strategy for Iraq in the following way:

The main objectives for environmental health issues in the UN Assistance Strategy for Iraq are formulated under the objective statements for Cluster D: Health and Nutrition.

Cluster D Objective: to re-establish basic health services while transforming centrally-planned and curative care-based services to a new system based on primary care, prevention and evidence based policy, which is equitable , of high quality , accessible and affordable.

One of the programme outcomes specified under this cluster and its core objective is to “create an enabling environment for healthy life styles” and specifically includes “environmental health issues”. This project attempts to remove a public health threat caused by public access and contamination of soil and water in the Al Qadissiya and Al Suwaira sites. While doing so, this project contributes to capacity building of the Ministry of Environment by inclusion of their staff in the clean up activities.

The Programme contributes to the following UN Millennium Development Goals (MDG):

The MDG dealing with environmental management is:

MDG: 7. Ensure Environmental Sustainability

Under this Goal the Programme focuses indirectly on:

MDG7, Target 1: Integrate the principles of sustainable development into country policies and programmes; reverse loss of environmental resources

The project contributes directly to the 2nd and 3rd Target under MDG7. Through clean up of two sites the threat to contamination of drinking water on these sites is removed and the environmental living conditions of habitants in those specific locations is improved.

MDG7, Target 2: Reduce by half the proportion of people without sustainable access to safe drinking water

MDG7, Target 3: Achieve significant improvement in lives of at least 100 million slum dwellers, by 2020

The Programme contributes to the following Iraq National Development Goals:

The National Development Strategy identifies “environment protection” as a sector under the Sector Development Programmes. The NDS targets, among others, to

- “conduct a comprehensive environmental assessment of water, air and soil conditions in Iraq, identifying sources and extent of contamination and needed remedies

This project is a result of such assessment, which was undertaken under the UNEP Capacity Building Programme. This environmental site assessment, was undertaken by the Ministry of Environment with key support and technical assistance from UNEP. During the course of the assessment phase, 5 high priority sites were identified, and the level of contamination assessed. This project was formulated to respond to this assessment, and facilitate the clean up of 2 highest priority contaminated sites.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

The key implementation partners for the project were

UNOPS- Who undertook the contracting of the project

Ministry of Environment – Who was the main national counterpart institution

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

Total budget – 905,000, details of commitment and disbursement in financial report

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

None

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

  - Indicate other funding sources, if applicable.

None

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

None

  - Project expenditures for the 1 July to 31 December 2007 period.

None

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

Work was undertaken using contractors, so no national staff employed in Iraq

National staff was employed in Amman. This included 1 professional staff and 2 G staff.

  - International Staff: Provide details on the number and type (operation/programme)

One programme manager, full time during the project implementation

Consultants as and when required

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

Referring to the stated outcomes of this project (see above), this project focused on the removal of the public health hazard posed by hazardous substances of the 2 sites. The project has completed the clean up works both at Al Suwaira and Al Qadissiya as per the Terms of Reference and removed an important public health hazard posed by mercury and cyanide. Storage facilities were constructed in which the wastes are now stored. The waste is clearly marked as dangerous and not to be touched and locked to the public.

The contractor has worked in close collaboration with the Ministry of Environment, and engaged their assigned staff in this project. Although the Ministry staff has not participated in the actual clean up, the coordination and monitoring of the works has been facilitated by the MoEN.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

Standard UN procurement practices were used to identify the contractor. Initial round of bidding resulted in bids above available funds so a second round of bid was conducted.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Due to the prevaililing security situation, field monitoring was not possible. Verification was done based on reports and photographs provided by the contractor.

  - Report on any assessments, evaluations or studies undertaken.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

Al Suwaira Site:

Pesticide residues from the Al Qadissiya warehouse were collected in plastic bags, and stored in sealed drums. The drums have been labelled indicating the contents: Toxic, environmentally hazardous, not to be touched, and flammable. The drums were numbered serially. Samples taken from each drum carry also the same serial number. A total of 149 barrels were filled as follows:

Table: Material Collected at Al Suwaira Site

| Item | Serial No. | Contents | No. of Drums |
| --- | --- | --- | --- |
| 1 | 1 – 90 | Hazardous waste such as soil, dust, birds shit mixed with chlorophenyl mercury | 90 |
| 2 | 91 – 117 | Chlorophenyl mercury | 27 |
| 3 | 118 – 148 | Calcium cyanide | 31 |
| 4 | 149 | Seeds | 1 |
| Total | 149 |

The drums were stored at the end of the ware house, and enclosed by a warning tape.

After collecting the pesticide residues, the warehouse was cleaned in the following manner;

- The ceiling was thoroughly cleaned, hovered, and washed with water jetting

- Damages on the walls were repaired, and holes were closed. The windows and doors were also repaired. The walls were cleaned, hovered and washed by water jetting. .

- The pesticides were collected off the floor, and the floor cleaned thoroughly, and hovered, before the cleaning the walls and ceiling. It underwent the same process after the cleaning of the walls and ceiling. Then it was washed and polished by special concrete polishing machine, which shaved off the upper layer, and  removed stains and colors from the surface of the concrete floor.

- After the ware house was cleaned it was washed with a warm soap solution, and a  hypochlorite  solution, then cleaned, and washed again to reach a satisfactory state.

- The manholes in the floor were thoroughly cleaned, and new covers were installed.

- The outside of the warehouse was cleaned, and washed.

The project objectives have been achieved.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

All project activities were completed. Only finalisation and close out is pending.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

There were initial delays due to contracting and later due to security. However the project is now fully implemented.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Security:

This project has been designed and reformulated during the formulation process to incorporate security concerns related to initially foreseen transport of hazardous chemicals. All risk imposing factors were carefully addressed. The contractor has also ensured to work closely together with local employees, who are capable to assess the risk situation on a day to day basis.

Gender:

Clean up works were only undertaken by men assigned in the communities of Al Suwaira and Al Qadissiya. This project does not have a specific gender dimension.

Human Rights:

This project contributes to the right to a clean and healthy living environment.

Employment:

Created no jobs short term /long term.

This project has provided short term employment (2 months) opportunities to 176 people. 70 Iraqi staff, headed by 2 engineers, worked at the Al Suwaira site, and 106 staff headed by 2 engineers worked at the Al Qadissiya site

- Future Work Plan

  - Summarize the projected activities up to the end of June 2007.

There is no further work planned. A close out and final evaluation is pending.