Sierra Leone MDTF

Fund Signature Page

(Note:  this page is attached to the programme document)

| Participating UN Organisation(s): UNFPA |  | Priority Area: JV: Rural Community Empowerment AFC: Chapter Eighteen –Democracy and Good Governance Chapter Ten- Growing the Private Sector |
| --- | --- | --- |
| Programme Manager, Participating UN Organization: UNFPA Name: Isatu Kajue Address: UNFPA,7b Sharon street, Wilberforce Telephone: +232.76805654 E-mail: kajue@unfpa.org |  | Implementing Partner(s): Ministry of Social Welfare, Gender and Children’s Affairs (MSWGCA), Decentralization Secretariat (Local Councils) and Traditional and Religious Leaders Name: N/A (Direct Execution) Address: N/A Telephone: N/A E-mail: N/A |
| Project Number: Joint Vision Programme Eighteen (ID 75580) |  | Programme Duration: 5 months Estimated Start-Up Date: July 2010 |
| Project Title: Community Empowerment to reduce Gender-based Violence and Maternal Health Complication. |  | Programme Location: Nation-wide |
| Project Description: Scaling up community stakeholders’ active involvement , particularly male involvement in the prevention and management of GBV and MMR |  | Total Project Cost: US$ 158,400 SL- MDTF: US$ 158,400 Government Input: 0 Other: 0 GRAND TOTAL: US$ 158,400 |
| Development Goal and Key Outcomes: Developmental Goal: Improve the capacity community stakeholders,, particularly traditional birth attendants and key male partners in the prevention of GBV and MMR in the rural communities Outcome 1: Enhanced reduction in GBV Maternal Health Complications occurrences Outcome 2: Male involvement in the Prevention and Management of GBV and MMR enhanced |  |  |
| Deliverables: - Traditional Births Attendants trained in effective monitoring and sensitization on HIV and AIDS , GBV and Maternal complications prevention - Community mobilization groups against GBV and Maternal Deaths established. - Communities capacities enhanced to record and report GBV cases to appropriate authorities |  |  |

|  | Signature |  | Date |  | Name/Title |
| --- | --- | --- | --- | --- | --- |
| UNFPA |  |  |  |  | Ms. Ratidzai Ndlovu Country Representative |
| DEPAC Co-Chair |  |  |  |  | Honorable Dr. Samura Kamara Minister of Finance and Economic Development |
| DEPAC Co-Chair |  |  |  |  | Mr. Engilbert Gudmundsson Country Manager World Bank |
| DEPAC Co-Chair |  |  |  |  | Mr. Michael von der Schulenburg Executive Representative of the Secretary General of the United Nations |

Project Document

- Executive Summary:

The Government of Sierra Leone continues to demonstrate their commitment to the promotion of Gender Equality. The government currently launched the National Gender Strategic Plan. One of the main priorities of this plan is Rural Community Empowerment, particularly on programmes and initiatives meant to empower rural women. This is based on the realities that rural women and young people remain to be deprived of the basic resources meant for all citizens in their respective localities. The Convention on the Elimination of All forms of Discrimination against Women (CEDAW) is very strong on ensuring that rural women enjoy their basic human rights.

There was a  reintroduction of Local Government in Sierra Leone, which provides an opportunity for inclusion and participation of the rural communities to take ownership and responsibilities of their development, and empowering the most marginalized groups to be more proactive in the decision making process. This was made legitimate by the Local Government Act of 2004, which ushered in decentralization in February 2004 after almost 30 years of centralized government.

The main aim of UNFPA’s contribution to this programme is to support the Government in ensuring rural development and empowerment and building the capacities of the respective stakeholders involved in the decentralization process.

- Situation analysis:

The Health and Social support related services in Sierra Leone are limited in addressing GBV related issues. The Traditional Births Attendants (TBAs) have been very active in engaging the communities but limited in technical capacity on how to monitor and support the communities on the prevention and management of GBV and Maternal Mortality related complications.

National response

The GoSL has recently launched the National Gender Strategic Plan. There is in existence an active National Gender-based Violence Committee, which provides a coordination role for all GBV related responses in the country. Plans are also place to draft a National Action Plan on the Prevention and Management of GBV.

Geographical coverage: Countrywide

The project implementation would be nation-wide with specific emphasis on the 7 districts of Operations: Port Loko, Bombali, Kenema, Western Area, Bo, Tonkolili, and Moyamba.

Beneficiaries: Traditional and Community Leaders,   and UNFPA’s Gender Implementing Partners.

- Institutional targeting and selection of beneficiaries:

TBAs are currently still active in deliveries but with limited capacities in relating GBV realities to Sexual Reproductive Health Rights. They would be specifically targeted to support the policy makers and implementer on GBV Prevention and Management. Male involvement is also very crucial in the successes of GBV and MMR Prevention and Management. The male engagement would be promoted.

- Strategies

The Government, development partners and NGOs are currently embarking on community mobilization meant to primarily engage the communities on issues of GBV. The intervention is also meant to enhance community ownership of the interventions related to GBV prevention and management, including supporting legal redress.

- Results framework

Joint Vision framework and benchmark

As part of the Joint Vision programme 18 UNFPA will contribute to the strengthening of capacities of the rural communities in the prevention of GBV and Maternal deaths.

Outcomes

Outcome 1:  Enhanced reduction in GBV Maternal Health Complications occurrences

Outcome 2:  Male involvement in the Prevention and Management of GBV and Maternal Mortality Reduction enhanced

Deliverables

- Traditional Births Attendants trained in effective monitoring and sensitization on HIV and AIDS,  GBV and Maternal complications prevention

- Community mobilization groups against GBV and Maternal Deaths established.

- Communities capacities enhanced to record and report GBV cases to appropriate authorities

Core activities:

- Training of Traditional Births Attendants in effective monitoring and sensitization on GBV, HIV Prevention and Maternal complications.

- Support conscientization of men on the positive implications of their involvement in the community prevention and monitoring of GBV related matters.

- Facilitate community mobilization around GBV related issues

- Management and coordination arrangement

UNFPA and MSWGCA will be responsible for the training and integration of GBV and Sexual Reproductive Health in the communities.

- Fund management arrangements

UNFPA will be the recipient of the funds and will support implementation through the Ministry of Social Welfare, Gender and Children’s Affairs and also Decentralization Secretariat (the local councils).

- Monitoring, evaluation and reporting

Project monitoring and reporting will be done as per the UNFPA M&E framework.

The impact of this project will be assessed as part of the Joint Vision programme 18 at the end of the project. However, quarterly reports on the project’s delivery will be issued as part of the MDTF reporting requirements.

Elements of the logical framework

| Results chain | Performance indicators |
| --- | --- |
| Joint Vision Priority Area: Rural Community Empowerment |  |
| JOINT VISION BENCHMARK |  |
| 1. Rural areas which have access to community growth centers that can provide basic communication services including internet where possible that would: a. Give farmers basic information about markets, prices, weather conditions, etc. b. Provide farmers with basic training in agricultural practices such as agro processing, zero waste technologies, entrepreneurship, accountancy, the management of livestock, forests, and fisheries, as well as broader livelihood skills such as literacy, health and nutrition d. Give access to TV programs, including educational programs and entertainment channels | 1. % of rural population that perceive they have greater access to information relating to livelihoods and opportunity to participate in decision making 5. # of PLHIV who actively participate in political and decision making processes in rural communities 6. # of people with increased income-generation through |
| OUTCOME |  |
| Outcome 1: Enhanced reduction in GBV Maternal Health Complications occurrences | Percentage Reduction of GBV Incidences and Maternal Deaths and complications |
| Outcome 2: Male involvement in the Prevention and Management of GBV and MMR enhanced | No. initiatives led by Men on GBV and MMR Prevention and reporting for action |
| DELIVERABLE |  |
| - Traditional Births Attendants trained in effective monitoring and sensitization on HIV and AIDS , GBV and Maternal complications prevention. - Community mobilization groups against GBV and Maternal Deaths established. - Communities capacities enhanced to record and report GBV cases to appropriate authorities | No of TBAs trained and functioning appropriately in GBV and MMR related programmes within the communities No of community mobilization established and functional No. GBV cases reported by the communities to the appropriate Authorities |

- Legal Context or Basis of Relationship

Signatory to the Joint Vision as the UN’s contribution to the GoSL Agenda for Change.

- Workplan and budget

Workplan

| Activity | Months of Year 2010 |  |  |  |  | Responsible |
| --- | --- | --- | --- | --- | --- | --- |
|  | July | Aug. | Sept. | Oct. | Nov. |  |
| Train 500 Traditional Births Attendants in effective monitoring and sensitization on GBV, HIV Prevention and Maternal complications |  |  |  |  |  | UNJV Programme Focal Person |
| Sensitize monthly 1000 men on the positive implications of their involvement in the community prevention and monitoring of GBV related matters |  |  |  |  |  | UNJV Programme Focal Person |
| Organize monthly community mobilization around GBV related issues |  |  |  |  |  | UNJV Programme Focal Person |
| Monitoring of project implementation |  |  |  |  |  | UNJV Programme Focal Person |
| Reporting |  |  |  |  |  | UNJV Programme Focal Person |

Budget (USD)

| Line # | Line description | Amount |
| --- | --- | --- |
| 1 | Train 500 Traditional Births Attendants | 40,000 |
| 2 | Sensitization of TBAs on GBV, HIV Prevention and Maternal complications | 37,000 |
| 3 | Monthly sensitization cost for 1000 men | 30,312 |
| 4 | Monthly community mobilization costs | 30,000 |
| 5 | Monitoring of project implementation | 10,000 |
| 6 |  |  |
|  | Sub-Total (Project Cost) | 147,312 |
| 6 | Indirect Costs (7%) | 11,088 |
| 7 | Total Received Funds (this project) | 158,400 |

The term “programme” is used for projects, programmes and joint programmes.