FOURTH Six-month progress report for project

Strengthening immunization services in Iraq

| Participating UN Organization: |  | Cluster: |
| --- | --- | --- |
| UNICEF |  | D – Health and Nutrition |

| Project No. and Project Title: |  | Report Number: |
| --- | --- | --- |
| D2-06: Strengthening immunization services in Iraq |  | 4 |

| Reporting Period: |  | Project Budget: |
| --- | --- | --- |
| 1 January - 30 June 2007 |  | US $7,900,000 |

| List Implementing Partners: |  | Project Coverage/Scope: |
| --- | --- | --- |
| Ministry of Health (MoH), the Directorates of Health (DoH), UN agencies and NGOs |  | National coverage |

| Abbreviations and acronyms: |  | Project Duration/Closed Project: |
| --- | --- | --- |
| MoH: Ministry of Health DoH: Directorate of Health PNIDs: Polio National Immunization Days EPI: Expanded Programme on Immunization MMR: Measles, Mumps and Rubella PHCCs: Primary Health Care Centres |  | Programme/project duration: from July 2005 to 31st March 2007. All funds ($ 7,900,000) have been fully utilized. The project has been operationally closed since 31st March 2007. |

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project:

- The main objective of this project is to contribute (by the end of 2006) to reducing infant mortality rates from 101/1000 in 1998 to 51/1000 and under-five mortality from 126/1000 in 1998 to 63/1000.

- The key immediate objectives are to ensure that by the end of 2006 poliovirus free status is maintained throughout the country, the number of measles cases are reduced by 90% compared to previous years and ensure that the coverage of all infants by essential vaccines at national level is 90%.

- The overall expected outcomes for the project by end 2006 were to strengthen immunization services through the provision of cold chain equipment, incinerators for medical waste management at PHCC level, and provision of urgently needed vaccines, syringes, needles/safety boxes and other immunisation related supplies for routine as well as accelerated/disease control activities, such as PNIDs and MMR campaign. Following the fire at the national vaccine store in 2006, which led to a substantial reduction in the national capacity to store vaccines, MoH requested to use part of the cold chain equipment/resources to rehabilitate a national vaccine store. This was added to expected outcomes for 2006. In addition, in the 2nd half of 2006 the expected outcome - incinerators for medical waste management at PHCC level was amended following a government request and subsequent UNDG budget adjustment approval, to transportation contract for vaccination teams during November/December 2006 PNIDs. During the reporting period the set outcome was to ensure that the EPI cold chain system in Iraq is strengthened through procurement and distribution of cold chain equipments and safety boxes.

- The following were the expected Outputs for the project planned during the reporting period January – June 2007:

  - EPI cold chain system in Iraq strengthened through provision of required cold chain equipments including refrigerators/freezers, spare parts and related accessories, and delivery to various parts of Iraq.

  - Proper disposal of syringes used for vaccination ensured through the supply of required safety boxes to cover annual needs for the entire country.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The project is fully in line with the UNDG strategic framework for health (cluster D), assisting MoH in improving quality and access, and sustaining vital basic social services for children and women, contributing to infant and under-five mortality reduction.

The objectives are set against the background of the Iraqi National Development Strategy (NDS), the Millennium Development Goals (MDGs), particularly Goals 4, 5 and 6 as well as indirectly contributing to Goal 1.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency: MoH is the main government partner implementing this project. It is fully in charge of management, implementation of the overall project through the Directorates of Health (DoHs) in the governorates. All provided support is coordinated with WHO through the UN Health Cluster, who provides overall technical as well as some financial support for routine and accelerated activities. In addition, coordination is ensured through the Health Working Group led by MoH.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed: In July 2005, US$ 7.9 million were allocated to UNICEF by ITF for this project for Strengthening Immunisation Services in Iraq.  By the end of 2006 US$ 7.55 million were already disbursed and spent, as a result only $353,288.66 was rolled over to 2007 and by 31st March 2007 the entire amount of $ 353,288.66 was committed and fully utilized.

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s): The amount projected was utilized as planned as there were no variations from the initial earmarked budget during the reporting period.

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures: During the reporting period funds were spent on procurement of supplies – cold chain equipments for EPI and its related spare parts as indicated in section 4.3 below.

  - Indicate other funding sources, if applicable:  A total amount of $1.2 million from other ITF and non-ITF projects were committed and utilized to support activities aiming at strengthening immunization services in Iraq.

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable: There was no revision of the budget as well as new submissions to UNDG ITF during the reporting period as funds were fully utilized according to the planned activities.

  - Project expenditures for the 1 July to 31 December 2007 period: as indicated above, the remaining balance of $353,688.66 from the total project budget which was rolled in 2007 was fully utilized by 31st March 2007, therefore there are no more expenditures expected from this project for the stated period. However, immunization will continue to be supported from ongoing projects utilizing funds from others sources (both ITF and non-ITF funds).

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme): 4 national staff (2 based in Amman and 2 based in Erbil) which include 2 National officers and 2 Programme Assistants. In addition, UNICEF has contracted a total of 5 facilitators and 2 engineers who are responsible for overseeing the implementation at governorate and district level in various parts of the country in collaboration with MoH and DoH staff.

  - International Staff: Provide details on the number and type (operation/programme): 2 international staff based in Amman. The chief of health and nutrition (L-5) and a UNV (L-2 – Health and Nutrition) are responsible for providing technical support to the immunization services as well as other health and nutrition interventions in collaboration with national staff.

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context: MoH is the main government partner with the primary responsibility for implementing this project. It is fully in charge of management, implementation of the overall project through the DoHs in the governorates and PHCCs at lower levels. In close coordination with MoH and the UN Health Cluster partners, UNICEF Project officers, backed up by contracted facilitators based in Baghdad and in other governorates as well National Officers in Erbil and Basra are all responsible for overseeing project implementation, ensuring procurement and timely delivery of required supplies. The monitoring activities for this project include field visits as well as regular meetings with DoHs staff in all governorates, and the preparation of periodic reports. UNICEF staff in Erbil, Baghdad and Amman, in coordination with MoH, prepare and finalise all technical and financial reports. In addition, all provided support is coordinated with WHO through the UN Health Cluster, whereby WHO provides overall technical as well as some financial support for routine and accelerated activities.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures: UNICEF has a well established procurement procedure. Procurement is usually done through the UNICEF Supply Division in Copenhagen based on a long-established international competitive bidding procedure and delivered to Baghdad under international insurance coverage. A UNICEF-contracted facilitator usually verifies the receipt of the supplies at the MoH/EPI Warehouse in Baghdad. In some occasions, and based on a request by MoH, UNICEF assists with distribution (through a separate contract) of these equipment/supplies to governorates/DoH level. UNICEF-contracted monitors, through their regular monitoring visits, will confirm distribution of these supplies to end-user locations, i.e. health facilities, and report on their use.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project: the monitoring system in place is usually through the MoH/DoH/PHCC on the government side, which is complemented by UNICEF contracted facilitators who in collaboration with MoH/DoH staff carry out regular visits to various facilities to oversee the implementation and collect data relevant for monitoring the progress in the implementation of EPI activities. Another mechanism is through the review of reports compiled by PHCCs, DoHs and MoH on immunization coverage and other information related to EPI. In collaboration with WHO and other cluster D members, regular discussion meetings within the cluster as well as MoH EPI officials are held on how to incorporate lessons learned to ensure effectiveness and improve delivery of immunization services.

  - Report on any assessments, evaluations or studies undertaken: through the use of other sources of funds UNICEF supported MoH to carry out a household EPI coverage survey starting with three northern governorates in the third week of June 2007. The main purpose of the household EPI survey was to provide recent data on immunization coverage for all antigens in the three Kurdistan Region governorates; to identify reasons for not immunizing children and to monitor the April/May 2007 MMR campaign coverage and the impact of the mobile outreach immunization teams. The results of the survey, which are expected in September 2007, will produce key recommendations on strategies and interventions that will enhance the achievement and sustainability of the EPI programme.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period: The Trust Fund significantly contributed to the sustainability of basic immunization services targeting 4.8 million children under five and over 1 million pregnant women (as well as all women of child bearing age, which require TT vaccination),  through provision of cold chain equipment including refrigerators/freezers, spares parts and accessories as well as safety boxes, which altogether contributed to strengthening the EPI cold chain system throughout the country. Due to increased insecurity in areas such as Baghdad most governorates/DoHs are unable to go to Baghdad to collect their share of vaccines. As a result, MoH requested UNICEF to assist in decentralizing the vaccine stores through rehabilitation/establishment of three regional vaccine stores in Erbil, Basra and Babil through the use of other sources of funds. Therefore some of the cold chain equipments purchased under this project will be distributed to these decentralized vaccine stores.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period: delivery of essential equipments for EPI services especially the cold chain equipments, refrigerators and safety boxes have strengthened the immunization services in most of the governorates especially taking into consideration that most governorates are unable to access the central vaccine store in Baghdad due to insecurity. Provision of these equipments to DoH, districts and PHCCs have increased their vaccine storage capacity and sustaining the cold chain system. This has enabled most governorates to sustain high immunization coverage rates (at least 80% and higher for DPT3) and have maintained polio free status, in addition to helping avoid major disease outbreaks during the first six months of 2007. In addition, some of the equipments were used to support the MMR campaign which was carried out nationally in April/May 2007, reaching more than 92% of the targeted 3.9 million children.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries: During the six month period a total amount of $ 353,288.66 was committed and utilized (100%) to support the following activities:

- Cold chain equipments and spare parts for a total value of $ 211,692.87 were procured and delivered in Baghdad.

- Various types of refrigerators and freezers for strengthening the cold chain system in Iraq were procured. A total of 213 refrigerators and freezers ($ 176,595.79) were procured and delivered to Baghdad and are currently being distributed to various parts of the country together with other cold chain equipments mentioned above. Some of these equipments will be installed in the three regional stores in Babil, Erbil and Basra, which have been upgraded under UNICEF support to ensure easy access by other governorates to vaccines and other related supplies.

- 150,000 safety boxes ($ 101,960) were procured and delivered to Baghdad in May 2007. These will be used for the collection of nearly 15 million used AD syringes for safe disposal and it is estimated that this quantity will cover the annual needs for 2007. Some of these safety boxes were used during the MMR campaign which was carried out throughout the country for the period 22nd April to 10th May 2007.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays:

- Insecurity and military operations remain paramount issues impeding programme implementation. Mothers/caregivers are reluctant to go to health facilities for preventive essential health services (immunization, maternal and child health care, antenatal care etc.) and go only when the child is critically ill. There are also incidences of health staff being kidnapping. Decentralization of vaccines will help in one way or another to accelerate the implementation of EPI services through strengthening of EPI cold chain systems throughout the country.

- High turnover of Senior/Middle level Managers at MoH and DoH level negatively affected programme implementation. Special efforts are required to build-up relationships with newly appointed managers and build their capacity to effectively manage UN assisted programmes.

- Recurrent costs for immunization and other basic health services remain a major challenge. Nevertheless, building on the budget provisions made in 2005 for all vaccines for routine EPI by MoH, UNICEF is intensifying its advocacy efforts to ensure the sustainability and self-sufficiency for all health and nutrition related activities. Starting from 2006 MoH established a budget line for procurement of all syringes and needles for the immunization programme.

- UNICEF has been unable to provide required technical support to MoH in certain technical fields inside Iraq as the local expertise to lead this process is lacking. Remote technical support/guidance is not always as effective as needed and in many occasions MoH is unable to send their staff outside Iraq for training.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results: The cluster approach adopted in 2004 has fostered close cooperation with other Agencies (in particular WHO, WFP, IOM, UNFPA, UNIDO, FAO, UNDP and NGOs). UNICEF is deputizing WHO in the health cluster (Cluster D) and actively participates in the work of the cluster. Coordination with WHO specifically contributed to the progress of this project.  In addition to the support provided by WHO to the surveillance of preventable diseases, their contribution to the planning, implementation, monitoring of PNIDs in spring and fall of 2006 was very valuable. UNICEF actively collaborates with WHO, to benefit from its technical expertise and comparative advantage to ensure the best possible synergy of actions on the ground. WHO supports all EPI target disease surveillance, including:

- Advocacy meetings for clinicians at the rate of three meeting/province/year;

- Incentive for conducting weekly active surveillance in all hospitals for acute flaccid paralysis cases (AFP) and other EPI target diseases, with special emphasis on neonatal tetanus and measles;

- Laboratory surveillance, physical rehabilitation of the polio laboratory, building a measles and rubella laboratory and provision of all equipments.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment: The project addressed gender equalities by providing EPI support to all children, as increased access to immunization services is a basic human right for all children.  Routine immunization monitoring does not include gender disaggregated data, but all related coverage assessments/surveys always provide data on services disaggregated by gender. The project was also aiming (for the first time) through the provision of incinerators/safety boxes and establishing the related disposal system, to contribute to a long term positive impact on the environment. Although provision of incinerators was not possible, provision of safety boxes contributed to the protection of environment and the establishment of the disposal system; capacity building activities will be undertaken using other UNICEF available resources in 2007 starting with 3 northern governorates.

- Future Work Plan

  - Summarize the projected activities up to the end of December 2007: As indicated earlier, funds from this project were fully utilized by 31st March 2007. However, immunization activities will continue to be supported utilizing other sources of funds as follows:

- Support MoH to carry out two rounds of PNIDs in September and October, targeting nearly 4.8 million children under five. UNICEF will provide support for social mobilisation, distribution of vaccines, registry books and transportation of vaccination teams.

- To ensure that districts with low immunization coverage have improved their coverage for up to 80% and above, UNICEF in collaboration with WHO will support MoH to implement the RED approach through the implementation of micro-plans for RED approach in the south-central governorates: UNICEF will provide support for capacity building as well logistic support to ensure that vaccination teams reach all areas with low immunization coverage.

- Delivery of supplies: cold chain equipments, safety boxes to MoH and DoH warehouses.

- Support mobile health teams for immunization outreach services particularly in IDP affected areas to ensure that all young children are fully immunized according to schedule.

- Continue with the work for rehabilitating/upgrading the regional vaccine stores in Erbil, Basra and Babil.