|  | UNITED NATIONS DEVELOPMENT GROUP |  |
| --- | --- | --- |
| UNITED NATIONS INDUSTRIAL DEVELOPMENT ORGANIZATION |  | FOOD AND AGRICULTURE ORGANIZATION OF THE UNITED NATIONS |

Six month PROJECT progress report (JANuary – JUNE 2007)

# Project Summary

| Participating UN Organisation: |  | Cluster: A |
| --- | --- | --- |
| United Nations Industrial Development Organization (UNIDO) – Lead Executing Agency Food and Agriculture Organization of the UN (FAO) – Collaborating Agency |  | Agriculture, food security, environment and natural resources management. |

| Project No. and Project Title: |  | Project Location/Region/Province: |
| --- | --- | --- |
| A5 – 17: Community Livelihoods and Micro-Industry Support Project in rural and urban areas of North Iraq |  | Selected Urban, Rural areas within Sulaimaniyah and Erbil Governorates. |

| Reporting Period: |  | Report no: |
| --- | --- | --- |
| 1 January to June 2007 |  | 2 |

| Counterpart organisations/implementing partners: |  | Project cost: USD 6,300,116 UNDG ITF: USD 5,800,116 Govt. Input: USD 500,000 (in kind) Total: USD 6,300,116 |
| --- | --- | --- |
| MOA – Ministry of Agriculture and Ministry of industry of Kurdistan regional government |  |  |
| Abbreviations and acronyms: |  | Project Duration: |
|  |  | 18 months |

# I. Purpose

1.1 Main objectives and outcomes expected as per approved project/Programme/ project document:

Main Objectives Support the local communities in the establishment of a variety of viable auxiliary income-generating activities in the food-processing sector and other cottage agro-industries, thereby strengthening their household economy so they can contribute to their well being on their own. Raise technology and production levels in targeted communities by providing the poor and marginalized communities the means to process their agricultural products. Improve the technical and business management skills of people in the project area especially the women, youth and the IDP’s, through appropriate training in the food processing, construction, manufacturing or service sectors. Outputs A more capable local community addressing not only their priorities but also facilitating their on-going participation in their development process. 15 model business associations in food processing centres and other cottage agro-industries established and linked with markets. Increased small-scale farmers’, IDP’s and returnees’ income through expanded basic agro-industrial production/productivity. A minimum of 2,000 households benefiting directly from improved technologies for post-harvest activities. A minimum of 600 young people provided with marketable skills to enable them to obtain jobs and/or start-up an economic activity to sustain livelihoods for themselves and their families. Main activities Assessing the needs of project beneficiaries (using selected participatory appraisal tools). Identifying viable productive income-generation activities, selection of appropriate technologies and associated skills. Selecting project sites in cooperation with stakeholders - based on the distribution of vulnerable groups in both urban and rural areas, availability of raw materials and market opportunities. Finalising selection and identification of beneficiaries based on criteria agreed upon by all stakeholders: local governments, women’s associations, directorates of counterpart ministries, village elders and Project Steering Committee (PSC). Rehabilitation of vocational training centres (infrastructure, supply of training equipment, training of trainers and development of curricula in the selected technologies/industries). Procurement of equipment for the project beneficiaries, model cottage and micro-industries; and installation of these equipments. Training of beneficiaries in entrepreneurial and management skills and technology to start their own business or to improve their employment opportunities. Mentoring of the beneficiaries , and providing ongoing support to entrepreneurs. Continuously monitor the project activities and corrective measures.

1.2 Reference to how the programme/project relates to the UN Assistance Strategy to Iraq 2005/5 and how it aims to support international and national development goals (revised National Development Strategy Dead Sea July 2005) including the Millennium Development Goals and other goals as pertinent:

The project addresses both the National Development Strategy (NDS) and the UN assistance strategy with respect to employment creation, sustainable food production and increase of incomes of vulnerable groups in rural and urban areas. The project will directly contribute to the attainment of the MDG's in Iraq, namely: Goal 1: “Eradicate extreme poverty and hunger” through its activities promoting income-generating activities and employment; and Goal 3: “Promote gender equality and empower women” through the association of women in all project activities and decision-making. The project will also indirectly contribute to other Goals (2, 4, 5 and 7) through its capacity building/training interventions and improvement of the food security situation.

1.3 Main international and national implementing partners involved, their specific roles and responsibilities in project implementation and their interaction with the agency:

This project is jointly implemented by UNIDO and FAO. This collaboration offers the opportunity for both UN agencies to pool their complementary expertise for the attainment of the project objectives. It promotes interagency collaboration between UN agencies in line with the ongoing UN reform. This project is second of its kind, developed and implemented jointly with FAO and UNIDO upon the request of the counterpart ministries and project beneficiaries based on the successful project being implemented in southern Iraq (Thiqar Governorate). The project is being implemented through a Project Management Unit located temporarily in Amman, and where the Project Chief Technical Adviser (CTA) is based and from Erbil through a National Project Coordinator (NPC). At the Headquarters of the two Agencies, project managers are assigned to coordinate the overall planning and implementation of the project. Partners from the Government of Iraq are the MOA MOI, and the Regional Government of Kurdistan. Each Ministry has appointed focal points for this project to follow-up on its activities and achievements. Furthermore, a Project Steering Committee (PSC) was established, composed of representatives from MOA, MOI, the Regional Government of Kurdistan, UNIDO and FAO. The PSC has an advisory and coordination role on the strategic and planning issues and implementation modalities. This will ensure transparency and promote ownership of the project among all the stakeholders. In addition to the CTA, the NPC and the focal points of the different ministries, the project recruits national and international short-term consultants for specific technical activities. The project also cooperates with local vocational training institutes for specialized training and development of training manuals. To overcome the problem of security which impedes the presence of international staff in the field and travel of government experts and national consultants to Amman and in the region, the project has a telephone and video conference facility to facilitate communication between the field, Amman and HQ of the two agencies.

# II. Resources

Total approved budget and summary of resources available to the programme/project from the UNDG Iraq Trust Fund and non-Trust Fund resources where applicable:

Total approved budget : 5,800,116 USD from the UNDG-ITF Total project expenditure as at 30th June 2007, 1,446,879.03 (24.95 %) The Government contributes USD 500,000, in kind, including a building with the size of 90 m x 40 m to serve as a vocational training centre for the project.

III.  RESULTS

3.1 Output Status Table

The output status table reports the extent to which the project is progressing towards the achievement/realization of the expected project outputs.

| Activities/Outputs | Description | Status | Reflections/Comments |
| --- | --- | --- | --- |
| Inception Report/Work plan | Report prepared at the beginning of the project to: Provide an overview of project activities Outline a plan of action Obtain agreement from stakeholders | Completed | The preparation of the Inception Report /Work-plan have been an essential factor in supporting project start-up |
| Base Line Study | The base line study (Needs Assessment) included findings, analysis and recommendations on: natural resources offering potential for value added through transfer of new technologies and skills; technologies needing upgrading for job creation and improved quality of production; marketing strategies; training curricula for beneficiaries; prevalence of capacity building infrastructure and absorptive capacity of communities; identification of vulnerable groups as identified by the project; collection and analysis of baseline information that will enable the project to measure achievements in terms of making a difference in the lives of identified vulnerable groups and project contribution to the revitalisation of the economy of the KRG. | Completed | This study formed the basis for implementation of the project approach. |
| Cottage Industry Vocational Training Centres | Construction and equipping of vocational training centres for food and non-food training and entrepreneurship skills development. Major project activities, including, Training of Beneficiaries and Mentoring activities are developed and implemented from this important project component. It also ensures the sustainability of project processes, outputs and outcomes. | On-going | Erbil Training Centre: preparation of detailed design, BOQ and supervision contracted; detailed design and BOQ prepared. Tender document for the construction of the training centre under preparation. |
| Training of Trainers (in technology and entrepreneurship | The project envisages training a total of about 50 trainers in food and non-food technologies and entrepreneurship skills. These trainers form major strategy for ensuring institutional sustainability. Activities involved include: identification of training providers, formulation of TORs for training providers, development of criteria for selection of trainees, and evaluation of trainees and training providers. | On-going The project has so far trained a total of 44 trainers. Food processing: (28) 4 in dairy processing 8 food safety and dairy and hygiene 10 Fruits and Vegetables processing 6 in beekeeping Non-food technologies: (16) 2 in carpet weaving 5 in textile/garment production 4 in agro/auto-mechanic 3 in machine tools (lathe) 2 in welding Training of 4 Trainers in Business Management and Entrepreneurship is in progress, in Amman, Jordan. The training started on July 29 ending the 13th of August 2007. | Training for trainers in food technologies and beekeeping and honey processing were provided in Amman, Jordan while carpet weaving was provided in Spain. Further training of trainers in olive oil processing and carpentry/joinery is planned for the next planning period. |
| Selection of Vulnerable Group Beneficiaries | Identification of vulnerable groups is conducted on the basis of the criteria established in the object document and adopted by the Project Steering Committee. | Completed | 1485 individuals have been identified across Erbil and Suleimaniyah governorates. 637 in 12 districts and 848 in 11 districts in Suleiymaniyah and Erbil governorates respectively. These individual beneficiaries will be provided with training in food processing and non-food technologies identified by the study on Needs Assessment. |
| Identification of Cottage Industries, Activities, and Processes | Selection of cottage industries for support and upgrading were based upon the assessment of the availability of raw materials and accessibility of markets. | Completed | This activity was conducted based on the key findings and recommendations established in the Needs Assessment – Baseline study. Activities identified include: (Food – Burghul, beekeeping, dairy, fruit and vegetable processing, olive oil extraction; Non-Food – Agro/Auto mechanic, welding, woodwork, machine-shop, carpet, tailoring) |
| Procurement of appropriate technology | The project provides plants and machinery for the Erbil Vocational Training Centre and in-kind business start-up support for significant number of trained beneficiaries and identified small scale cottage enterprises that serve as community training centres. The latter provide apprenticeship services for community members in identified technologies in order to revitalize essential services and create employment within communities. | Overall, about 50% of procurement has been processed and the first arrival expected in July/August 2007. | Non-food: Metalwork, Woodwork, Machine Shop, Tractor Mechanics motor mechanics - tenders evaluated, Food Technologies: Fruit & Vegetable, Honey, Olive Oil and Miscellaneous machinery and equipment. |
| Development of Training Material for Training of Trainers (ToT) and Training of Beneficiaries (TOBs) | The project will adapt the tested training material used by the Thi-Qar project. | On-going | Reviewed and used for the contingency training programme organized in the Industrial Institute of Technical Education in Erbil. |
| Training of Beneficiaries | Individual beneficiaries selected in accordance with the criteria established in the project document and the baseline study is provided with food and non-food technologies. Training will largely be provided in the Erbil Vocational Training Centre but the project will also support small scale enterprises to contribute to training individuals from within communities they provide essential services. | Contingency Beneficiary Training Programme In collaboration with the Industrial Institute of technical education in Erbil, the project developed a training programme for beneficiaries in non-food technologies in order to gain time until the completion of the construction of the Erbil training centre. Under this programme, a total of 72 beneficiaries were trained in Welding (38) and auto and agro-mechanics (34). | This programme was initiated to serve as a stop-gap measure to gain time until the Erbil Vocational Training Centre is established and fully operational. The first round of this programme is under evaluation to decide on whether or not the programme met expectations and continuing for more rounds is justifiable. |

3.2. Implementation constraints, lessons learned from addressing these and knowledge gained from assessments, evaluations and studies that have taken place during the reporting period:

Security which hampers the free movement of international and national staff and consultants poses some difficulties to effectively implement project activities. The members of the project steering committee and counterpart ministries are following up the project implementation through their involvement in endorsing equipment specifications; vetting nominations of trainers; endorsing tender evaluation reports and providing input in the development of work plans. Their continuous involvement is ensures the relevance of project responses to the needs of beneficiaries. The project will benefit from the lessons learned and good practices established in the implementation of project "Promotion of Cottage Industry in Rural and Urban Areas" in Thi Qar Governorate. Past experience of FAO in northern Iraq contributes to improved project implementation.

3.3. Key partnerships and inter-agency collaboration, impact on results:

The strategic partnership and collaboration between FAO and UNIDO has helped the project to pool the expertise of both agencies in the inception, development, and implementation of this multi-pronged approach. The joint implementation arrangements with clear roles and responsibilities of FAO and UNIDO have enhanced efficiency in the delivery of project objectives. At the operational level, sharing costs using common facilities at field offices improves effective utilisation of project funds.

3.4. Highlights and cross cutting issues pertinent to the results being reported on, e.g. gender disaggregation, policy engagement and participation of the public:

Women Beneficiaries: The project’s main objective is to increase household income for rural and urban poor. Women constitute substantial proportion of the poor. It is estimated that approx. 50% of the beneficiaries will be women (women-headed households, widows, IDPs). Women will be encouraged to participate in project activities and in the leadership positions in production groups and association established by the project Environment: Technologies and work processes are designed to have minimal impact on the environment. The project will promote technologies that do not adversely affect the environment of the targeted project areas. Technologies employed are relevant, appropriate, and environmentally sustainable. Social/Trust Building in Conflict Areas: The village elders, community leaders, district and sub-district officials, mayors of cities and the beneficiaries through their associations have been participating in the selection of beneficiaries, identifying the location and kind of income generating activities they want to embark on. Ensuring stakeholders to actively participate in such key decisions enhances the trust and partnership between project partners, which is essential in the implementation of the project.

# IV. Future Work Plan

4.1 Priority actions planned for the subsequent reporting period to overcome constraints, build on achievements and partnerships, and use the lessons learned during the previous period:

Construction of the Erbil Training Centre: The priority activity for the next planning period (July to December 2007) will be the completion of the construction of the training centre. Establishing the centre i.e. building, equipping, and staffing the centre with trainers is one of the key project components, both in terms of providing training and mentoring programmes for beneficiaries and micro-enterprises during the project life but more importantly, ensuring sustainability of project achievements. Training of Trainers: Given the number of beneficiaries identified for food technologies the project may need to revise whether there is a need to provide more advanced training in some of identified subjects. Also, the project has developed business management and entrepreneurial training with Amman based training providers, IMI-WAEDAT. All on-going 3 UNIDO-FAO projects (Thi-Qar, North Iraq, and Diwaniyah) addressing job creation through technology transfer and institutional and individual capacity building at the community level will benefit from this TOT programme. The programme will run in July/August 2007. Training of Beneficiaries: On the basis of the outcome of the evaluation process on the first round Contingency Programme implemented in Erbil and Suleymaniyah (currently in progress), the project plans to continue training beneficiaries in non-food technologies under the auspices of the Technical Industrial Schools. Further, beneficiaries in food technologies will be trained using household tools and equipment in suitable centres across districts and villages where appropriate, benefiting from experience gained in Thi-Qar project. Specific plan will be drawn in July in time for the arrival of pertinent equipment and tools. The contingency programme was initiated in order to help the project make up for lost time pending the completion of the construction of the Erbil training centre. Micro-Enterprises and business associations: Encourage and support existing micro-enterprises and businesses associations who serve communities with the provision of critical service. Moreover, promote the rationale for the formation of business associations among trained beneficiaries and provide training in business management and entrepreneurship development in cooperation with established entities, including regional Chamber of Commerce and Specialised Trade and/or professional associations. Completion of Procurement: Finalise specifications and initiate the procurement of the remaining equipment and machinery in the next few months in time for the start of operations of the Erbil Training Centre and also make it possible for the distribution of equipment to both beneficiaries and micro enterprises and business associations.

4.2 Indication of major adjustments in the strategies, targets or key outcomes and outputs:

The project has developed and implemented a Contingency Training of Beneficiaries programme to gain time pending the construction and equipping of the Erbil Vocational Training Centre.

4.3 Estimated Budget required (including any major funding shortfalls): No additional budge required at this stage.