Sierra Leone MDTF

Fund Signature Page

(Note:  this page is attached to the programme document)

| Participating UN Organisation(s): UNIDO |  | Priority Area: JV: Community Empowerment and Integration. AFC: Chapter seven – Human Development |
| --- | --- | --- |
| Programme Manager, Participating UN Organization: UNIDO Name: Stephen Bainous Kargbo Address: UNIDO Freetown Telephone: +232.76.912.509 E-mail: s.kargbo@unido.org |  | Implementing Partner(s): Ministry of Trade and Industry, Ministry of Energy and Water Resources Name: Mr. Mickail Turay Address: Ministry of Trade and Industry (UNIDO focal point) Telephone: N/A E-mail: N/A |
| Project Number: Joint Vision Programme Eighteen (ID 75579) |  | Programme Duration: Six Months Estimated Start-Up Date: July 2010 |
| Project Title: Solar Powered Business Information and Communication (BIC) Platforms |  | Programme Location: Binkolo, Bo, Koindu, Kpadembu, Pujehun and Newton |
| Project Description: Support the establishment of Business Information and Communication (BIC) platforms in the premises of each of the five growth centres. |  | Total Project Cost: USD 158,400 [SL- MDTF]: USD 158,400 Government Input: 0 Other: 0 GRAND TOTAL: USD 158,400 |
| Development Goal and Key Outcomes: Contribute to local economic development by providing access to global information on job opportunities, commodity prices, adaptable technologies and entrepreneurial knowledge and skills Promote non-formal education and acquisition of life skills by youth and community leaders through multimedia campaigns/programmes on gender, HIV/AIDS, conflict management, etc. Strengthen social cohesion and participation through positive entertainment activities, face-to-face and/virtual engagement and communication among various stakeholders. |
| Deliverables: 18.5.1 Communication hubs established and integrated into growth/community production centres in each rural district 18.5.2 Each hub provides access to the internet (and to satellite TV), market and other technical information; pay phone and/or money transfer services; non-formal education and entertainment services 18.5.3 Each hub connected to a national Youth Platform; a web-based tool to enhance networking, participation, information/knowledge sharing, and to generate ideas and recommendations amongst youth and between community members and other stakeholders or leaders. 18.5.4 Renewable energy supply systems (e.g. solar) installed for each communication hub as autonomous green energy units/business models. |

|  | Signature |  | Date |  | Name/Title |
| --- | --- | --- | --- | --- | --- |
| UNIDO |  |  |  |  |  |
| DEPAC Co-Chair |  |  |  |  | Honorable Doctor Samura Kamara, Minister of Finance and Economic Development |
| DEPAC Co-Chair |  |  |  |  | Mr. Engilbert Gudmundsson Country Manager World Bank |
| DEPAC Co-Chair |  |  |  |  | Mr. Michael von der Schulenburg Executive Representative of the Secretary General of the United Nations |

Project Document

Executive Summary:

Participation of rural men and women in community-based development programmes that affect their livelihoods, such as access to adult education, market opportunities, communication networks and financial services through community-level and district- level support centres and farmer schools is limited in scope and depth. The objective is to provide scalable models for rural communities to enter into the local and national dialogue while building on the initiatives already underway as described in the joint vision supported by both the Government and development partners.

The project will also assist communities to upgrade local markets and assist in the negotiations for better and more secure access to traditional land in rural and town areas. The programme will ensure that gender equity and women’s empowerment issues are mainstreamed in decision-making and service delivery.  In particular, the project will contribute to local economic development by providing access to global information on job opportunities, commodity prices, adaptable technologies and entrepreneurial knowledge and skills. It will also promote non-formal education and acquisition of life skills by youth and community leaders through multimedia campaigns/programmes on gender, HIV/AIDS, conflict management,  as well as strengthen social cohesion and participation through positive entertainment activities, face-to-face and/virtual engagement and communication among various stakeholders.

Situation analysis:

Within the framework of UNIDO’s support to the establishment of Rural Industrial Growth Centres and its contribution to youth employment, special focus will be placed on promoting community participation in economic development and social dialogue. UNIDO supported growth centres in Guinea, Liberia and Sierra Leone are being increasingly recognised as scalable models that can foster local economic development, community engagement and participation.  In Sierra Leone, Community Production/Growth Centers have been established in five different locations across the country. Hence UNIDO’s contribution will particularly emphasize the integration of add-on components to the community production and marketing centres (to be) established in each district across the country in line with Government requests and priorities.

Production and processing in those centres is powered by fossil-fueled machines. One serious concern is sustainable energy supply that is more reliable, cheap and modern. In the search for viable alternatives, particularly renewable ones, Solar PV seems a technically and economically attractive option; a conclusion reached after Sierra Leone’s first multi-stakeholder solar energy forum organized by the Ministry of Energy and Water Resources.

Many rural communities, especially women and youth, feel marginalized and de-linked from the rest of (urban) society and its decision- making processes. The Business Information and Communication (BIC) platforms will be a step towards improving access to information and promoting dialogue among various stakeholders.

Strategies including lessons learned and the proposed project

UNIDO, UNDP and FAO have agreed to collaborate and expand the concept of the solar-powered BIC platforms to cover junior secondary schools and farmer-based Agri-business centres (ABCs) respectively. When these components are incorporated, the project will then be implemented in three options or modules:   the package for the school-based learning hubs will be referred to as the school module, and the growth-centre-based BIC platform as the centre module, which will have a parallel subscription facility/channel besides the free school-learning channel.  A farmer module, which is a reduced form of the centre module, will be implemented for the FAO-supported ABCs. Objectives, activities and budget for the school and farmer modules are outlined separately and treated as independent projects in line with the respective requirements of UNDP and FAO.

Results framework

Joint Vision framework and benchmark

As part of the Joint Vision programme 18, this project will contribute to the UN Joint Vision’s broader effort to equip rural areas with access to community growth centres that can provide basic communication services including internet where possible that would:

- Give farmers basic information about markets, prices, weather conditions, etc.

- Give youth farmers access to a variety of programs including TV and educational programs plus entertainment channels for youth recreations.

In this way, the project would have contributed to local economic development by providing access to local/global information; promoted non-formal education and acquisition of life skills by youth and community leaders and strengthened social cohesion and participation through positive entertainment activities, face-to-face and/virtual engagement and communication among various stakeholders.

Deliverables (outputs)

18.5.1 Communication hubs established and integrated into growth/community production centres in each rural district

18.5.2 Each hub provides access to the internet (and to satellite TV), market and other technical information; pay phone and/or money transfer services; non-formal education and entertainment services

18.5.3 Each hub connected to a national Youth Platform; a web-based tool to enhance networking, participation, information/knowledge sharing, and to generate ideas and recommendations amongst youth and between community members and other stakeholders or leaders.

18.5.4 Renewable energy supply systems (e.g. solar) installed for each communication hub as autonomous green energy units/business models.

Core activities:

Facilitate and support the acquisition and operation of Solar PV system, DSTV system for information, education and entertainment and other relevant items for the setup and proper functioning of the business information system; train locals in assembly and maintenance of solar equipment/devices; assist local entrepreneur develop and implement business plan to ensure sustainability of the BIC platform.

Geographical coverage:

The Business Information and Communication (BIC) platforms will be located in the premises of each of the five growth centres in Binkolo, Bo, Koindu, Kpadembu and Pujehun, as well as Newton

Beneficiaries:

The principal beneficiaries of the BIC platform are communities, including schools and other institutions, located within commuting distance (approximately 5km radius) to the centres. Each platform can potentially service at least 200 persons/visits per month. This easily translates to over 14,000 visits per year for the six pilot BIC platforms.

Management and coordination arrangements

UNIDO will be responsible for the procurement and transporting of commodities to the designated growth centres. The growth centres’ management will work with UNIDO for a speedy completion of completion of all required deliverables in the project. The Renewable Energy unit of UNIDO headquarters will provide technical advice on the procurement and installation of the solar PV system.

The Ministry of Trade and Industry, Transnational Limited and the District Councils will be the main counterparts and UNIDO will be responsible for the coordination of all activities of the programme.

Fund management arrangements

UNIDO has signed the necessary MoU with the AA at the MDTFO to be a recipient of funds channelled through the SL-MDTF. Agency Service Requests will be issued from UNIDO Headquarters in Vienna to the UNDP Country office for the attention of UNIDO in Freetown.

Monitoring, evaluation and reporting

Project implementation, monitoring and reporting will be done by UNIDO on a continuous basis. The impact of this project will be assessed as part of the Joint Vision programme 18 at least one calendar year after the end of the project.

Elements of the logical framework

| Results chain | Performance indicators |
| --- | --- |
| Joint Vision Priority Area: Community Empowerment and Integration |  |
| JOINT VISION BENCHMARK |  |
| Rural areas which have access to community growth centres that can provide basic communication services including internet where possible. |  |
| OUTCOME |  |
| Outcome 1: Contribute to local economic development by providing access to global information on markets, commodity prices, weather conditions, job opportunities, adaptable technologies and entrepreneurial knowledge and skills | Proportion of rural population that perceive they have greater access to information relating to markets, livelihoods and opportunity to participate in decision making |
| Outcome 2: Promote non-formal education and acquisition of life skills by youth and community leaders through access to TV/multimedia programmes on gender, HIV/AIDS, conflict management as well as educational programmes and entertainment channels. |  |
| Outcome 3: Strengthen social cohesion and participation through positive entertainment activities, face-to-face and/virtual engagement and communication among various stakeholders | Access to and participation at the communication platform by youth and other interested parties/persons (number of hubs, users and entries) |
| DELIVERABLE 18.5.1 Communication hubs established and integrated into growth/community production centers in each rural district 18.5.2 Each hub provides access to the internet (and to satellite TV), market and other technical information; pay phone and/or money transfer services; non-formal education and entertainment services 18.5.3 Each hub connected to a national Youth Platform; a web-based tool to enhance networking, participation, information/knowledge sharing, and to generate ideas and recommendations amongst youth and between community members and other stakeholders or leaders. 18.5.4 Renewable energy supply systems (e.g. solar) installed for each communication hub as autonomous green energy units/business models. |  |

Legal Context or Basis of Relationship

Signatory to the Joint Vision as the UN’s contribution to the GoSL Agenda for Change.

Workplan

| Activity | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Consultations with stakeholders/interested parties |  |  |  |  |  |  |  |  |
| Recruitment of support staff |  |  |  |  |  |  |  |  |
| Procurement of equipment and furniture |  |  |  |  |  |  |  |  |
| Installation and training |  |  |  |  |  |  |  |  |
| Trial run of installed/assembled systems |  |  |  |  |  |  |  |  |
| Monitoring visits |  |  |  |  |  |  |  |  |
| Joint review meetings and documentation |  |  |  |  |  |  |  |  |
| Certification and Commissioning |  |  |  |  |  |  |  |  |
| End of Project Reporting |  |  |  |  |  |  |  |  |

Budget

# Footnotes

The term “programme” is used for projects, programmes and joint programmes.