Sixth Six-month progress report for project

“UNDG ITF Project A7-03 – Support to the Iraq-Kurdistan Mine Action Centre (IKMAAC)”

# Summary

| Participating UN Organisation: |  | Cluster: |
| --- | --- | --- |
| United Nations Office for Project Services (indicated for UNDP) and UNDG |  | UNDG Cluster 7 |

| Project No. and Project Title: |  | Project Location/Region/Province: |
| --- | --- | --- |
| UNDG ITF Project A7-03 UNOPS Project 00051104 “Support to the Iraq-Kurdistan Mine Action Agency (IKMAA)” |  | Erbil Governorate in Northern Iraq |

| Reporting Period: |  | Report no: |
| --- | --- | --- |
| 1 January 2007 to 31 April 2008 |  | Three |

| Counterpart organisations / implementing partners: |  | Project cost: |
| --- | --- | --- |
| UNOPS is the Executing agency of the project under the supervision of UNDG Cluster as per the umbrella MoU signed in April 2004 between UNDP, as administrator of the UNDG/ITF, and UNOPS. UNOPS is supported by UNDP with the National Field Coordinator located in Erbil as a resource person, as required. UNOPS is the implementing partner of the IKMAA and administers the funds provided by the UNDG/ITF to the IKMAA as per the terms of the MOA between UNOPS and the IKMAA. |  | USD 2,921,852 |

| Abbreviations and acronyms: |  | Project Duration: |
| --- | --- | --- |
| UNOPS: United Nations Office for Project Services IKMAA: Iraqi Kurdistan Mine Action Agency (formerly known as Iraqi Kurdistan Mine Action Centre (IKMAC) MoU: Memorandum of Understanding MoA : Memorandum of Agreement MDD : Mine Detection Dog RFP : Request for Proposals NMAA : National Mine Action Authority CROMAC : Croatian Mine Action Centre SRSA : Swedish Rescue Services Agency |  | Initially one Year. A request for a project extension for an additional 12 months was approved by the Steering Committee during December 2006. A further extension through April 2008 was then requested and approved in May 2007. |

# NARRATIVE REPORT

# Purpose

1.1 The overall objective of the Project is to increase the capacity building of the IKMAA as follows.

- To increase demining performance and production rates by providing up to date mechanical demining equipment and accessories to the IKMAA (formerly known as IKMAA).

- To provide Awareness courses Explosive Ordnance Disposal Training, Information Management Training and Planning and Operations Training.

- Procurement of Mine Detection Equipment including Mine Detectors, Personal Protection Equipment.

- Procurement of IT Equipment.

- Procurement of spare parts for the existing fleet of Mine Detectors and Mechanical Mine Clearance Equipment.

The following outcomes are expected through the above activities:

- Increased production rates and enhanced deminer's performance through providing up to date demining equipment, office equipment and mine clearance accessories.

Note:

1. The project lacked a project manager during most of 2006. A UNOPS project manager was initially identified during early 2006. However the candidate later rejected the offer why a new candidate had to be identified. A suitable candidate was later identified in September but could not take up the position in Amman until early December 2006 due to other commitments with UNOPS and with another Mine Action Programme.

2. In December 2006 it was requested that the project objective “construction of mechanical clearance equipment” with a budget of US$ 1,992,000 for construction of mini flails, front end loaders and excavators to be utilized for clearance of landmines to be contracted through an initial competitive process (through a Request For Proposals (RFP) issued by UNOPS from the APIF), rather than through prequalification as per the project document. It was previously requested by the Iraqi National Mine Action Authority (NMAA) and IKMAA during a meeting held in Amman in May 2006 that the contract would be awarded through a competitive process (including the issuing of an Expression of Interest and the issuing of an RFP locally in Kurdistan Region) to invite other possible contractors and to provide transparency. This request was supported by UNOPS and was also subsequently approved by the SC in early 2007.

3. In addition to the above IKMAA requested that the objective in the Project Document; Awareness courses on quality and International Mine Action Standards were not necessary and therefore this should be replaced with Explosive Ordnance Disposal Training, Information Management Training and Planning and Operations Training. This request was supported by UNOPS and was also subsequently approved by the SC during early 2007.

4. It was requested by the NMAA and IKMAA the MDD activity to be removed under the project. This part of the project was to include purchasing of MDD;s, MDD food, MDD medicine and hiring of MDD staff in at a total cost of US$ 259,704. IKMAA requested that this amount should be used to repair the current fleet of Bozena mini flails and to purchase Bozena spare parts and three Camcorders. Reason for this is that the originally envisaged cost to repair the Bozenas was much lower than what has been quoted by Bozena in January 2007 resulting that funds needed to be added to this budget line in order to enable UNOPS to purchase all the spare parts required.. This request was supported by UNOPS and was also subsequently approved by the SC in early 2007.

  - 1.2 Explanation how the programme/project is relevant to the following benchmarks:

The UN System, under the auspices of the United Nations Assistance Mission for Iraq (UNAMI) developed a UN Strategy for the support to Iraq’s reconstruction and development. UNPD was designated to serve as the lead UN agency for Cluster 7, Mine Action, in Iraq effective 1 January 2004 with participation by UNMAS and UNOPS in the same cluster. In this cluster the project addresses the problem of Explosive Remnants of War (ERW) contamination throughout Iraq that poses a serious threat to the safety of the civilian population by denying access to valuable resources including agricultural land, grazing land, roads, water sources and residential areas. UNDG/ITF Cluster A is designated for Agriculture, Environment and Natural Resources Management and therefore its goals are dependent on continuing to address the ERW problem. Under Cluster A7-03 project 51104, also falling under the umbrella of the NMAA, aims to increase and improve the existing assets of the indigenous Iraqi Kurdistan Mine Action Center (IKMAA) in Northern Iraq to address the needs of the Iraqi Kurdistan communities and vulnerable groups affected by landmines and other ERW.

1.3 Main implementing partners, their roles and responsibilities, and their interaction with the UNOPS

This project is carried out within UNDG’s Cluster A with overall project management from the UNOPS Mine Action Unit (MAU) in the UNOPS North America Office (NAO) and field implementation from the Project Manager based in UNOPS Iraq Operations Centre (IQOC). The Project Manager (recruited in December 2006) reports to the IQOC Country Director on matters relating to project coordination, field support and reporting to the ITF Steering Committee, and to the UNOPS MAU Senior Portfolio Manager on technical matters of substance. The Project Manager will travel to Iraq frequently to oversee the implementation of the project by the IKMAA, and also works in close consultation with the UNDP Mine Action Team. The Project Manager is supported by a UNOPS National Field Coordinator who reports directly to the Project Manager. On occasions the National Field Coordinator may travel to Amman for coordination meetings.

A Memorandum of Agreement between UNOPS and IKMAA that delineates the role of UNOPS as IKMAA’s implementing partner was drafted in December 2006 for signature by both parties. The MoA was signed in January 2007. Procurement and contracting is carried out by the Project Manager using UNOPS long term agreements and UNOPS procurement channels.

- Resources

Financial Resources:

2.1 Total funds provided, disbursed and committed

Amount and Source of funds for the project: 	US$ 2,921,852 (UNDG ITF)

Total Disbursements until June 2007: 	US$ 366,335

Total Commitments until June 2007: 		US$ 2,497,713

2.2 Variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

Until December 2006 expenditures were slower than predicted due to the lack of a Project Manager. The project has lacked a project manager during most of 2006. A UNOPS project manager was initially identified during early 2006. The candidate later rejected the offer why a new candidate had to be identified. A suitable candidate was later identified in September but could not take up the position in Amman until early December 2006 due to other commitments.

The project document as signed between UNOPS (for UNDP) and UNDG/ITF on 23 March 2006. Therefore while the project’s original timetable was from December 2005 – December 2006, the delayed start-up of project activities changes the timetable to January 2007 – December 2007. Since the recruitment of the Project Manager was delayed until December 2006. The MOA with IKMAA was signed in January 2007. The project has been extended through April 2008 through a request to the SC.

2.3 Programme/project expenditures within the 10 budget categories, including security expenditures.

Project Expenditures January – June 2007:

| Personnel | $94,408.86 |
| --- | --- |
| Contracts |  |
| Training of counterparts | $121,730.34 |
| Transport |  |
| Supplies and commodities | $962.00 |
| Equipment | $2,107,622.67 |
| Travel | $12,294.00 |
| Security | $5,000.00 |
| Miscellaneous | $25,294.96 |
| Total Programme costs: | $2,367,312.83 |

2.4 Details on budget revisions approved by the UNDG ITF Steering Committee

In December 2006 a request for a budget revision was submitted to UNDG ITF and was subsequently approved. The request also included a request of the scope of the project. Details regarding this request are to be found under “1. Purpose” in this report.

Human Resources:

2.5 National Staff: Provide details on the number and type (operation/programme)

Programme and Operation

One National Field Coordinator based in Erbil, Iraq.

2.6 International Staff: Provide details on the number and type (operation/programme)

One International Project Manager (P4) based in Amman, Jordan.

- Methods of Operating

3.1 Details on the procurement procedures utilized and explain variances in standard procedures.

Procurement of Mine Clearance and Office Equipment

The demining equipment indicated below has been purchased by UNOPS. Some of the equipment has been purchased using the UNOPS long term agreements. IKMAA will have the responsibility of inspecting and receiving the equipment and provide a Receive and Inspection Report for UNOPS to make the payment to the supplying company directly. Ever since the procurement done under Oil-for-Food Program by UNOPS several years ago, no new equipment has been provided to the Iraqi Kurdistan Mine Action program. During the Ronco funding phase in 2004 while NGO operating costs were covered, no new procurement of sensitive equipment was done. The demining and office equipment has suffered normal wear and tear and is therefore in urgent need of replacement.

  - 3.2 Details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

During the period no monitoring missions has been undertaken due to security restrictions, instead the UNOPS National Field Coordinator has travelled to Amman and Jordan on three occasions in order to liaise on project activities with the Project Manager. The Project Manager has also been denied security clearance on one occasion.

- Results

  - 4.1 Summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

During the reporting period the following progress has been achieved:

- Procurement of demining equipment,

- Procurement of office equipment,

- Signing an MOA between UNOPS and IKMAA,

- Procurement of two trucks,

- Contracting for construction of mine clearance machines locally,

- EOD training,

- A study visit to the Croatian Mine Action Centre for ten IKMAA senior staff.

  - 4.2 Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

Construction of Mechanical Mine Clearance Machines (50%)

The Mechanical Clearance Machines construction will be implemented by a local entity that has been selected by UNOPS through a local competitive procurement process in the Kurdistan Region. The competitive process was carried out in early 2007 and included the issuing of an EOI and the subsequent issuing of an RFP. The contract has been awarded by UNOPS to a local contractor in the Kurdistan Region. IKMAA has the responsibility of monitoring and supervising the construction, which is estimated to carry on trough May 2008. In addition IKMAA has the responsibility of certifying the monthly reports submitted by the entity constructing the machines. The below machines are being constructed in Northern Iraq through a contractual arrangement and delivered after six and twelve months.

The following machines are scheduled to be constructed for IKMAA during 2007/2008:

- 3 x front end loaders

- 3 x excavators

- 3 x mine sifters

- 1 x mini flail

- 4 x mobile workshops

Note: This also includes quantity of spare parts for one-year maintenance and repair of all machinery above. The quantities initially indicated had to be reduced after the issuing of the RFP since the funds available were not sufficient to cover the procurement of all machines as per initially envisaged.

For purposes of transportation UNOPS are also purchasing one or two trucks under the project for transportation of the above listed machines between mine clearance sites.

As of June 2007 the following equipment has been purchased and delivered to IKMAA (100%):

- Minelab detector spare parts – Worth of US$ 51,945 for repair of the current fleet of Minelab detectors.

- Bozena spare parts - Worth of US$ 261,690.28 for repair of the current fleet of Bozena Miniflails.

- Battery Rechargeable for Minelab detector – 3,500pcs

- Charger Battery for detector – 240pcs

- Helmet lightweight c/w visor 30cm – 434pcs

- Appliqué for visor – 1,900pcs

- Battery Rechargeable for VHF hand held Radios – 168pcs

- Minelab F3 Mine Detectors – 12pcs

- Vest protective RBR c/w carry bag (OS) – 154pcs

- Laptop computer Sony Vaio VGN-FS875P/H – 10pcs

- UPS Power ware 9155 15KVA – 1pcs

- Digital Cameras – 18pcs

- Global Positioning Systems (GPS) - 25

Procurement of equipment by IKMAA under the MOA between IKMAA and UNOPS (30%).

Through the MOA with IKMAA, UNOPS are also providing IKMAA with funds for equipment to be purchased locally in the Kurdistan Region. This equipment will be purchased using UN rules for procurement. Payments to IKMAA under the MOA are only done once IKMAA provides evidence of following those rules. The following equipment has been or is currently being procured by IKMAA directly under the MOA:

| Item Description | Quantity |
| --- | --- |
| Computer Dell PowerEdge 2800 | 3 |
| Computer Dell OptiPlex GX620 | 3 |
| Computer Dell OptiPlex 210L | 3 |
| Laptop computer Sony Vaio VGN-TX770P/W | 3 |
| HP LaserJet 5100nt | 3 |
| Netgear Access point GW602 | 4 |
| Netgear Wireless Router WGR614 | 4 |
| Netgear Wall-Plugged Wireless Range Extender WGXB102 | 4 |
| Netgear 16 port Gigabit switch GS516T | 2 |
| Netgear 8 port Gigabit switch GS100 | 8 |
| Dedicated Internet System (DATUM PSM 4900L, Cisco Router, 1.8m dish, 4watt BUC, LNB, Original cable and connectors, waterproof, etc.). | 1 |
| Copier Machine RICOH FT5632 | 3 |
| Copier Machine Canon NP7161 | 8 |
| Printer HP Colour Laser jet 9500 HDN | 3 |
| APC Smart UPS 1000VA SUA1000I | 25 |
| Video Cameras | 3 |

Training activities (80%)

Official Study Tour to Croatia

During the month of April 2007 IKMAA conducted an Official Study Tour to the Croatian Mine Action Programme and the Croatian Mine Action Centre. The study visit to Croatia took place between the 19th of April and the 1st of May. 10 senior staff from the Iraqi Kurdistan Mine Action Centre (IKMAA), including the IKMAA General Director, participated during the study visit. The aim of the study visit was for IKMAA staff to exchange knowledge with their colleagues in the Croatian Mine Action Programme and the Croatian Mine Action Centre (CROMAC) and to participate during a symposium on mechanical clearance whereas more than 170 Mine Action Stakeholders from all over the world participated. The study visit, amongst other activities, covered the following:

- Field visit to demining operations conducted by CROMAC.

- Visits to Croatian communities impacted by landmines.

- Participating during the CROMAC annual symposium on humanitarian mine clearance. This year the main topic was mechanical clearance. The participants got to see a comparative test between 12 different mine clearance machines. In addition the symposium covered topics such as; tests of personal protective equipment, tests of mine detectors and briefings on new mine clearance technology.

- A visit to the CROMAC sub office in Zadar where briefings were given on operational activities, information management and quality assurance and quality control.

- A visit to the CROMAC sub office in Zadar where briefings were given on operational activities, information management, quality assurance and quality control, finance and administration, resource mobilization and donor reporting amongst other topics.

- A visit to the factory belonging to one of the commercial companies in Croatia manufacturing mine clearance machines.

- A visit to a company in Zagreb which is working with aerial pictures and information management.

- An official dinner with CROMAC and sightseeing of Zagreb.

Explosive Ordnance Disposal (EOD) Training

One of the activities under this project is EOD training of IKMAA staff. To date many teams have successfully graduated and are operational in Kurdistan Region. The IKMAA EOD Supervisors, EOD Operators, EOD Group Supervisors, EOD Team Leaders are all qualified at the EOD Level 1. and 2 (as per IMAS 9.3 paragraph 4.2), but require a further three weeks of supervised operational deployment in order to qualify as Level 3. EOD Operators (as per IMAS 9.3 paragraph 4.2), and carry out demolitions in accordance with the requirements laid down in the relevant IMAS. Two EOD Trainers will spend four weeks in Kurdistan Region (arrival through Amman, Jordan and there after Erbil, Iraq and training to be carried out in IKMAA Training Base in Soran in Northern Iraq) and conduct EOD training to a Level 3. as per IMAS. The trainers will also be providing advice and assessing individual skills. The Contractor will also provide a Project Manager for a period of 10 days during the period of the contract. Concerning Render Safe Procedures (RSP), focus should be on RSP’s of Anti Personal (AP) and Anti Tank (AT) mines. This training is provided under a contractual agreement with Swedish Rescue Services Agency (SRSA) whereas SRSA will also provide EOD equipment to IKMAA for free.

Information Management Training and Planning and Operations Training

During the August 2007 a two-week training course on Information Management Training and Planning and Operations Training will be carried out for 8 IKMAA staff. The training will be carried out by UNOPS in Jordan in cooperation with UNDP and Swedish Rescue Services Agency (SRSA) who will be providing a trainer at no cost for the duration of the training course. Other stakeholders in Mine Action that will be involved are Norwegian Peoples Aid (NPA) to who’s clearance operations a study visit will be conducted, and the Mine Action Centre in South Lebanon, who will provide an instructor for two days during the course.

The expected outputs of the project are as follows:

- The ability of the IKMAA to effectively manage the projects that it implements will be increased, as damaged, unusable, and expired demining equipment will be replaced by up-to-date equipment.

- The introduction of supplementary, more efficient clearance technologies will greatly improve the rates of clearance currently being realized within the programme. Complimentary to the training courses on Explosive Ordnance Disposal Training, Information Management Training and Planning and Operations Training will make best use of the financial resources allocated to the programme now and in the future.

- At the end of the project it is expected that the IKMAA will have the necessary technical capacity and equipment to accelerate and enhance the on-going clearance activities.

Humanitarian and development goals and priorities are all addressed under this project, and all individuals and communities within the IKMAA area of responsibility stand to benefit from a more efficient and effective mine action programme.

  - 4.3 Key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

Regular meetings with the UNDP Mine Action team have been undertaken since the Project Manager was hired in early December. The Project Manager has also participated during UNDP Cluster A meetings.

  - 4.4 Achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

Nothing to report

- Future Work Plan

  - 5.1 Summary of the projected activities up to the end of December 2007.

- Monitoring of construction of all items of mechanical equipment by IKMAA logistics staff and UNOPS staff,

- Conduct training courses for IKMAA EOD staff up to EOD Level 3.,

- Conduct IMSMA and Operations Training,

- Preparations of course reports on the above mentioned courses,

- Create additional training opportunities for IKMAA staff,

- Monitoring of IKMAA procurement of office equipment,

- Accreditation of mechanical demining equipment delivered in November 2007.