| - United Nations Peace Fund for Nepal (UNPFN) - Project Status Report - As of 11 February 2008 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Recipient UN Organization: | UNDP | Priority Area: |  | Elections Sub-area: Technical advice/assistance on elections |
| Project Number: | UNPFN/2007-06-a/02 (UNPFN/B-2) |  |  |  |
| Title: | Provision of Specialised Electoral Assistance to the Election Commission of Nepal |  |  |  |
| Funds Committed: | USD 384,500 | % of approved | 100% |  |
| Funds Disbursed: | USD 49,812 | % of approved | 13% |  |
| Forecast final date: |  | Delay (months) |  |  |

| Objectives | Achievements / Results | % of planned |
| --- | --- | --- |
| assist the Election Commission of Nepal in effectively and swiftly addressing a number of unforeseen challenges and evolving needs connected to the conduct of the Constituent Assembly election through the rapid identification, recruitment and deployment of highly specialised electoral experts; and | Two specialists were hired - “Ballot Paper Specialist” - “Regional Training Advisor” | 10% |
| assist the Election Commission of Nepal in conducting a comprehensive Post-Election Review exercise to identify, analyse and retain crucial lessons learned during the organisation of the CA election that could be effectively applied to the future administration of the electoral process by the EC and to future electoral assistance programmes. |  | 0 % |

Qualitative achievements against objectives and results

The project started implementation immediately after its earlier approval and two specialists - a “Ballot Paper Specialist”; and a “Regional training Advisor” were hired. Following the postponement of the CA election, the project was stopped and the specialists’ contracts terminated. A no-cost extension has been proposed and is presented for the Executive Committee for their consideration.