Six month PROJECT progress report (JANuary – JUNE 2007)

# Project Summary

| ## Participating UN Organization: |  | ## Cluster: |
| --- | --- | --- |
| World Food Programme |  | A – Agriculture and Food Security |

| ## Project No. and Project Title: |  | ## Report Number: |
| --- | --- | --- |
| A6-02 (WFP project EMOP 10360.0) Development of Safety Nets and Food Security through Food Assistance. |  | 6 |

| ## Reporting Period: |  | ## Project Budget: |
| --- | --- | --- |
| 1 January to 30 June 2007 |  | US$ 9,194,839 |

| ## List Implementing Partners: |  | ## Project Coverage/Scope: |
| --- | --- | --- |
| - Ministry of Health (MoH) - Ministry of Education (MoE) - Ministry of Planning and Development Cooperation (MoPDC) |  | 14 governorates |

| ## Abbreviations and acronyms: |  | ## Project Duration/Closed Project: |
| --- | --- | --- |
| Ministry of Health (MoH) Ministry of Education (MoE) Ministry of Planning and Development Cooperation (MoPDC) Central Organisation for Statistics and Information Technology (COSIT) World Food Programme (WFP) National Development Strategy (NDS) Millennium Development Goal (MDG) Project Management Committee (PMC) Project Management Unit (PMU) Parent-Teacher Association (PTA) |  | - Mar 2005 – Dec 2007 - Extension in time approved on 29/5/07 without change in budget. Project completion date now 31 Dec 2007. - Not operationally closed during the reporting period. |

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Do not put the narrative text into boxes as was done in the previous report and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

# NARRATIVE REPORT FORMAT

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Development Goal

Development of Iraqi Government capacity for the implementation of social safety nets, developing and managing safety net and food security programmes; Support to improved nutrition and health status of vulnerable groups; Improve access to primary education in particular for girls

Immediate objectives

- Assist MOPDC/COSIT and Food Security Unit in improving Iraq institutional capacity in monitoring and analyzing poverty/food security;

- Support in establishing nationwide school feeding programme;

- Support MOE in increasing enrolment and regular attendance of children, in particular girls, in primary schools;

- Assist MOH in improving knowledge of mothers and caretakers of young children on appropriate feeding practices and improving the nutritional status of malnourished children and pregnant and lactating mothers;

- Assist MOH in increasing attendance of the vulnerable at local health care facilities.

Outputs and Outcomes:

- Assist in the establishment of food security unit within MOPDC/COSIT and strengthen the capacity of the Government for continued monitoring and analysis of food security and in developing cost effective and targeted safety net strategies;

- Support MOE/MOH in establishing inter ministerial project implementation capacity, training of trainers and advocacy/awareness raising on food security and need for education;

- Train staff and implementing partners in the implementation of targeted assistance programmes;

- Enhance learning capacity and attendance of children particularly girls in WFP assisted primary schools.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

The National Development Strategy (NDS) is established on 4 major pillars, the third of which is "Improving the quality of life". This requires actions "to reduce drop-out rates at the primary (school) level" and the enactment of "a social safety net program for the poor and vulnerable".

This WFP assistance to Iraq specifically addresses these requirements of the NDS through the provision of targeted food aid to those identified in WFP's 2004 Baseline Food Security Analysis as being extremely food insecure and to school children to encourage attendance and reduce drop-out rates.

Through the provision of food assistance and by undertaking capacity building activities, mainly based on a training programme, the Operation is addressing the following Millennium Development Goals:

- MDG 1: “Eradicate extreme poverty and hunger” by distributing food to vulnerable groups and school children.

- MDG 2: “Achieve universal primary education” by working towards increasing enrolment and improving the attendance rates of Iraqi primary school level children.

- MDG 3: “Promote gender equality and empower women” by contributing to the elimination of gender disparity in primary education, through provision of incentives to female school children.

- MDG 4 “Reduce child mortality” and 5 “improve maternal health” are addressed through provision of food aid to pregnant women and nursing mothers and malnourished children, and through education aiming to improve knowledge of appropriate feeding practices.

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

WFP’s partners are the Ministries of Health (MOH), Education (MOE) and Planning and Development Cooperation (MoPDC) who manage and implement the EMOP activities through the central Project Management Committee (PMC). Each of the Ministries (MOH & MOE) is represented by two senior staff at policy and decision making levels who are delegated responsibility for the overall implementation of the project with WFP playing an advisory role. The PMC coordinates monitors and reports on the implementation progress.

At the governorate level, a Project Management Unit (PMU) composed of representatives from the Ministries of Health and Education as well as WFP (in an advisory capacity) carries out the day-to-day implementation and oversight activities.

These activities comprise responsibility for receiving and storing of food commodities arriving from neighbouring countries, secondary transport of commodities, distribution, monitoring and reporting. Parent-Teacher Associations (PTAs) are responsible for supervision of food storage and stocks and the organization and supervision of the food distribution process to the beneficiaries.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed

Total IRFFI funds received = $9,194,839

Committed = $ 8,904,783 (97%)

Disbursed = $ 8,450,330 (95%)

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s).

Not applicable; variations insignificant.

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

  - Indicate other funding sources, if applicable.

The remainder of the project has been funded by bilateral contributions.

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable

An extension-in-time to 31 December 2007 was approved on 29 May 2007 with no change to the budget.

  - Project expenditures for the 1 July to 31 December 2007 period.

The remaining balance of $290,056 will be committed and spent along the termination date of the current WFP emergency assistance for Iraq (31/12/07).

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

74 national staff including 57 based inside Iraq (programme and logistics staff).  The 17 staff in Jordan and Syria are also comprised of programme and logistics staff as well as ICT, administration, finance, HR, security and drivers.

  - International Staff: Provide details on the number and type (operation/programme)

9 international staff – 2 management, 1 finance/admin, 1 security, 3 logistics, 2 programme

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context.

As mentioned earlier, the key partners in the implementation of the project are the Ministry of Health and the Ministry of Education, together with the Ministry of Planning, Development and Cooperation through COSIT. There is strong inter-agency collaboration with WHO and UNICEF. The input of the line ministries is fundamental to project delivery, as described above. The reporting line agreed to by WFP and the three clusters to which it is an active member is that “Project A6-02”, approved to cover associated costs for the WFP assistance to Iraq, is implemented within the context of clusters B and D. Therefore, while reporting of project expenditure is made within Cluster A, operational reporting on the school feeding element of this project is done through cluster B and on the vulnerable group feeding through Cluster D”.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures.

All food for this project is either in-kind donations or procured by the Procurement Unit in Headquarters following WFP’s strict procurement protocols.  There have been no variances from the standard procedures.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project.

Monitoring is carried out by PMU members and WFP staff working together. Information is fed into an M&E database which provides up-to-date information on project progress to date.

  - Report on any assessments, evaluations or studies undertaken.

A follow up on the baseline food security study (published in September, 2004) through a Food Security and Vulnerability Analysis in Iraq, was undertaken in collaboration with MOPDC/ COSIT, MOH/ Nutrition Research Institute and UNICEF as part of the project.

The 2005 Food Security and Vulnerability Analysis survey was carried out with funds contributed by IRFFI. The results have reveal indicators that have raised concerns among members of the UN country team, the humanitarian community and the government of Iraq as well and hence a need to urgently address the critical issues revealed by the report. One of the indicators was the increase in acute malnutrition rate to 9 % from 4 % reported by the WFP in 2004. The results also showed that 15% of the Iraqi population are food insecure and in dire need of assistants. The need to address the increasing rate of acute malnutrition for children under 5 years, when the damage has occurred cannot be reversible, requests that food assistance for the vulnerable groups in Iraq is a matter of urgency to reverse the trend.

The Food Security and Vulnerability Analysis report was launched on 11 May 2006, by WFP Representative and Country Director for Iraq in a ceremony in Amman attended by representatives of the donors’ community, UN agencies and NGOs. The same report was launched in Iraq on May 8 by the Minister of Planning and Development Cooperation, in Iraq. The report has been posted to Ministry of Planning and Development Cooperation website http://www.iraqcosit.org/english/activities_reports.shtm for access by the public.

Due to the rapidly changing circumstances inside Iraq, WFP is now planning a follow-up Food Security Survey.  Implementing staff have been trained and the data collection, analysis and report writing are scheduled to take place in the second half of 2007.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period.

- Increase enrollment and regular attendance of children, in particular girls, in primary schools; - not achieved due to the suspension of school feeding activities during the reporting period.

- Increase attendance of malnourished children and pregnant and lactating women at local healthcare facilities; - achieved during food distributions.

- Improve the nutritional status of malnourished children and pregnant and lactating women; achieved, recovery rate of malnourished children receiving WFP food is over 90%

- Secure regular attendance of tuberculosis patients enrolled in the National Programme at local healthcare facilities; - achieved.  TB patients receiving WFP food.

- Improve the knowledge and daily practices of mothers and caretakers of young children on appropriate feeding practices; - achieved. Mothers receiving WFP food also receive information on good feeding practices.

- Improve Iraqi institutional capacity in monitoring and analyzing food security. – achieved.  Food Security Unit established within Ministry of Planning and Development cooperation.  They have conducted two comprehensive food security and vulnerability surveys with WFP since 2004.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

Medium term outcomes on school feeding (increased enrolment, particularly of girls) have not been achieved, but in outcomes relating to the capacity of MoPDC to conduct food security monitoring and assessments have been, along with outcomes relating to the nutritional status of those vulnerable groups receiving WFP food.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

For the first half of 2007, only 14.2% of target beneficiaries were reached with 11% of the planned amount of food.  No school feeding took place as this activity remains suspended following the Minister of Education’s decision last year to review the food basket.

Distributions were limited in the first half of the year primarily by internal funds transfer constraints.  Funds for local transport, storage and handling were not reaching the governorate levels in spite of being received in Baghdad.  Without adequate funds, local officials were not able to accept significant quantities of commodities, nor get them to the health centers for distribution.  The food that did reach the beneficiaries did so because committed PMU staff paid the up front costs out-of-pocket to ensure that food reached those in need.

The number of counterpart staff trained is higher than planned (294% of planned figures) as WFP and UNICEF cooperated in supporting the training of 153 health workers in Basrah on nutrition, health and hygiene practices.  This was not in the original project plan, but of added value to the project.

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

The principal constraint has been the continued suspension of the school feeding component of this project.  Since there has been no WFP support to school feeding this year, no progress has been made on the outputs related to school feeding, specifically:

      - food provided to send girls to school

      - food provided to primary school students

      - number of schools assisted

      - number of school feeding days

Discussions have been on-going with the Ministry of Education to try to overcome this impasse and re-start school feeding.  The turnover of key government counterparts is a constraint as agreements often have to be re-negotiated with incoming staff as evidenced by the incoming Minister of Education objecting to a food basket that had been fully supported by his predecessor.  The current political reality inside Iraq is one of very high turnover in government staff which could impact on the ability of the achievement of results.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

As mentioned above, this project is implemented through the Ministries of Health, Education and Planning and Development Cooperation through a Project Management Committee (PMC) in Baghdad and Project Management Units (PMUs) in each governorate.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

WFP’s Enhanced commitment to women is built into the project implementation strategy whereby women constitute 48 percent of those working in leadership positions in the food management committees and an average of 56 percent of the beneficiaries are women. Female paramedical staff are in the lead in educating beneficiaries on nutrition and hygiene and women take the lead in the food management committees for school feeding.

- Future Work Plan

  - Summarize the projected activities up to the end of Dec 2007.

Conduct a follow-up food security survey along with continued food support to vulnerable groups through the Ministry of Health.