Sixth Six-month progress report for project

# REPORT COVER PAGE

| ## Participating UN Organization: |  | ## Cluster: |
| --- | --- | --- |
| WHO and UNICEF |  | D Health and nutrition |

| ## Project No. and Project Title: |  | ## Report Number: |
| --- | --- | --- |
| D2-19a (UNICEF) and D2 -19b (WHO) Disease Eradication, Elimination and Introducing New Vaccines |  | 1 |

| ## Reporting Period: |  | ## Project cost: 12,000,000 |
| --- | --- | --- |
| April-June 2007 |  | Total for Project: USD 12,000,000 WHO received: USD 6,201,841 UNICEF received USD 5,798,159 |

| ## List Implementing Partners: |  | ## Project Coverage/Scope: |
| --- | --- | --- |
| - MoH - WHO - UNICEF |  | All Iraq |

| ## Abbreviations and acronyms: |  | ## Project Duration/Closed Project: |
| --- | --- | --- |
| AFP Acute Flaccid Paralysis DoH Directorate of health EPI Expanded program on Immunization IMR Infant mortality Rate IRCS Iraq Red Crescent Society MCV Measles containing vaccine MNFI Multi-National Forces in Iraq MMR Measles, Mumps and Rubella vaccine MDGs Millennium Development Goals MoH Ministry of health NDS National Development Strategy NIDs National Immunization days OPV Oral Polio vaccine PHCU Primary Health Care Unit SIAs Supplementary Immunization Activities UNICEF United Nations Children Emergency Fund WHO World Health Organization |  | One year, April 2007 to May 2008 |

NARRATIVE REPORT FORMAT

Report Formatting Instructions: We kindly ask that you review the instructions below and follow them in the preparation of your report:

- Do not put the narrative text into boxes as was done in the previous report and do not incorporate boxes, graphs, etc into the narrative report.

- Add additional information including charts, graphs, etc as annexes to the report and clearly reference the annexes using footnotes or endnotes within the body of the narrative

- Number all sections and paragraphs as indicated below

- Format the entire document using the following font: 12point _ Times New Roman & do not use colours.

# Purpose

  - Provide the main objectives, outcomes, outputs of the programme/project

Outcomes: Contribute (by the end of 2007) to the reduction of infant and child morbidity and mortality through protecting more children against more diseases.

The key immediate objectives are:

- Achieve by the end of 2007 coverage of at least 80%, by all essential vaccines among infants in every district.

- Maintain poliovirus free status through 2007 and Eliminate measles from Iraq the end of 2007.

- Provide evidence base for the introduction of rotavirus and Hib vaccines in the EPI program by end of 2007.

- Decentralize vaccine storage and management by the end of 2007.

  - Explain how the programme/project is relevant to the following benchmarks:

- UN Assistance Strategy for Iraq,

- UN Millennium Development Goals,

- Joint Needs Assessment ,

- Iraqi National Development Strategy

This project is in line with the UN Iraq Assistance Atrategy and the UN Health Cluster matrix, as immunization will contribute significantly to the achievement of the National Development Strategy and MDGs by preventing disease and reducing mortality and morbidity especially among women and children, and contributing to poverty reduction and development efforts

  - Indicate the main implementing partners, their roles and responsibilities, and their interaction with the Agency

- The responsibility of health and well being of Iraqi people falls on the MoH, but it is recognized that the actions undertaken by other ministries also have a great impact on successful implementation. Hence, WHO works closely with Ministries of: Education, Higher Education, Environment, Municipalities and Public Works, Agriculture, Interior, Finance and Planning.

- Through the programmatic approach adopted by the UN in Iraq, WHO as the leading agency in health, works in close collaboration with all the other Health Cluster members including UNICEF, WFP, UNFPA, UNIDO UNOPS, IOM and UNIFEM. This collaboration occurs at the planning and implementation stages to ensure consistency and continuity and to prevent overlapping.

- During this period WHO has been actively engaged with USAID and other international organizations.

- WHO as the leading agency in the health and nutrition cluster acts as the secretariat for the Health Sector working group Biweekly meetings. These meeting are led by the MoH with the [participation of the international organizations and donors. During these meeting different policies are discussed, proposals are endorsed.

- WHO’s major implementation partner is the Ministry of Health. All WHO programs are implemented by MoH staff, with the active participation -especially in the area of monitoring and capacity building- of WHO national staff in Iraq who is considered experts at international levels.

- WHO is also working with UNICEF, IRCS, Medical schools and the other key health related line ministries and works in close collaboration with the UN Health Cluster members.

- UNICEF is mainly responsible for vaccine and cold chain equipment procurement and social mobilization.

- IRCS and medical schools are mainly responsible for independent monitoring of SIAs and internal reviews of activities.

- Resources

Financial Resources:

  - Provide total funds provided, disbursed and committed:

| Component activity | allocated | committed | disbursed | Remaining balances |
| --- | --- | --- | --- | --- |
| Personnel | 850,893 | 50,053 | 0 | 237 |
| Contracts | 4,666,553 | 895,089 | 38,089 | 3,771,464 |
| Trainings | 272,065 | 122,091 | 6,630 | 149,974 |
| Supplies, commodities and Equipment | 116,875 | 6,875 | 0 | 110,000 |
| Miscellaneous; travel and security | 295,455 | 17,379 | 17379 | 278,076 |
| Total | 6,201,841 | 1,091,487 | 62,098 | 4,309,751 |

For UNICEF, a total amount of $ 5,798,159.00 was received from ITF. Out of these funds, 3,638,000.00 were committed for 2007, and around $ 600,000 were planned to be utilized during the reporting period and more than 70% of these have already been disbursed.

  - Highlight any variation(s) in projected versus actual spending for the reporting period indicating the reason for such variation(s): The amount projected was utilized as planned; the expenditure was not up to 100% due to some delays in the delivery of OPV vaccines in Baghdad due to insecurity. However, it is anticipated that by September 07 all funds committed during the reporting period will be fully utilized.

  - Explain programme/project expenditures within the 10 budget categories, including security expenditures.

Expected expenditures April-June 2007: The Bulk of expenditure will be in the form of logistic support for the follow up national measles campaign (22 April- 8 May 2007). In addition there will be remarkable support to improve EPI target disease surveillance and monitoring of infant immunization coverage and strengthening the technical and managerial capacity of governorate and district teams in the form of:

- Training on AFP and measles surveillance.

- Training on micro-planning and mapping for house to house immunization activities.

- Strengthening of supervisory activities.

- Purchase of equipment and supplies for the national measles and polio laboratories.

- Internal independent review of AFP surveillance by medical schools.

- Hiring of international (2) and national (5) staff

The other partner in the implementation of this plan is UNICEF, which will cover the cost of transportation for outreach teams for RED approach strategy, social mobilisation activities and support some cost of vaccine purchase.   In addition, the major expenditure during the reporting period for the UNICEF component was i) procurement of EPI supplies and commodities – OPV vaccine ($283,000 utilized); ii) Training and social mobilisation ($ 57,460); and iii) contracts ($260,000): which supported the contracts for provision of transport for vaccination teams during MMR campaign and rehabilitation/upgrading of the Erbil vaccine store.

  - Indicate other funding sources, if applicable: MoH provides most of the funding together with UNICEF and WHO core resources. UNICEF utilized a total amount of additional $1.2 million from other ITF and non-ITF projects were committed and utilized to support activities aiming at strengthening immunization services in Iraq.

  - Provide details on any budget revisions approved by the UNDG ITF Steering Committee, if applicable: since the project was approved and funds made available during the reporting period there has not been any major revision done up to this moment.

  - Project expenditures for the 1 July to 31 December 2007 period: it is anticipated that most of the expenditure will be mainly on supporting the two rounds of PNIDs scheduled to take place in September and October and UNICEF will provide support for transportation of vaccination teams and social mobilisation campaign. In addition, UNICEF will support the implementation of Reach Every District (RED) approach in the central and southern governorates as well as immunization out-reach services particularly in the IDP affected areas. It is anticipated that a total amount of $ 2 million will be committed and spent by 31st December 2007.

Human Resources:

  - National Staff: Provide details on the number and type (operation/programme)

Three Surveillance focal points (WHO) and for UNICEF two staff based in Erbil and five contracted facilitators as well as three staff in Amman (one technical officer and two programme assistants).

  - International Staff: Provide details on the number and type (operation/programme)

Two technical officers (WHO) and for UNICEF two technical officers all based in Amman.

- Methods of Operating

  - Summarize the implementation mechanisms primarily utilized and how they are adapted to achieve maximum impact given the challenging operating context: The Ministry of Health (MOH) is the main government partner with the primary responsibility for implementing this project. It is fully in charge of management, implementation of the overall project through the Directorates of Health (DOHs) in the governorates and PHCs at lower levels. In close coordination with MOH and UN Health and Nutrition Cluster partners WHO and UNICEF project officers, backed up by contracted facilitators and focal points based in Baghdad and in other governorates as well National Officers in Erbil and Basra. They are all responsible for overseeing project implementation, ensuring procurement and timely delivery of required supplies. The monitoring activities for this project include field visits as well as regular meetings with DOHs staff in all governorates, and the preparation of periodic reports. WHO and UNICEF staff in Erbil, Basra, Baghdad and Amman, in coordination with MoH, prepares and finalise all technical and financial reports. In addition, all the provided support is coordinated with WHO through the UN Health Cluster, whereby WHO provides overall technical as well as some financial support for routine and accelerated activities.

  - Provide details on the procurement procedures utilized and explain variances in standard procedures:  WHO and UNICEF have a well established procurement procedure; this is as well an element of programme support. Usually the procurement is done through UNICEF Supply Division in Copenhagen and WHO in Regional Office-EMRO based on a long-established international competitive bidding procedure and delivered to Baghdad under international insurance coverage. UNICEF-contracted facilitator or WHO logistic officers usually verifies the receipt of the supplies at MoH/EPI Ware House in Baghdad. Sometimes under request of MOH, UNICEF or WHO assists with distribution (through separate contract) of these equipment/supplies to governorates/DOH level. UNICEF-contracted monitors, and WHO focal points through their regular monitoring visits, will confirm distribution of these supplies to end-user locations, i.e. health facilities and reports on their use.

  - Provide details on the monitoring system(s) that are being used and how you identify and incorporate lessons learned into the ongoing programme/project: the monitoring system in place is usually through the MOH/DOH/PHC on the government side which is complemented by UNICEF contracted facilitators/ WHO focal points who in collaboration with MOH/DOH staff carry out regular visit to various facilities to oversee the implementation and collect relevant data for monitoring the progress in the implementation of EPI activities. Another mechanism is through the review of reports compiled by PHC, DOH and MOH on immunization coverage and other information related to EPI. In collaboration with WHO and other Cluster D members regular discussions meetings within the Cluster as well as MOH EPI officials are held on how to incorporate lessons learned to assure effective and improve delivery of immunization services.

  - Report on any assessments, evaluations or studies undertaken: through the use of other sources of funds UNICEF supported MOH to carry out household EPI coverage survey starting with three northern governorates in the third week of June 2007. The main purpose of the household EPI survey was to provide recent data on immunization coverage for all antigens in the three Kurdistan Region governorates; to identify reasons for not immunizing children and to monitor the April/May 2007 MMR campaign coverage and the impact of the mobile out reach immunization teams. The results of the survey expected in September 2007, will come out with the key recommendations on the strategies and interventions that will enhance the achievement and sustainability of EPI programme.

- Results

  - Provide a summary of programme/project progress in relation to planned outcomes and outputs; explain any variance in achieved versus planned outputs during the six month reporting period:

- Infant coverage of at least 80%, by all essential vaccines among infants was achieved in 50% of district.

- Poliovirus free status maintained during the reporting period.

- Measles elimination progressing as planned with >90% reduction in measles cases during the reporting period compared to 2004.

- Sentinel surveillance for rotavirus diarrhoea, streptococcus pneumonia and heamophilus influenza type b started in all 6 targeted hospitals

- Decentralize vaccine storage and management by the end of 2007, the work for decentralization of three regional vaccine stores (in Erbil, Basra and Babil) was initiated during the reporting period.

  - Report on progress made toward the achievement of specific medium-term outcomes of the programme/project as a result of the achieved short-term outputs during this reporting period.

Measles is considered as one of the main child hood killer disease, 90% reduction in measles cases will mean 90% reduction in mortality reduction due to measles.

  - Report on the key outputs achieved in the six month period including # and nature of the activities (inputs), % of completion and beneficiaries.

- Training of all province and national EPI managers and surveillance officers  on:

    - Reaching every district strategy to enhance infant and child immunization coverage.

    - Measles strategies and activities to achieve measles elimination by 2010.

    - Introduction of new and improved vaccines

      - Logistic support 145 province and district surveillance officers for active surveillance for Polio and other EPI targeted diseases.

      - Pre-measles campaign training of all vaccination teams ( 7176 vaccinators)  and field supervisors (1,024) on:

- Micro planning and mapping;

- The correct methods and precautions to maintain the cold chain system.

- How to reconstitute and correctly inject measles containing vaccine as well as environment friendly methods of disposal of used syringes and empty vials.

  - Implementation in April and May 2007 of a house to house nationwide MMR campaign. The number of children aged 12-59 months vaccinated in this campaign was 3549529 (92%). UNICEF provided support for transportation of around 2,000 vaccination teams for the MMR campaign as well as social mobilisation campaign.

  - Procurement of two million doses of OPV to be delivered soon in Baghdad which will contribute to the government efforts in maintaining polio free status.

  - Rehabilitation of the Erbil vaccine store started successfully during the reporting period and it is in good progress where the work has been completed to nearly 40% and on its finalization the vaccine store will have the capacity to store the vaccines for five northern governorates (Erbil, Suleimaniyah, Dohuk, Ninewah and Kirkuk). The bills of quantities for Babil and Basra vaccine stores have been issued and the process for contracting has started

  - Explain, if relevant, delays in programme/project implementation, the nature of the constraints, lessons learned in the process and actions taken to mitigate future delays.

- Real effort is needed to urge MNFI to create corridors of peace -during NIDs- for the safe passage of vaccination teams and supervisors.

- Military operations and curfews have always been the main obstacle for reaching and vaccinating children.

- Bad security condition is still prevailing and harmfully affecting health services provision. Nevertheless, Iraqi health staff maintain their performance through modifying scenarios to complete their work e.g. working in holidays, joining two or three vaccination teams to finish the work in one place peacefully and rapidly then shift to other one, avoid marking on houses in hot or risky areas to hide the movement of the vaccination teams.

- Social mobilization played a vital role in the high acceptance of immunization by families.

- Parents and the community in general were very supportive during the campaign which reflects their high believe in immunization program.

- There are some deficiencies in reporting and documentation. It is unbelievable that there are no adverse events from the vaccine in such big campaign and the percentage of children vaccinated for the first time was very low.

  - List the key partnerships and collaborations, and explain how such relationships impact on the achievement of results.

WHO main partner is MoH; the result of this collaboration is continuous capacity building in the field of immunization which is seen as crucial for the wider strengthening of the health systems and a major element of the effort to attain the millennium development goals.

WHO is providing technical and logistics support, in addition to coordination and leadership. UNICEF is providing support in the field of social mobilization and vaccine and cold chain equipment procurement. IRCS and medical schools are responsible for independent monitoring and play an important role internal reviews and technical and advisory committees.

  - Summarize achievements against planned results for cross cutting issues: security, gender, human rights, employment (including # of short and/or long-term jobs created), and environment.

All people – without distinction of gender, race, religion, political belief, economic or social condition, has a right to equal access to the needed vaccines.

The success of the EPI program was due to effort done in advocacy (specially for decision makers) and social mobilization to ensure that immunization is highly valued by all partners and actors at all levels and their solidarity in ensuring that all children irrespective of ethnicity or belief are vaccinated with vaccines that meets internationally recognized standards of quality and safety, and services are delivered according to best practices.

Provision of vaccine through house to house visits with special attention to high risk areas and population is the best methods to ensure equal opportunities irrespective of gender, race, and religion, and political belief, economic or social condition

- Future Work Plan

  - Summarize the projected activities up to the end of June 2007.

i. WHO

- Continuous advocacy; among policy makers to ensure that EPI remains high on the agenda of the MoH, MOPD and MOF to ensure enough financial support to maintain the gains in routine EPI coverage, measles elimination and interruption of poliovirus transmission.

- Further strengthening of Polio and measles case based surveillance and laboratory confirmation of suspect cases by the provision of standardized reagents, cell line, local and international training for laboratory and EPI governorate managers.

- Continuous weekly feed back and technical guidance from WHO technical units to governorate and MOH staff.

ii. UNICEF

- Support MOH to carry out two round Polio National Immunization Days in September and October in collaboration with WHO. UNICEF will provide support for social mobilisation, distribution of vaccines, registry book and transportation of vaccination teams.

- Continue Support the implementation of RED approach in the southern/central governorates through provision of support for capacity building as well logistic support to ensure that vaccination teams reach all areas with low immunization coverage.

- Procurement and delivery of supplies: cold chain equipments, safety boxes to MOH and DOH ware houses.

- Support mobile health teams for immunization out-reach services particularly in IDPs affected areas.

- Complete rehabilitation of the Erbil regional vaccine store and at the same time issues the contracts and start the rehabilitation/upgrading work for other two regional stores in Babil and Basra.